## Overall
| PROJECT : ECOCERES SUBSTRUCTURE WORKS | [18 empty] | Updated On : | 2024-05-10
| WEEKLY SCHEDULE & PROGRESS UPDATE |  | 202375369360256000 and 2116 |  |  |  |  | PASTE THIS FROM MS PROJECT |  | 2238233521382130
| CONTRACTOR | PACKAGE NO |  |  | Plan Start | Plan Finish |  | For Dyna Only | For Dyna Only | SPI |  |  |  |  | Plan % |  |  |  | Actual % |  | Delta
| DYNACIATE | ECOCERES SUBSTRUCTURE PACKAGE |  |  | 2023-11-29 | 2024-02-28 |  |  |  | -98 |  |  |  | -39 | 100% |  |  |  | 91.26% |  | -8.743%
| Activity ID | Activity Description | Sub sum | Plan Duration | Baseline Start | Baseline Finish | Actual / Forecast Start |  |  | Actual / Forecast Finish | Total Quantity |  |  | Installed Quantity | Unit | Plan Units | Cost | Weightage | Plan Prog % | Actual Prog % | Delta | Remark
| ECOCERES SUBSTRUCTURE PACKAGE |  | 11395 | 92 | 2023-11-29 | 2024-02-28 | 2023-11-27 | Start | Finish | 2024-06-05 |  | MSP Paste Here | Check Here |  |  |  |  | 100% | 100% | 91.26% | -8.743%
147 | UNIT 700, 800 and 900 (SUBSTRUCTURE) |  | 8924 | 92 | 2023-11-29 | 2024-02-28 | 2023-11-27 | 2023-11-27 | 2024-06-05 | 2024-06-05 |  | 0.01 | [5 empty] | 78.32% | 100% | 93.55% | -6.449%
148 | Unit 700 - Auxillary & Tank Yard |  | 819 | 73 | 2023-12-05 | 2024-02-15 | 2023-12-05 | 2023-12-05 | 2024-06-05 | 2024-06-05 |  | 0 | [5 empty] | 9.177% | 100% | 61.47% | -38.53%
149 | Piling (Cutting only) |  | 7 | 7 | 2023-12-05 | 2023-12-11 | 2023-12-05 | 2023-12-05 | 2023-12-11 | 2023-12-11 |  | 0 | [5 empty] | 0.8547% | 100% | 100% | 0%
150 | Cutting off Pile to GL |  | 7 | 7 | 2023-12-05 | 2023-12-11 | 2023-12-05 | 2023-12-05 | 2023-12-11 | 2023-12-11 | 100 | 0 | 0 | 100 | % | 100 |  | 100% | 100% | 100% | 0%
151 | Completion of Piling |  | 0 | 1 | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2023-12-11 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
152 | Substructure |  | 812 | 62 | 2023-12-16 | 2024-02-15 | 2024-01-22 | 2024-01-22 | 2024-06-05 | 2024-06-05 |  | 0 | [5 empty] | 99.15% | 100% | 61.14% | -38.86%
153 | Structure |  | 313 | 56 | 2023-12-16 | 2024-02-09 | 2024-04-01 | 2024-04-01 | 2024-06-05 | 2024-06-05 |  | 0 | [5 empty] | 38.55% | 100% | 87.99% | -12.01%
154 | Pile Cap |  | 188 | 41 | 2023-12-16 | 2024-01-25 | 2024-04-01 | 2024-04-01 | 2024-05-21 | 2024-05-21 |  | 0 | [5 empty] | 60.06% | 100% | 94.47% | -5.532%
155 | Excavation |  | 21 | 21 | 2023-12-16 | 2024-01-05 | 2024-04-01 | 2024-04-01 | 2024-04-13 | 2024-04-13 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
156 | Leveling and Compaction |  | 21 | 21 | 2023-12-19 | 2024-01-08 | 2024-04-02 | 2024-04-02 | 2024-04-16 | 2024-04-16 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
157 | Lean Concrete Pouring |  | 21 | 21 | 2023-12-20 | 2024-01-09 | 2024-04-05 | 2024-04-05 | 2024-04-18 | 2024-04-18 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
158 | Pile Cutting and Treatment |  | 21 | 21 | 2023-12-22 | 2024-01-11 | 2024-04-05 | 2024-04-05 | 2024-04-20 | 2024-04-20 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
159 | Reinforcement Bar Fixing |  | 21 | 21 | 2023-12-26 | 2024-01-15 | 2024-04-12 | 2024-04-12 | 2024-04-25 | 2024-04-25 | 100 | 0 | 0 | 90 | % | 100 |  | 11.17% | 100% | 90% | -10%
160 | Formwork Fixing |  | 21 | 21 | 2023-12-29 | 2024-01-18 | 2024-05-01 | 2024-05-01 | 2024-05-14 | 2024-05-14 | 100 | 0 | 0 | 90 | % | 100 |  | 11.17% | 100% | 90% | -10%
161 | Concrete Pouring |  | 20 | 20 | 2024-01-01 | 2024-01-20 | 2024-05-03 | 2024-05-03 | 2024-05-16 | 2024-05-16 | 100 | 0 | 0 | 90 | % | 100 |  | 10.64% | 100% | 90% | -10%
162 | Formwork Dismantling |  | 21 | 21 | 2024-01-04 | 2024-01-24 | 2024-05-07 | 2024-05-07 | 2024-05-20 | 2024-05-20 | 100 | 0 | 0 | 90 | % | 100 |  | 11.17% | 100% | 90% | -10%
163 | Backfill with compaction |  | 21 | 21 | 2024-01-05 | 2024-01-25 | 2024-05-08 | 2024-05-08 | 2024-05-21 | 2024-05-21 | 100 | 0 | 0 | 90 | % | 100 |  | 11.17% | 100% | 90% | -10%
164 | Completion of Pile Cap |  | 0 | 1 | 2024-01-25 | 2024-01-25 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
165 | Stump |  | 125 | 33 | 2024-01-08 | 2024-02-09 | 2024-05-10 | 2024-05-10 | 2024-06-05 | 2024-06-05 |  | 0 | [5 empty] | 39.94% | 100% | 78.24% | -21.76%
166 | Reinforcement Bar Fixing |  | 20 | 20 | 2024-01-08 | 2024-01-27 | 2024-05-10 | 2024-05-10 | 2024-05-23 | 2024-05-23 | 100 | 0 | 0 | 90 | % | 100 |  | 16% | 100% | 90% | -10%
167 | Formwork Fixing |  | 21 | 21 | 2024-01-10 | 2024-01-30 | 2024-05-13 | 2024-05-13 | 2024-05-25 | 2024-05-25 | 100 | 0 | 0 | 90 | % | 100 |  | 16.8% | 100% | 90% | -10%
168 | Anchor Bolt Fixing |  | 21 | 21 | 2024-01-12 | 2024-02-01 | 2024-05-15 | 2024-05-15 | 2024-05-28 | 2024-05-28 | 100 | 0 | 0 | 90 | % | 100 |  | 16.8% | 100% | 90% | -10%
169 | Concrete Pouring |  | 21 | 21 | 2024-01-16 | 2024-02-05 | 2024-05-18 | 2024-05-18 | 2024-05-31 | 2024-05-31 | 100 | 0 | 0 | 90 | % | 100 |  | 16.8% | 100% | 90% | -10%
170 | Formwork Dismantling |  | 21 | 21 | 2024-01-19 | 2024-02-08 | 2024-05-22 | 2024-05-22 | 2024-06-04 | 2024-06-04 | 100 | 0 | 0 | 90 | % | 100 |  | 16.8% | 100% | 90% | -10%
171 | Backfill with compaction |  | 21 | 21 | 2024-01-20 | 2024-02-09 | 2024-05-23 | 2024-05-23 | 2024-06-05 | 2024-06-05 | 100 | 0 | 0 | 20 | % | 100 |  | 16.8% | 100% | 20% | -80%
172 | Completion of Stump |  | 0 | 1 | 2024-02-09 | 2024-02-09 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
173 | Completion of Structure |  | 0 | 1 | 2024-02-09 | 2024-02-09 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
174 | Tank / Equipment and Pump Foundation |  | 185 | 42 | 2024-01-05 | 2024-02-15 | 2024-01-25 | 2024-01-25 | 2024-03-23 | 2024-03-23 |  | 0 | [5 empty] | 22.78% | 100% | 100% | 0%
175 | Tank / Equipment Foundation |  | 185 | 42 | 2024-01-05 | 2024-02-15 | 2024-01-25 | 2024-01-25 | 2024-03-23 | 2024-03-23 |  | 0 | [5 empty] | 100% | 100% | 100% | 0%
176 | Excavation |  | 19 | 19 | 2024-01-05 | 2024-01-23 | 2024-01-25 | 2024-01-25 | 2024-02-12 | 2024-02-12 | 100 | 0 | 0 | 100 | % | 100 |  | 10.27% | 100% | 100% | 0%
177 | Leveling and Compaction |  | 18 | 18 | 2024-01-08 | 2024-01-25 | 2024-02-03 | 2024-02-03 | 2024-02-13 | 2024-02-13 | 100 | 0 | 0 | 100 | % | 100 |  | 9.73% | 100% | 100% | 0%
178 | Lean Concrete Pouring |  | 18 | 18 | 2024-01-09 | 2024-01-26 | 2024-02-06 | 2024-02-06 | 2024-02-19 | 2024-02-19 | 100 | 0 | 0 | 100 | % | 100 |  | 9.73% | 100% | 100% | 0%
179 | Pile Cutting and Treatment |  | 19 | 19 | 2024-01-11 | 2024-01-29 | 2024-02-07 | 2024-02-07 | 2024-02-20 | 2024-02-20 | 100 | 0 | 0 | 100 | % | 100 |  | 10.27% | 100% | 100% | 0%
180 | Reinforcement Bar Fixing |  | 18 | 18 | 2024-01-15 | 2024-02-01 | 2024-02-08 | 2024-02-08 | 2024-02-29 | 2024-02-29 | 100 | 0 | 0 | 100 | % | 100 |  | 9.73% | 100% | 100% | 0%
181 | Formwork Fixing |  | 19 | 19 | 2024-01-18 | 2024-02-05 | 2024-02-13 | 2024-02-13 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 10.27% | 100% | 100% | 0%
182 | Anchor Bolt / Inserted Plate Fixing |  | 19 | 19 | 2024-01-20 | 2024-02-07 | 2024-02-24 | 2024-02-24 | 2024-03-19 | 2024-03-19 | 100 | 0 | 0 | 100 | % | 100 |  | 10.27% | 100% | 100% | 0%
183 | Concrete Pouring |  | 18 | 18 | 2024-01-24 | 2024-02-10 | 2024-02-27 | 2024-02-27 | 2024-03-20 | 2024-03-20 | 100 | 0 | 0 | 100 | % | 100 |  | 9.73% | 100% | 100% | 0%
184 | Formwork Dismantling |  | 19 | 19 | 2024-01-27 | 2024-02-14 | 2024-03-01 | 2024-03-01 | 2024-03-21 | 2024-03-21 | 100 | 0 | 0 | 100 | % | 100 |  | 10.27% | 100% | 100% | 0%
185 | Backfill with compaction |  | 18 | 18 | 2024-01-29 | 2024-02-15 | 2024-03-02 | 2024-03-02 | 2024-03-23 | 2024-03-23 | 100 | 0 | 0 | 100 | % | 100 |  | 9.73% | 100% | 100% | 0%
186 | Completion of Tank / Equipment |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
187 | Completion of Tank / Equipment and Pump Foundation |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
188 | General |  | 314 | 58 | 2023-12-20 | 2024-02-15 | 2024-01-22 | 2024-01-22 | 2024-04-06 | 2024-04-06 |  | 0 | [5 empty] | 38.67% | 100% | 11.48% | -88.52%
189 | Pipe Gallery |  | 188 | 56 | 2023-12-20 | 2024-02-13 | 2024-01-22 | 2024-01-22 | 2024-04-06 | 2024-04-06 |  | 0 | [5 empty] | 59.87% | 100% | 13.96% | -86.04%
190 | Pile Cap |  | 188 | 41 | 2023-12-20 | 2024-01-29 | 2024-01-22 | 2024-01-22 | 2024-04-06 | 2024-04-06 |  | 0 | [5 empty] | 100% | 100% | 13.96% | -86.04%
191 | Excavation |  | 21 | 21 | 2023-12-20 | 2024-01-09 | 2024-01-22 | 2024-01-22 | 2024-04-06 | 2024-04-06 | 100 | 0 | 0 | 75 | % | 100 |  | 11.17% | 100% | 75% | -25%
192 | Leveling and Compaction |  | 21 | 21 | 2023-12-22 | 2024-01-11 | 2024-01-24 | 2024-01-24 | 2024-02-06 | 2024-02-06 | 100 | 0 | 0 | 50 | % | 100 |  | 11.17% | 100% | 50% | -50%
193 | Lean Concrete Pouring |  | 21 | 21 | 2023-12-23 | 2024-01-12 | 2024-01-25 | 2024-01-25 | 2024-02-07 | 2024-02-07 | 100 | 0 | 0 |  | % | 100 |  | 11.17% | 100% | 0% | -100%
194 | Pile Cutting and Treatment |  | 21 | 21 | 2023-12-26 | 2024-01-15 | 2024-01-27 | 2024-01-27 | 2024-02-09 | 2024-02-09 | 100 | 0 | 0 |  | % | 100 |  | 11.17% | 100% | 0% | -100%
195 | Reinforcement Bar Fixing |  | 21 | 21 | 2023-12-29 | 2024-01-18 | 2024-01-31 | 2024-01-31 | 2024-02-13 | 2024-02-13 | 100 | 0 | 0 |  | % | 100 |  | 11.17% | 100% | 0% | -100%
196 | Formwork Fixing |  | 21 | 21 | 2024-01-02 | 2024-01-22 | 2024-02-03 | 2024-02-03 | 2024-02-16 | 2024-02-16 | 100 | 0 | 0 |  | % | 100 |  | 11.17% | 100% | 0% | -100%
197 | Concrete Pouring |  | 21 | 21 | 2024-01-04 | 2024-01-24 | 2024-02-06 | 2024-02-06 | 2024-02-19 | 2024-02-19 | 100 | 0 | 0 |  | % | 100 |  | 11.17% | 100% | 0% | -100%
198 | Formwork Dismantling |  | 20 | 20 | 2024-01-08 | 2024-01-27 | 2024-02-09 | 2024-02-09 | 2024-02-22 | 2024-02-22 | 100 | 0 | 0 |  | % | 100 |  | 10.64% | 100% | 0% | -100%
199 | Backfill with compaction |  | 21 | 21 | 2024-01-09 | 2024-01-29 | 2024-02-10 | 2024-02-10 | 2024-02-23 | 2024-02-23 | 100 | 0 | 0 |  | % | 100 |  | 11.17% | 100% | 0% | -100%
200 | Completion of Pile Cap |  | 0 | 1 | 2024-01-29 | 2024-01-29 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
201 | Completion of Pipe Gallery |  | 0 | 1 | 2024-02-13 | 2024-02-13 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
202 | Tank Yard Slab with Cofferdam |  | 126 | 36 | 2024-01-11 | 2024-02-15 | 2024-02-13 | 2024-02-13 | 2024-03-19 | 2024-03-19 |  | 0 | [5 empty] | 40.13% | 100% | 7.778% | -92.22%
203 | Tank Yard Slab |  | 98 | 31 | 2024-01-11 | 2024-02-10 | 2024-02-13 | 2024-02-13 | 2024-03-07 | 2024-03-07 |  | 0 | [5 empty] | 77.78% | 100% | 10% | -90%
204 | Leveling and Compaction |  | 14 | 14 | 2024-01-11 | 2024-01-24 | 2024-02-13 | 2024-02-13 | 2024-02-19 | 2024-02-19 | 100 | 0 | 0 | 70 | % | 100 |  | 14.29% | 100% | 70% | -30%
205 | Sub Base Laying and Compaction |  | 14 | 14 | 2024-01-13 | 2024-01-26 | 2024-02-15 | 2024-02-15 | 2024-02-21 | 2024-02-21 | 100 | 0 | 0 |  | % | 100 |  | 14.29% | 100% | 0% | -100%
206 | Lean Concrete Pouring |  | 14 | 14 | 2024-01-16 | 2024-01-29 | 2024-02-17 | 2024-02-17 | 2024-02-23 | 2024-02-23 | 100 | 0 | 0 |  | % | 100 |  | 14.29% | 100% | 0% | -100%
207 | Reinforcement Bar Fixing |  | 14 | 14 | 2024-01-17 | 2024-01-30 | 2024-02-19 | 2024-02-19 | 2024-02-24 | 2024-02-24 | 100 | 0 | 0 |  | % | 100 |  | 14.29% | 100% | 0% | -100%
208 | Formwork Fixing |  | 13 | 13 | 2024-01-22 | 2024-02-03 | 2024-02-23 | 2024-02-23 | 2024-02-29 | 2024-02-29 | 100 | 0 | 0 |  | % | 100 |  | 13.27% | 100% | 0% | -100%
209 | Concrete Pouring |  | 14 | 14 | 2024-01-24 | 2024-02-06 | 2024-02-26 | 2024-02-26 | 2024-03-02 | 2024-03-02 | 100 | 0 | 0 |  | % | 100 |  | 14.29% | 100% | 0% | -100%
210 | Formwork Dismantling |  | 14 | 14 | 2024-01-27 | 2024-02-09 | 2024-02-29 | 2024-02-29 | 2024-03-06 | 2024-03-06 | 100 | 0 | 0 |  | % | 100 |  | 14.29% | 100% | 0% | -100%
211 | Backfill with compaction |  | 1 | 1 | 2024-02-10 | 2024-02-10 | 2024-03-07 | 2024-03-07 | 2024-03-07 | 2024-03-07 | 100 | 0 | 0 |  | % | 100 |  | 1.02% | 100% | 0% | -100%
212 | Cofferdam Wall |  | 28 | 20 | 2024-01-27 | 2024-02-15 | 2024-02-29 | 2024-02-29 | 2024-03-19 | 2024-03-19 |  | 0 | [5 empty] | 22.22% | 100% | 0% | -100%
213 | Reinforcement Bar Fixing |  | 7 | 7 | 2024-01-27 | 2024-02-02 | 2024-02-29 | 2024-02-29 | 2024-03-06 | 2024-03-06 | 100 | 0 | 0 |  | % | 100 |  | 25% | 100% | 0% | -100%
214 | Formwork Fixing |  | 7 | 7 | 2024-02-03 | 2024-02-09 | 2024-03-07 | 2024-03-07 | 2024-03-13 | 2024-03-13 | 100 | 0 | 0 |  | % | 100 |  | 25% | 100% | 0% | -100%
215 | Concrete Pouring |  | 7 | 7 | 2024-02-06 | 2024-02-12 | 2024-03-09 | 2024-03-09 | 2024-03-15 | 2024-03-15 | 100 | 0 | 0 |  | % | 100 |  | 25% | 100% | 0% | -100%
216 | Formwork Dismantling |  | 7 | 7 | 2024-02-09 | 2024-02-15 | 2024-03-13 | 2024-03-13 | 2024-03-19 | 2024-03-19 | 100 | 0 | 0 |  | % | 100 |  | 25% | 100% | 0% | -100%
217 | Completion of Tank Yard Slab with Cofferdam |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 2024-03-19 | 2024-03-19 | 2024-03-19 | 2024-03-19 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
218 | Completion of General |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
219 | Completion of Substructure |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
220 | Completion of Unit 700 - Auxillary & Tank Yard |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
221 | Unit 700 - Frame & Auxillary Room |  | 552 | 73 | 2023-12-05 | 2024-02-15 | 2023-12-05 | 2023-12-05 | 2024-05-18 | 2024-05-18 |  | 0.02 | [5 empty] | 6.186% | 100% | 57.28% | -42.72%
222 | Piling (Cutting only) |  | 9 | 9 | 2023-12-05 | 2023-12-13 | 2023-12-05 | 2023-12-05 | 2023-12-13 | 2023-12-13 |  | 1 | [5 empty] | 1.63% | 100% | 100% | 0%
223 | Cutting off Pile to GL |  | 9 | 9 | 2023-12-05 | 2023-12-13 | 2023-12-05 | 2023-12-05 | 2023-12-13 | 2023-12-13 | 100 | 1 | 100 | 100 | % | 100 |  | 100% | 100% | 100% | 0%
224 | Completion of Piling |  | 0 | 1 | 2023-12-13 | 2023-12-13 | 2023-12-13 | 2023-12-13 | 2023-12-13 | 2023-12-13 | 100 | 1 | 100 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
225 | Substructure |  | 543 | 62 | 2023-12-16 | 2024-02-15 | 2023-12-12 | 2023-12-12 | 2024-05-18 | 2024-05-18 |  | 0 | [5 empty] | 98.37% | 100% | 56.57% | -43.43%
226 | Structure |  | 266 | 62 | 2023-12-16 | 2024-02-15 | 2023-12-12 | 2023-12-12 | 2024-04-26 | 2024-04-26 |  | 0 | [5 empty] | 48.99% | 100% | 96.5% | -3.496%
227 | Pile Cap |  | 240 | 47 | 2023-12-16 | 2024-01-31 | 2023-12-12 | 2023-12-12 | 2024-04-26 | 2024-04-26 |  | 0 | [5 empty] | 90.23% | 100% | 96.67% | -3.333%
228 | Excavation |  | 27 | 27 | 2023-12-16 | 2024-01-11 | 2023-12-12 | 2023-12-12 | 2024-03-07 | 2024-03-07 | 100 | 0 | 0 | 100 | % | 100 |  | 11.25% | 100% | 100% | 0%
229 | Leveling and Compaction |  | 26 | 26 | 2023-12-19 | 2024-01-13 | 2023-12-14 | 2023-12-14 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 10.83% | 100% | 100% | 0%
230 | Lean Concrete Pouring |  | 27 | 27 | 2023-12-20 | 2024-01-15 | 2023-12-16 | 2023-12-16 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 11.25% | 100% | 100% | 0%
231 | Pile Cutting and Treatment |  | 27 | 27 | 2023-12-22 | 2024-01-17 | 2023-12-20 | 2023-12-20 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 | 95 | % | 100 |  | 11.25% | 100% | 95% | -5%
232 | Reinforcement Bar Fixing |  | 26 | 26 | 2023-12-26 | 2024-01-20 | 2023-12-21 | 2023-12-21 | 2024-01-18 | 2024-01-18 | 100 | 0 | 0 | 95 | % | 100 |  | 10.83% | 100% | 95% | -5%
233 | Formwork Fixing |  | 27 | 27 | 2023-12-29 | 2024-01-24 | 2023-12-21 | 2023-12-21 | 2024-01-19 | 2024-01-19 | 100 | 0 | 0 | 95 | % | 100 |  | 11.25% | 100% | 95% | -5%
234 | Concrete Pouring |  | 26 | 26 | 2024-01-01 | 2024-01-26 | 2024-01-02 | 2024-01-02 | 2024-01-27 | 2024-01-27 | 100 | 0 | 0 | 95 | % | 100 |  | 10.83% | 100% | 95% | -5%
235 | Formwork Dismantling |  | 27 | 27 | 2024-01-04 | 2024-01-30 | 2024-01-05 | 2024-01-05 | 2024-01-31 | 2024-01-31 | 100 | 0 | 0 | 95 | % | 100 |  | 11.25% | 100% | 95% | -5%
236 | Backfill with compaction |  | 27 | 27 | 2024-01-05 | 2024-01-31 | 2024-01-06 | 2024-01-06 | 2024-02-01 | 2024-02-01 | 100 | 0 | 0 | 95 | % | 100 |  | 11.25% | 100% | 95% | -5%
237 | Completion of Pile Cap |  | 0 | 1 | 2024-01-31 | 2024-01-31 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
238 | Stump | Reinforcement Bar only | 26 | 39 | 2024-01-08 | 2024-02-15 | 2023-12-28 | 2023-12-28 | 2024-01-23 | 2024-01-23 |  | 0 | [5 empty] | 9.774% | 100% | 95% | -5%
239 | Reinforcement Bar Fixing |  | 26 | 26 | 2024-01-08 | 2024-02-02 | 2023-12-28 | 2023-12-28 | 2024-01-23 | 2024-01-23 | 100 | 0 | 0 | 95 | % | 100 |  | 100% | 100% | 95% | -5%
240 | Completion of Stump |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 2024-01-23 | 2024-01-23 | 2024-01-23 | 2024-01-23 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
241 | Completion of Structure |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
242 | Underground Pits (RV 7903 and 7902) |  | 54 | 62 | 2023-12-16 | 2024-02-15 | 2024-01-04 | 2024-01-04 | 2024-05-18 | 2024-05-18 |  | 0 | [5 empty] | 9.945% | 100% | 93.52% | -6.481%
243 | Temporary Sheet Pile |  | 6 | 6 | 2023-12-16 | 2023-12-21 | 2024-01-04 | 2024-01-04 | 2024-01-25 | 2024-01-25 | 100 | 0 | 0 | 100 | % | 100 |  | 11.11% | 100% | 100% | 0%
244 | Excavation |  | 15 | 15 | 2023-12-22 | 2024-01-05 | 2024-01-10 | 2024-01-10 | 2024-01-30 | 2024-01-30 | 100 | 0 | 0 | 100 | % | 100 |  | 27.78% | 100% | 100% | 0%
245 | Leveling and Compaction |  | 3 | 3 | 2023-12-27 | 2023-12-29 | 2024-01-31 | 2024-01-31 | 2024-02-01 | 2024-02-01 | 100 | 0 | 0 | 100 | % | 100 |  | 5.556% | 100% | 100% | 0%
246 | Lean Concrete Pouring |  | 1 | 1 | 2024-01-06 | 2024-01-06 | 2024-02-02 | 2024-02-02 | 2024-02-02 | 2024-02-02 | 100 | 0 | 0 | 100 | % | 100 |  | 1.852% | 100% | 100% | 0%
247 | Base |  | 7 | 8 | 2024-01-08 | 2024-01-15 | 2024-02-29 | 2024-02-29 | 2024-04-05 | 2024-04-05 |  | 0 | [5 empty] | 12.96% | 100% | 100% | 0%
248 | Reinforcement Bar Fixing |  | 4 | 4 | 2024-01-08 | 2024-01-11 | 2024-02-29 | 2024-02-29 | 2024-04-01 | 2024-04-01 | 100 | 0 | 0 | 100 | % | 100 |  | 57.14% | 100% | 100% | 0%
249 | Formwork Fixing |  | 2 | 2 | 2024-01-12 | 2024-01-13 | 2024-04-02 | 2024-04-02 | 2024-04-04 | 2024-04-04 | 100 | 0 | 0 | 100 | % | 100 |  | 28.57% | 100% | 100% | 0%
250 | Concrete Pouring |  | 1 | 1 | 2024-01-15 | 2024-01-15 | 2024-04-05 | 2024-04-05 | 2024-04-05 | 2024-04-05 | 100 | 0 | 0 | 100 | % | 100 |  | 14.29% | 100% | 100% | 0%
251 | Wall |  | 19 | 19 | 2024-01-16 | 2024-02-03 | 2024-04-23 | 2024-04-23 | 2024-05-07 | 2024-05-07 |  | 0 | [5 empty] | 35.19% | 100% | 97.37% | -2.632%
252 | Reinforcement Bar Fixing |  | 9 | 9 | 2024-01-16 | 2024-01-24 | 2024-04-23 | 2024-04-23 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 | 100 | % | 100 |  | 47.37% | 100% | 100% | 0%
253 | Formwork Fixing |  | 9 | 9 | 2024-01-25 | 2024-02-02 | 2024-04-26 | 2024-04-26 | 2024-05-06 | 2024-05-06 | 100 | 0 | 0 | 100 | % | 100 |  | 47.37% | 100% | 100% | 0%
254 | Concrete Pouring |  | 1 | 1 | 2024-02-03 | 2024-02-03 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 100 | 0 | 0 | 50 | % | 100 |  | 5.263% | 100% | 50% | -50%
255 | Formwork Dismantling |  | 1 | 1 | 2024-02-13 | 2024-02-13 | 2024-05-16 | 2024-05-16 | 2024-05-16 | 2024-05-16 | 100 | 0 | 0 |  | % | 100 |  | 1.852% | 100% | 0% | -100%
256 | Backfill with compaction |  | 2 | 2 | 2024-02-14 | 2024-02-15 | 2024-05-17 | 2024-05-17 | 2024-05-18 | 2024-05-18 | 100 | 0 | 0 |  | % | 100 |  | 3.704% | 100% | 0% | -100%
257 | Completion of Underground Pits |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
258 | Tank / Equipment and Pump Foundation |  | 223 | 42 | 2024-01-05 | 2024-02-15 | 2024-01-06 | 2024-01-06 | 2024-02-05 | 2024-02-05 |  | 0 | [5 empty] | 41.07% | 100% | 0% | -100%
259 | Tank / Equipment Foundation |  | 223 | 42 | 2024-01-05 | 2024-02-15 | 2024-01-06 | 2024-01-06 | 2024-02-05 | 2024-02-05 |  | 0 | [5 empty] | 100% | 100% | 0% | -100%
260 | Excavation |  | 23 | 23 | 2024-01-05 | 2024-01-27 | 2024-01-06 | 2024-01-06 | 2024-01-12 | 2024-01-12 | 100 | 0 | 0 |  | % | 100 |  | 10.31% | 100% | 0% | -100%
261 | Leveling and Compaction |  | 23 | 23 | 2024-01-08 | 2024-01-30 | 2024-01-09 | 2024-01-09 | 2024-01-15 | 2024-01-15 | 100 | 0 | 0 |  | % | 100 |  | 10.31% | 100% | 0% | -100%
262 | Lean Concrete Pouring |  | 23 | 23 | 2024-01-09 | 2024-01-31 | 2024-01-10 | 2024-01-10 | 2024-01-16 | 2024-01-16 | 100 | 0 | 0 |  | % | 100 |  | 10.31% | 100% | 0% | -100%
263 | Pile Cutting and Treatment |  | 23 | 23 | 2024-01-11 | 2024-02-02 | 2024-01-12 | 2024-01-12 | 2024-01-18 | 2024-01-18 | 100 | 0 | 0 |  | % | 100 |  | 10.31% | 100% | 0% | -100%
264 | Reinforcement Bar Fixing |  | 23 | 23 | 2024-01-15 | 2024-02-06 | 2024-01-16 | 2024-01-16 | 2024-01-22 | 2024-01-22 | 100 | 0 | 0 |  | % | 100 |  | 10.31% | 100% | 0% | -100%
265 | Formwork Fixing |  | 23 | 23 | 2024-01-18 | 2024-02-09 | 2024-01-19 | 2024-01-19 | 2024-01-25 | 2024-01-25 | 100 | 0 | 0 |  | % | 100 |  | 10.31% | 100% | 0% | -100%
266 | Anchor Bolt / Inserted Plate Fixing |  | 24 | 24 | 2024-01-20 | 2024-02-12 | 2024-01-22 | 2024-01-22 | 2024-01-27 | 2024-01-27 | 100 | 0 | 0 |  | % | 100 |  | 10.76% | 100% | 0% | -100%
267 | Concrete Pouring |  | 23 | 23 | 2024-01-24 | 2024-02-15 | 2024-01-25 | 2024-01-25 | 2024-01-31 | 2024-01-31 | 100 | 0 | 0 |  | % | 100 |  | 10.31% | 100% | 0% | -100%
268 | Formwork Dismantling |  | 20 | 20 | 2024-01-27 | 2024-02-15 | 2024-01-29 | 2024-01-29 | 2024-02-03 | 2024-02-03 | 100 | 0 | 0 |  | % | 100 |  | 8.969% | 100% | 0% | -100%
269 | Backfill with compaction |  | 18 | 18 | 2024-01-29 | 2024-02-15 | 2024-01-30 | 2024-01-30 | 2024-02-05 | 2024-02-05 | 100 | 0 | 0 |  | % | 100 |  | 8.072% | 100% | 0% | -100%
270 | Completion of Tank / Equipment |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-02-05 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
271 | Completion of Tank / Equipment and Pump Foundation |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-02-05 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
272 | Completion of Substructure |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
273 | Completion of Unit 700 - Frame & Auxillary Room |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
274 | Unit 800 - Compressor Shed |  | 1429 | 92 | 2023-11-29 | 2024-02-28 | 2023-11-27 | 2023-11-27 | 2024-03-16 | 2024-03-16 |  | 0.02 | [5 empty] | 16.01% | 100% | 98.89% | -1.109%
275 | Piling (Cutting only) |  | 21 | 21 | 2023-11-29 | 2023-12-19 | 2023-11-29 | 2023-11-29 | 2023-12-19 | 2023-12-19 |  | 1 | [5 empty] | 1.47% | 100% | 100% | 0%
276 | Cutting off Pile to GL |  | 21 | 21 | 2023-11-29 | 2023-12-19 | 2023-11-29 | 2023-11-29 | 2023-12-19 | 2023-12-19 | 100 | 1 | 100 | 100 | % | 100 |  | 100% | 100% | 100% | 0%
277 | Completion of Piling |  | 0 | 1 | 2023-12-19 | 2023-12-19 | 2023-12-19 | 2023-12-19 | 2023-12-19 | 2023-12-19 | 100 | 1 | 100 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
278 | Substructure |  | 1408 | 89 | 2023-12-02 | 2024-02-28 | 2023-11-27 | 2023-11-27 | 2024-03-16 | 2024-03-16 |  | 0 | [5 empty] | 98.53% | 100% | 98.87% | -1.126%
279 | Structure |  | 642 | 63 | 2023-12-02 | 2024-02-02 | 2023-11-27 | 2023-11-27 | 2024-02-28 | 2024-02-28 |  | 0 | [5 empty] | 45.6% | 100% | 100% | 0%
280 | Pile Cap |  | 251 | 48 | 2023-12-02 | 2024-01-18 | 2023-11-27 | 2023-11-27 | 2024-01-26 | 2024-01-26 |  | 0 | [5 empty] | 39.1% | 100% | 100% | 0%
281 | Excavation |  | 28 | 28 | 2023-12-02 | 2023-12-29 | 2023-11-27 | 2023-11-27 | 2024-01-09 | 2024-01-09 | 100 | 0 | 0 | 100 | % | 100 |  | 11.16% | 100% | 100% | 0%
282 | Leveling and Compaction |  | 28 | 28 | 2023-12-05 | 2024-01-01 | 2023-11-30 | 2023-11-30 | 2024-01-10 | 2024-01-10 | 100 | 0 | 0 | 100 | % | 100 |  | 11.16% | 100% | 100% | 0%
283 | Lean Concrete Pouring |  | 28 | 28 | 2023-12-06 | 2024-01-02 | 2023-12-05 | 2023-12-05 | 2024-01-12 | 2024-01-12 | 100 | 0 | 0 | 100 | % | 100 |  | 11.16% | 100% | 100% | 0%
284 | Pile Cutting and Treatment |  | 28 | 28 | 2023-12-08 | 2024-01-04 | 2023-12-08 | 2023-12-08 | 2024-01-12 | 2024-01-12 | 100 | 0 | 0 | 100 | % | 100 |  | 11.16% | 100% | 100% | 0%
285 | Reinforcement Bar Fixing |  | 28 | 28 | 2023-12-12 | 2024-01-08 | 2023-12-12 | 2023-12-12 | 2024-01-16 | 2024-01-16 | 100 | 0 | 0 | 100 | % | 100 |  | 11.16% | 100% | 100% | 0%
286 | Formwork Fixing |  | 28 | 28 | 2023-12-15 | 2024-01-11 | 2023-12-12 | 2023-12-12 | 2024-01-16 | 2024-01-16 | 100 | 0 | 0 | 100 | % | 100 |  | 11.16% | 100% | 100% | 0%
287 | Concrete Pouring |  | 27 | 27 | 2023-12-18 | 2024-01-13 | 2023-12-18 | 2023-12-18 | 2024-01-16 | 2024-01-16 | 100 | 0 | 0 | 100 | % | 100 |  | 10.76% | 100% | 100% | 0%
288 | Formwork Dismantling |  | 28 | 28 | 2023-12-21 | 2024-01-17 | 2023-12-20 | 2023-12-20 | 2024-01-19 | 2024-01-19 | 100 | 0 | 0 | 100 | % | 100 |  | 11.16% | 100% | 100% | 0%
289 | Backfill with compaction |  | 28 | 28 | 2023-12-22 | 2024-01-18 | 2024-01-03 | 2024-01-03 | 2024-01-26 | 2024-01-26 | 100 | 0 | 0 | 100 | % | 100 |  | 11.16% | 100% | 100% | 0%
290 | Completion of Pile Cap |  | 0 | 1 | 2024-01-18 | 2024-01-18 | 2024-01-26 | 2024-01-26 | 2024-01-26 | 2024-01-26 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
291 | Stump |  | 167 | 40 | 2023-12-25 | 2024-02-02 | 2023-12-21 | 2023-12-21 | 2024-02-28 | 2024-02-28 |  | 0 | [5 empty] | 26.01% | 100% | 100% | 0%
292 | Reinforcement Bar Fixing |  | 27 | 27 | 2023-12-25 | 2024-01-20 | 2023-12-21 | 2023-12-21 | 2024-01-17 | 2024-01-17 | 100 | 0 | 0 | 100 | % | 100 |  | 16.17% | 100% | 100% | 0%
293 | Formwork Fixing |  | 28 | 28 | 2023-12-27 | 2024-01-23 | 2024-01-11 | 2024-01-11 | 2024-02-02 | 2024-02-02 | 100 | 0 | 0 | 100 | % | 100 |  | 16.77% | 100% | 100% | 0%
294 | Anchor Bolt Fixing |  | 28 | 28 | 2023-12-29 | 2024-01-25 | 2024-01-11 | 2024-01-11 | 2024-02-07 | 2024-02-07 | 100 | 0 | 0 | 100 | % | 100 |  | 16.77% | 100% | 100% | 0%
295 | Concrete Pouring |  | 28 | 28 | 2024-01-02 | 2024-01-29 | 2024-01-18 | 2024-01-18 | 2024-02-08 | 2024-02-08 | 100 | 0 | 0 | 100 | % | 100 |  | 16.77% | 100% | 100% | 0%
296 | Formwork Dismantling |  | 28 | 28 | 2024-01-05 | 2024-02-01 | 2024-01-22 | 2024-01-22 | 2024-02-09 | 2024-02-09 | 100 | 0 | 0 | 100 | % | 100 |  | 16.77% | 100% | 100% | 0%
297 | Backfill with compaction |  | 28 | 28 | 2024-01-06 | 2024-02-02 | 2024-02-02 | 2024-02-02 | 2024-02-28 | 2024-02-28 | 100 | 0 | 0 | 100 | % | 100 |  | 16.77% | 100% | 100% | 0%
298 | Completion of Stump |  | 0 | 1 | 2024-02-02 | 2024-02-02 | 2024-02-28 | 2024-02-28 | 2024-02-28 | 2024-02-28 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
299 | Ground Beam |  | 224 | 45 | 2023-12-06 | 2024-01-19 | 2023-11-27 | 2023-11-27 | 2024-01-26 | 2024-01-26 |  | 0 | [5 empty] | 34.89% | 100% | 100% | 0%
300 | Excavation |  | 28 | 28 | 2023-12-06 | 2024-01-02 | 2023-11-27 | 2023-11-27 | 2024-01-09 | 2024-01-09 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
301 | Leveling and Compaction |  | 28 | 28 | 2023-12-08 | 2024-01-04 | 2023-11-29 | 2023-11-29 | 2024-01-10 | 2024-01-10 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
302 | Lean Concrete Pouring |  | 28 | 28 | 2023-12-09 | 2024-01-05 | 2023-12-12 | 2023-12-12 | 2024-01-12 | 2024-01-12 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
303 | Reinforcement Bar Fixing |  | 28 | 28 | 2023-12-13 | 2024-01-09 | 2023-12-12 | 2023-12-12 | 2024-01-15 | 2024-01-15 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
304 | Formwork Fixing |  | 28 | 28 | 2023-12-16 | 2024-01-12 | 2023-12-12 | 2023-12-12 | 2024-01-15 | 2024-01-15 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
305 | Concrete Pouring |  | 28 | 28 | 2023-12-19 | 2024-01-15 | 2023-12-18 | 2023-12-18 | 2024-01-16 | 2024-01-16 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
306 | Formwork Dismantling |  | 28 | 28 | 2023-12-22 | 2024-01-18 | 2023-12-20 | 2023-12-20 | 2024-01-19 | 2024-01-19 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
307 | Backfill with compaction |  | 28 | 28 | 2023-12-23 | 2024-01-19 | 2024-01-03 | 2024-01-03 | 2024-01-26 | 2024-01-26 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
308 | Completion of Ground Beam |  | 0 | 1 | 2024-01-19 | 2024-01-19 | 2024-01-26 | 2024-01-26 | 2024-01-26 | 2024-01-26 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
309 | Completion of Structure |  | 0 | 1 | 2024-02-02 | 2024-02-02 | 2024-02-28 | 2024-02-28 | 2024-02-28 | 2024-02-28 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
310 | Compressor / Equipment Foundation |  | 453 | 69 | 2023-12-22 | 2024-02-28 | 2023-11-30 | 2023-11-30 | 2024-03-16 | 2024-03-16 |  | 0 | [5 empty] | 32.17% | 100% | 96.5% | -3.499%
311 | Equipment Foundation |  | 453 | 69 | 2023-12-22 | 2024-02-28 | 2023-11-30 | 2023-11-30 | 2024-03-16 | 2024-03-16 |  | 0 | [5 empty] | 100% | 100% | 96.5% | -3.499%
312 | Excavation |  | 46 | 46 | 2023-12-22 | 2024-02-05 | 2023-11-30 | 2023-11-30 | 2024-01-09 | 2024-01-09 | 100 | 0 | 0 | 100 | % | 100 |  | 10.15% | 100% | 100% | 0%
313 | Leveling and Compaction |  | 45 | 45 | 2023-12-25 | 2024-02-07 | 2023-12-07 | 2023-12-07 | 2024-01-10 | 2024-01-10 | 100 | 0 | 0 | 100 | % | 100 |  | 9.934% | 100% | 100% | 0%
314 | Lean Concrete Pouring |  | 45 | 45 | 2023-12-26 | 2024-02-08 | 2023-12-08 | 2023-12-08 | 2024-02-22 | 2024-02-22 | 100 | 0 | 0 | 100 | % | 100 |  | 9.934% | 100% | 100% | 0%
315 | Pile Cutting and Treatment |  | 45 | 45 | 2023-12-28 | 2024-02-10 | 2023-12-09 | 2023-12-09 | 2024-02-23 | 2024-02-23 | 100 | 0 | 0 | 100 | % | 100 |  | 9.934% | 100% | 100% | 0%
316 | Reinforcement Bar Fixing |  | 45 | 45 | 2024-01-01 | 2024-02-14 | 2023-12-21 | 2023-12-21 | 2024-02-03 | 2024-02-03 | 100 | 0 | 0 | 95 | % | 100 |  | 9.934% | 100% | 95% | -5%
317 | Formwork Fixing |  | 45 | 45 | 2024-01-04 | 2024-02-17 | 2023-12-21 | 2023-12-21 | 2024-02-03 | 2024-02-03 | 100 | 0 | 0 | 95 | % | 100 |  | 9.934% | 100% | 95% | -5%
318 | Anchor Bolt / Inserted Plate Fixing |  | 46 | 46 | 2024-01-06 | 2024-02-20 | 2024-01-12 | 2024-01-12 | 2024-02-26 | 2024-02-26 | 100 | 0 | 0 | 95 | % | 100 |  | 10.15% | 100% | 95% | -5%
319 | Concrete Pouring |  | 45 | 45 | 2024-01-10 | 2024-02-23 | 2024-01-16 | 2024-01-16 | 2024-02-29 | 2024-02-29 | 100 | 0 | 0 | 95 | % | 100 |  | 9.934% | 100% | 95% | -5%
320 | Formwork Dismantling |  | 46 | 46 | 2024-01-13 | 2024-02-27 | 2024-01-19 | 2024-01-19 | 2024-03-04 | 2024-03-04 | 100 | 0 | 0 | 95 | % | 100 |  | 10.15% | 100% | 95% | -5%
321 | Backfill with compaction |  | 45 | 45 | 2024-01-15 | 2024-02-28 | 2024-02-01 | 2024-02-01 | 2024-03-16 | 2024-03-16 | 100 | 0 | 0 | 90 | % | 100 |  | 9.934% | 100% | 90% | -10%
322 | Completion of Equipment Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
323 | Completion of Compressor / Equipment and Pump Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
324 | General |  | 313 | 56 | 2023-12-09 | 2024-02-02 | 2023-11-30 | 2023-11-30 | 2024-03-15 | 2024-03-15 |  | 0 | [5 empty] | 22.23% | 100% | 100% | 0%
325 | Pipe Gallery |  | 313 | 56 | 2023-12-09 | 2024-02-02 | 2023-11-30 | 2023-11-30 | 2024-03-15 | 2024-03-15 |  | 0 | [5 empty] | 100% | 100% | 100% | 0%
326 | Pile Cap |  | 188 | 41 | 2023-12-09 | 2024-01-18 | 2023-11-30 | 2023-11-30 | 2024-02-16 | 2024-02-16 |  | 0 | [5 empty] | 60.06% | 100% | 100% | 0%
327 | Excavation |  | 21 | 21 | 2023-12-09 | 2023-12-29 | 2023-11-30 | 2023-11-30 | 2024-01-09 | 2024-01-09 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
328 | Leveling and Compaction |  | 21 | 21 | 2023-12-12 | 2024-01-01 | 2023-12-07 | 2023-12-07 | 2024-01-10 | 2024-01-10 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
329 | Lean Concrete Pouring |  | 21 | 21 | 2023-12-13 | 2024-01-02 | 2023-12-27 | 2023-12-27 | 2024-01-19 | 2024-01-19 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
330 | Pile Cutting and Treatment |  | 21 | 21 | 2023-12-15 | 2024-01-04 | 2023-12-28 | 2023-12-28 | 2024-01-19 | 2024-01-19 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
331 | Reinforcement Bar Fixing |  | 21 | 21 | 2023-12-19 | 2024-01-08 | 2024-01-10 | 2024-01-10 | 2024-01-19 | 2024-01-19 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
332 | Formwork Fixing |  | 21 | 21 | 2023-12-22 | 2024-01-11 | 2024-01-10 | 2024-01-10 | 2024-01-19 | 2024-01-19 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
333 | Concrete Pouring |  | 20 | 20 | 2023-12-25 | 2024-01-13 | 2024-01-16 | 2024-01-16 | 2024-02-02 | 2024-02-02 | 100 | 0 | 0 | 100 | % | 100 |  | 10.64% | 100% | 100% | 0%
334 | Formwork Dismantling |  | 21 | 21 | 2023-12-28 | 2024-01-17 | 2024-01-19 | 2024-01-19 | 2024-02-16 | 2024-02-16 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
335 | Backfill with compaction |  | 21 | 21 | 2023-12-29 | 2024-01-18 | 2024-01-26 | 2024-01-26 | 2024-02-16 | 2024-02-16 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
336 | Completion of Pile Cap |  | 0 | 1 | 2024-01-18 | 2024-01-18 | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-16 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
337 | Stump |  | 125 | 33 | 2024-01-01 | 2024-02-02 | 2024-01-18 | 2024-01-18 | 2024-03-15 | 2024-03-15 |  | 0 | [5 empty] | 39.94% | 100% | 100% | 0%
338 | Reinforcement Bar Fixing |  | 20 | 20 | 2024-01-01 | 2024-01-20 | 2024-01-18 | 2024-01-18 | 2024-02-02 | 2024-02-02 | 100 | 0 | 0 | 100 | % | 100 |  | 16% | 100% | 100% | 0%
339 | Formwork Fixing |  | 21 | 21 | 2024-01-03 | 2024-01-23 | 2024-02-07 | 2024-02-07 | 2024-03-06 | 2024-03-06 | 100 | 0 | 0 | 100 | % | 100 |  | 16.8% | 100% | 100% | 0%
340 | Anchor Bolt Fixing |  | 21 | 21 | 2024-01-05 | 2024-01-25 | 2024-02-09 | 2024-02-09 | 2024-03-07 | 2024-03-07 | 100 | 0 | 0 | 100 | % | 100 |  | 16.8% | 100% | 100% | 0%
341 | Concrete Pouring |  | 21 | 21 | 2024-01-09 | 2024-01-29 | 2024-02-16 | 2024-02-16 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 16.8% | 100% | 100% | 0%
342 | Formwork Dismantling |  | 21 | 21 | 2024-01-12 | 2024-02-01 | 2024-02-20 | 2024-02-20 | 2024-03-13 | 2024-03-13 | 100 | 0 | 0 | 100 | % | 100 |  | 16.8% | 100% | 100% | 0%
343 | Backfill with compaction |  | 21 | 21 | 2024-01-13 | 2024-02-02 | 2024-02-21 | 2024-02-21 | 2024-03-15 | 2024-03-15 | 100 | 0 | 0 | 100 | % | 100 |  | 16.8% | 100% | 100% | 0%
344 | Completion of Stump |  | 0 | 1 | 2024-02-02 | 2024-02-02 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
345 | Completion of Pipe Gallery |  | 0 | 1 | 2024-02-02 | 2024-02-02 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
346 | Completion of General |  | 0 | 1 | 2024-02-02 | 2024-02-02 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
347 | Completion of Substructure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
348 | Completion of Unit 800 - Compressor Shed |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
349 | Unit 800 - Desulfurization Frame |  | 697 | 85 | 2023-12-06 | 2024-02-28 | 2023-12-06 | 2023-12-06 | 2024-04-19 | 2024-04-19 |  | 0 | [5 empty] | 7.81% | 100% | 100% | 0%
350 | Piling (Cutting only) |  | 9 | 9 | 2023-12-06 | 2023-12-14 | 2023-12-06 | 2023-12-06 | 2023-12-14 | 2023-12-14 |  | 0 | [5 empty] | 1.291% | 100% | 100% | 0%
351 | Cutting off Pile to GL |  | 9 | 9 | 2023-12-06 | 2023-12-14 | 2023-12-06 | 2023-12-06 | 2023-12-14 | 2023-12-14 | 100 | 0 | 0 | 100 | % | 100 |  | 100% | 100% | 100% | 0%
352 | Completion of Piling |  | 0 | 1 | 2023-12-14 | 2023-12-14 | 2023-12-14 | 2023-12-14 | 2023-12-14 | 2023-12-14 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
353 | Substructure |  | 688 | 80 | 2023-12-11 | 2024-02-28 | 2024-01-08 | 2024-01-08 | 2024-04-19 | 2024-04-19 |  | 0 | [5 empty] | 98.71% | 100% | 100% | 0%
354 | Structure |  | 317 | 48 | 2023-12-11 | 2024-01-27 | 2024-01-08 | 2024-01-08 | 2024-03-11 | 2024-03-11 |  | 0 | [5 empty] | 46.08% | 100% | 100% | 0%
355 | Pile Cap |  | 125 | 33 | 2023-12-11 | 2024-01-12 | 2024-01-08 | 2024-01-08 | 2024-02-26 | 2024-02-26 |  | 0 | [5 empty] | 39.43% | 100% | 100% | 0%
356 | Excavation |  | 13 | 13 | 2023-12-11 | 2023-12-23 | 2024-01-08 | 2024-01-08 | 2024-01-25 | 2024-01-25 | 100 | 0 | 0 | 100 | % | 100 |  | 10.4% | 100% | 100% | 0%
357 | Leveling and Compaction |  | 14 | 14 | 2023-12-13 | 2023-12-26 | 2024-01-08 | 2024-01-08 | 2024-01-29 | 2024-01-29 | 100 | 0 | 0 | 100 | % | 100 |  | 11.2% | 100% | 100% | 0%
358 | Lean Concrete Pouring |  | 14 | 14 | 2023-12-14 | 2023-12-27 | 2024-02-05 | 2024-02-05 | 2024-02-08 | 2024-02-08 | 100 | 0 | 0 | 100 | % | 100 |  | 11.2% | 100% | 100% | 0%
359 | Pile Cutting and Treatment |  | 14 | 14 | 2023-12-16 | 2023-12-29 | 2024-02-06 | 2024-02-06 | 2024-02-09 | 2024-02-09 | 100 | 0 | 0 | 100 | % | 100 |  | 11.2% | 100% | 100% | 0%
360 | Reinforcement Bar Fixing |  | 14 | 14 | 2023-12-20 | 2024-01-02 | 2024-02-12 | 2024-02-12 | 2024-02-16 | 2024-02-16 | 100 | 0 | 0 | 100 | % | 100 |  | 11.2% | 100% | 100% | 0%
361 | Formwork Fixing |  | 14 | 14 | 2023-12-23 | 2024-01-05 | 2024-02-14 | 2024-02-14 | 2024-02-16 | 2024-02-16 | 100 | 0 | 0 | 100 | % | 100 |  | 11.2% | 100% | 100% | 0%
362 | Concrete Pouring |  | 14 | 14 | 2023-12-26 | 2024-01-08 | 2024-02-19 | 2024-02-19 | 2024-02-20 | 2024-02-20 | 100 | 0 | 0 | 100 | % | 100 |  | 11.2% | 100% | 100% | 0%
363 | Formwork Dismantling |  | 14 | 14 | 2023-12-29 | 2024-01-11 | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-02-23 | 100 | 0 | 0 | 100 | % | 100 |  | 11.2% | 100% | 100% | 0%
364 | Backfill with compaction |  | 14 | 14 | 2023-12-30 | 2024-01-12 | 2024-02-24 | 2024-02-24 | 2024-02-26 | 2024-02-26 | 100 | 0 | 0 | 100 | % | 100 |  | 11.2% | 100% | 100% | 0%
365 | Completion of Pile Cap |  | 0 | 1 | 2024-01-12 | 2024-01-12 | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-26 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
366 | Stump |  | 83 | 26 | 2024-01-02 | 2024-01-27 | 2024-02-14 | 2024-02-14 | 2024-03-11 | 2024-03-11 |  | 0 | [5 empty] | 26.18% | 100% | 100% | 0%
367 | Reinforcement Bar Fixing |  | 14 | 14 | 2024-01-02 | 2024-01-15 | 2024-02-14 | 2024-02-14 | 2024-03-01 | 2024-03-01 | 100 | 0 | 0 | 100 | % | 100 |  | 16.87% | 100% | 100% | 0%
368 | Formwork Fixing |  | 14 | 14 | 2024-01-04 | 2024-01-17 | 2024-03-02 | 2024-03-02 | 2024-03-04 | 2024-03-04 | 100 | 0 | 0 | 100 | % | 100 |  | 16.87% | 100% | 100% | 0%
369 | Anchor Bolt Fixing |  | 14 | 14 | 2024-01-06 | 2024-01-19 | 2024-03-04 | 2024-03-04 | 2024-03-05 | 2024-03-05 | 100 | 0 | 0 | 100 | % | 100 |  | 16.87% | 100% | 100% | 0%
370 | Concrete Pouring |  | 14 | 14 | 2024-01-10 | 2024-01-23 | 2024-03-05 | 2024-03-05 | 2024-03-06 | 2024-03-06 | 100 | 0 | 0 | 100 | % | 100 |  | 16.87% | 100% | 100% | 0%
371 | Formwork Dismantling |  | 14 | 14 | 2024-01-13 | 2024-01-26 | 2024-03-06 | 2024-03-06 | 2024-03-07 | 2024-03-07 | 100 | 0 | 0 | 100 | % | 100 |  | 16.87% | 100% | 100% | 0%
372 | Backfill with compaction |  | 13 | 13 | 2024-01-15 | 2024-01-27 | 2024-03-08 | 2024-03-08 | 2024-03-11 | 2024-03-11 | 100 | 0 | 0 | 100 | % | 100 |  | 15.66% | 100% | 100% | 0%
373 | Completion of Stump |  | 0 | 1 | 2024-01-27 | 2024-01-27 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
374 | Ground Beam |  | 109 | 31 | 2023-12-14 | 2024-01-13 | 2024-01-11 | 2024-01-11 | 2024-02-26 | 2024-02-26 |  | 0 | [5 empty] | 34.38% | 100% | 100% | 0%
375 | Excavation |  | 14 | 14 | 2023-12-14 | 2023-12-27 | 2024-01-11 | 2024-01-11 | 2024-01-25 | 2024-01-25 | 100 | 0 | 0 | 100 | % | 100 |  | 12.84% | 100% | 100% | 0%
376 | Leveling and Compaction |  | 14 | 14 | 2023-12-16 | 2023-12-29 | 2024-01-12 | 2024-01-12 | 2024-01-29 | 2024-01-29 | 100 | 0 | 0 | 100 | % | 100 |  | 12.84% | 100% | 100% | 0%
377 | Lean Concrete Pouring |  | 13 | 13 | 2023-12-18 | 2023-12-30 | 2024-02-05 | 2024-02-05 | 2024-02-09 | 2024-02-09 | 100 | 0 | 0 | 100 | % | 100 |  | 11.93% | 100% | 100% | 0%
378 | Reinforcement Bar Fixing |  | 14 | 14 | 2023-12-21 | 2024-01-03 | 2024-02-13 | 2024-02-13 | 2024-02-16 | 2024-02-16 | 100 | 0 | 0 | 100 | % | 100 |  | 12.84% | 100% | 100% | 0%
379 | Formwork Fixing |  | 13 | 13 | 2023-12-25 | 2024-01-06 | 2024-02-14 | 2024-02-14 | 2024-02-16 | 2024-02-16 | 100 | 0 | 0 | 100 | % | 100 |  | 11.93% | 100% | 100% | 0%
380 | Concrete Pouring |  | 14 | 14 | 2023-12-27 | 2024-01-09 | 2024-02-19 | 2024-02-19 | 2024-02-20 | 2024-02-20 | 100 | 0 | 0 | 100 | % | 100 |  | 12.84% | 100% | 100% | 0%
381 | Formwork Dismantling |  | 14 | 14 | 2023-12-30 | 2024-01-12 | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-02-23 | 100 | 0 | 0 | 100 | % | 100 |  | 12.84% | 100% | 100% | 0%
382 | Backfill with compaction |  | 13 | 13 | 2024-01-01 | 2024-01-13 | 2024-02-24 | 2024-02-24 | 2024-02-26 | 2024-02-26 | 100 | 0 | 0 | 100 | % | 100 |  | 11.93% | 100% | 100% | 0%
383 | Completion of Ground Beam |  | 0 | 1 | 2024-01-13 | 2024-01-13 | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-26 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
384 | Completion of Structure |  | 0 | 1 | 2024-01-27 | 2024-01-27 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
385 | Equipment Foundation |  | 371 | 61 | 2023-12-30 | 2024-02-28 | 2024-01-08 | 2024-01-08 | 2024-04-19 | 2024-04-19 |  | 0 | [5 empty] | 53.92% | 100% | 100% | 0%
386 | Equipment Foundation |  | 371 | 61 | 2023-12-30 | 2024-02-28 | 2024-01-08 | 2024-01-08 | 2024-04-19 | 2024-04-19 |  | 0 | [5 empty] | 100% | 100% | 100% | 0%
387 | Excavation |  | 38 | 38 | 2023-12-30 | 2024-02-05 | 2024-01-08 | 2024-01-08 | 2024-02-09 | 2024-02-09 | 100 | 0 | 0 | 100 | % | 100 |  | 10.24% | 100% | 100% | 0%
388 | Leveling and Compaction |  | 37 | 37 | 2024-01-02 | 2024-02-07 | 2024-01-10 | 2024-01-10 | 2024-02-13 | 2024-02-13 | 100 | 0 | 0 | 100 | % | 100 |  | 9.973% | 100% | 100% | 0%
389 | Lean Concrete Pouring |  | 37 | 37 | 2024-01-03 | 2024-02-08 | 2024-03-02 | 2024-03-02 | 2024-03-15 | 2024-03-15 | 100 | 0 | 0 | 100 | % | 100 |  | 9.973% | 100% | 100% | 0%
390 | Pile Cutting and Treatment |  | 37 | 37 | 2024-01-05 | 2024-02-10 | 2024-03-04 | 2024-03-04 | 2024-03-15 | 2024-03-15 | 100 | 0 | 0 | 100 | % | 100 |  | 9.973% | 100% | 100% | 0%
391 | Reinforcement Bar Fixing |  | 37 | 37 | 2024-01-09 | 2024-02-14 | 2024-03-05 | 2024-03-05 | 2024-04-16 | 2024-04-16 | 100 | 0 | 0 | 100 | % | 100 |  | 9.973% | 100% | 100% | 0%
392 | Formwork Fixing |  | 37 | 37 | 2024-01-12 | 2024-02-17 | 2024-03-06 | 2024-03-06 | 2024-04-17 | 2024-04-17 | 100 | 0 | 0 | 100 | % | 100 |  | 9.973% | 100% | 100% | 0%
393 | Anchor Bolt / Inserted Plate Fixing |  | 37 | 37 | 2024-01-15 | 2024-02-20 | 2024-03-08 | 2024-03-08 | 2024-04-17 | 2024-04-17 | 100 | 0 | 0 | 100 | % | 100 |  | 9.973% | 100% | 100% | 0%
394 | Concrete Pouring |  | 37 | 37 | 2024-01-18 | 2024-02-23 | 2024-03-15 | 2024-03-15 | 2024-04-18 | 2024-04-18 | 100 | 0 | 0 | 100 | % | 100 |  | 9.973% | 100% | 100% | 0%
395 | Formwork Dismantling |  | 37 | 37 | 2024-01-22 | 2024-02-27 | 2024-03-16 | 2024-03-16 | 2024-04-19 | 2024-04-19 | 100 | 0 | 0 | 100 | % | 100 |  | 9.973% | 100% | 100% | 0%
396 | Backfill with compaction |  | 37 | 37 | 2024-01-23 | 2024-02-28 | 2024-03-19 | 2024-03-19 | 2024-04-19 | 2024-04-19 | 100 | 0 | 0 | 100 | % | 100 |  | 9.973% | 100% | 100% | 0%
397 | Completion of Equipment Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
398 | Completion of Compressor / Equipment and Pump Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
399 | Completion of Substructure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
400 | Completion of Unit 800 - Desulfurization Frame |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
401 | Unit 800 - Distillation Frame |  | 858 | 85 | 2023-12-06 | 2024-02-28 | 2023-12-06 | 2023-12-06 | 2024-04-20 | 2024-04-20 |  | 0 | [5 empty] | 9.615% | 100% | 100% | 0%
402 | Piling (Cutting only) |  | 9 | 9 | 2023-12-06 | 2023-12-14 | 2023-12-06 | 2023-12-06 | 2023-12-15 | 2023-12-15 |  | 0 | [5 empty] | 1.049% | 100% | 100% | 0%
403 | Cutting off Pile to GL |  | 9 | 9 | 2023-12-06 | 2023-12-14 | 2023-12-06 | 2023-12-06 | 2023-12-14 | 2023-12-14 | 100 | 0 | 0 | 100 | % | 100 |  | 100% | 100% | 100% | 0%
404 | Completion of Piling |  | 0 | 1 | 2023-12-14 | 2023-12-14 | 2023-12-14 | 2023-12-14 | 2023-12-15 | 2023-12-15 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
405 | Substructure |  | 849 | 80 | 2023-12-11 | 2024-02-28 | 2024-02-05 | 2024-02-05 | 2024-04-20 | 2024-04-20 |  | 0 | [5 empty] | 98.95% | 100% | 100% | 0%
406 | Structure |  | 478 | 55 | 2023-12-11 | 2024-02-03 | 2024-02-05 | 2024-02-05 | 2024-04-05 | 2024-04-05 |  | 0 | [5 empty] | 56.3% | 100% | 100% | 0%
407 | Pile Cap |  | 188 | 40 | 2023-12-11 | 2024-01-19 | 2024-02-05 | 2024-02-05 | 2024-03-08 | 2024-03-08 |  | 0 | [5 empty] | 39.33% | 100% | 100% | 0%
408 | Excavation |  | 20 | 20 | 2023-12-11 | 2023-12-30 | 2024-02-05 | 2024-02-05 | 2024-02-07 | 2024-02-07 | 100 | 0 | 0 | 100 | % | 100 |  | 10.64% | 100% | 100% | 0%
409 | Leveling and Compaction |  | 21 | 21 | 2023-12-13 | 2024-01-02 | 2024-02-06 | 2024-02-06 | 2024-02-08 | 2024-02-08 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
410 | Lean Concrete Pouring |  | 21 | 21 | 2023-12-14 | 2024-01-03 | 2024-02-08 | 2024-02-08 | 2024-02-09 | 2024-02-09 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
411 | Pile Cutting and Treatment |  | 21 | 21 | 2023-12-16 | 2024-01-05 | 2024-02-08 | 2024-02-08 | 2024-02-09 | 2024-02-09 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
412 | Reinforcement Bar Fixing |  | 21 | 21 | 2023-12-20 | 2024-01-09 | 2024-02-15 | 2024-02-15 | 2024-02-23 | 2024-02-23 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
413 | Formwork Fixing |  | 21 | 21 | 2023-12-23 | 2024-01-12 | 2024-02-16 | 2024-02-16 | 2024-02-22 | 2024-02-22 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
414 | Concrete Pouring |  | 21 | 21 | 2023-12-26 | 2024-01-15 | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-02-29 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
415 | Formwork Dismantling |  | 21 | 21 | 2023-12-29 | 2024-01-18 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-03-02 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
416 | Backfill with compaction |  | 21 | 21 | 2023-12-30 | 2024-01-19 | 2024-03-06 | 2024-03-06 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
417 | Completion of Pile Cap |  | 0 | 1 | 2024-01-19 | 2024-01-19 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
418 | Stump |  | 125 | 33 | 2024-01-02 | 2024-02-03 | 2024-02-27 | 2024-02-27 | 2024-04-05 | 2024-04-05 |  | 0 | [5 empty] | 26.15% | 100% | 100% | 0%
419 | Reinforcement Bar Fixing |  | 21 | 21 | 2024-01-02 | 2024-01-22 | 2024-02-27 | 2024-02-27 | 2024-03-01 | 2024-03-01 | 100 | 0 | 0 | 100 | % | 100 |  | 16.8% | 100% | 100% | 0%
420 | Formwork Fixing |  | 21 | 21 | 2024-01-04 | 2024-01-24 | 2024-03-18 | 2024-03-18 | 2024-03-29 | 2024-03-29 | 100 | 0 | 0 | 100 | % | 100 |  | 16.8% | 100% | 100% | 0%
421 | Anchor Bolt Fixing |  | 21 | 21 | 2024-01-06 | 2024-01-26 | 2024-03-21 | 2024-03-21 | 2024-04-01 | 2024-04-01 | 100 | 0 | 0 | 100 | % | 100 |  | 16.8% | 100% | 100% | 0%
422 | Concrete Pouring |  | 21 | 21 | 2024-01-10 | 2024-01-30 | 2024-03-25 | 2024-03-25 | 2024-04-02 | 2024-04-02 | 100 | 0 | 0 | 100 | % | 100 |  | 16.8% | 100% | 100% | 0%
423 | Formwork Dismantling |  | 21 | 21 | 2024-01-13 | 2024-02-02 | 2024-03-26 | 2024-03-26 | 2024-04-03 | 2024-04-03 | 100 | 0 | 0 | 100 | % | 100 |  | 16.8% | 100% | 100% | 0%
424 | Backfill with compaction |  | 20 | 20 | 2024-01-15 | 2024-02-03 | 2024-03-27 | 2024-03-27 | 2024-04-05 | 2024-04-05 | 100 | 0 | 0 | 100 | % | 100 |  | 16% | 100% | 100% | 0%
425 | Completion of Stump |  | 0 | 1 | 2024-02-03 | 2024-02-03 | 2024-04-05 | 2024-04-05 | 2024-04-05 | 2024-04-05 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
426 | Ground Beam |  | 165 | 38 | 2023-12-14 | 2024-01-20 | 2024-02-06 | 2024-02-06 | 2024-03-08 | 2024-03-08 |  | 0 | [5 empty] | 34.52% | 100% | 100% | 0%
427 | Excavation |  | 21 | 21 | 2023-12-14 | 2024-01-03 | 2024-02-06 | 2024-02-06 | 2024-02-08 | 2024-02-08 | 100 | 0 | 0 | 100 | % | 100 |  | 12.73% | 100% | 100% | 0%
428 | Leveling and Compaction |  | 21 | 21 | 2023-12-16 | 2024-01-05 | 2024-02-08 | 2024-02-08 | 2024-02-16 | 2024-02-16 | 100 | 0 | 0 | 100 | % | 100 |  | 12.73% | 100% | 100% | 0%
429 | Lean Concrete Pouring |  | 20 | 20 | 2023-12-18 | 2024-01-06 | 2024-02-15 | 2024-02-15 | 2024-02-16 | 2024-02-16 | 100 | 0 | 0 | 100 | % | 100 |  | 12.12% | 100% | 100% | 0%
430 | Reinforcement Bar Fixing |  | 21 | 21 | 2023-12-21 | 2024-01-10 | 2024-02-16 | 2024-02-16 | 2024-02-22 | 2024-02-22 | 100 | 0 | 0 | 100 | % | 100 |  | 12.73% | 100% | 100% | 0%
431 | Formwork Fixing |  | 20 | 20 | 2023-12-25 | 2024-01-13 | 2024-02-20 | 2024-02-20 | 2024-02-23 | 2024-02-23 | 100 | 0 | 0 | 100 | % | 100 |  | 12.12% | 100% | 100% | 0%
432 | Concrete Pouring |  | 21 | 21 | 2023-12-27 | 2024-01-16 | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-02-29 | 100 | 0 | 0 | 100 | % | 100 |  | 12.73% | 100% | 100% | 0%
433 | Formwork Dismantling |  | 21 | 21 | 2023-12-30 | 2024-01-19 | 2024-03-01 | 2024-03-01 | 2024-03-02 | 2024-03-02 | 100 | 0 | 0 | 100 | % | 100 |  | 12.73% | 100% | 100% | 0%
434 | Backfill with compaction |  | 20 | 20 | 2024-01-01 | 2024-01-20 | 2024-03-06 | 2024-03-06 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 12.12% | 100% | 100% | 0%
435 | Completion of Ground Beam |  | 0 | 1 | 2024-01-20 | 2024-01-20 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
436 | Completion of Structure |  | 0 | 1 | 2024-02-03 | 2024-02-03 | 2024-04-05 | 2024-04-05 | 2024-04-05 | 2024-04-05 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
437 | Equipment Foundation |  | 371 | 61 | 2023-12-30 | 2024-02-28 | 2024-02-05 | 2024-02-05 | 2024-04-20 | 2024-04-20 |  | 0 | [5 empty] | 43.7% | 100% | 100% | 0%
438 | Equipment Foundation |  | 371 | 61 | 2023-12-30 | 2024-02-28 | 2024-02-05 | 2024-02-05 | 2024-04-20 | 2024-04-20 |  | 0 | [5 empty] | 100% | 100% | 100% | 0%
439 | Excavation |  | 38 | 38 | 2023-12-30 | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-04-19 | 2024-04-19 | 100 | 0 | 0 | 100 | % | 100 |  | 10.24% | 100% | 100% | 0%
440 | Leveling and Compaction |  | 37 | 37 | 2024-01-02 | 2024-02-07 | 2024-02-09 | 2024-02-09 | 2024-04-19 | 2024-04-19 | 100 | 0 | 0 | 100 | % | 100 |  | 9.973% | 100% | 100% | 0%
441 | Lean Concrete Pouring |  | 37 | 37 | 2024-01-03 | 2024-02-08 | 2024-02-13 | 2024-02-13 | 2024-03-13 | 2024-03-13 | 100 | 0 | 0 | 100 | % | 100 |  | 9.973% | 100% | 100% | 0%
442 | Pile Cutting and Treatment |  | 37 | 37 | 2024-01-05 | 2024-02-10 | 2024-02-14 | 2024-02-14 | 2024-03-14 | 2024-03-14 | 100 | 0 | 0 | 100 | % | 100 |  | 9.973% | 100% | 100% | 0%
443 | Reinforcement Bar Fixing |  | 37 | 37 | 2024-01-09 | 2024-02-14 | 2024-02-27 | 2024-02-27 | 2024-03-27 | 2024-03-27 | 100 | 0 | 0 | 100 | % | 100 |  | 9.973% | 100% | 100% | 0%
444 | Formwork Fixing |  | 37 | 37 | 2024-01-12 | 2024-02-17 | 2024-02-28 | 2024-02-28 | 2024-03-30 | 2024-03-30 | 100 | 0 | 0 | 100 | % | 100 |  | 9.973% | 100% | 100% | 0%
445 | Anchor Bolt / Inserted Plate Fixing |  | 37 | 37 | 2024-01-15 | 2024-02-20 | 2024-03-05 | 2024-03-05 | 2024-04-03 | 2024-04-03 | 100 | 0 | 0 | 100 | % | 100 |  | 9.973% | 100% | 100% | 0%
446 | Concrete Pouring |  | 37 | 37 | 2024-01-18 | 2024-02-23 | 2024-03-14 | 2024-03-14 | 2024-04-12 | 2024-04-12 | 100 | 0 | 0 | 100 | % | 100 |  | 9.973% | 100% | 100% | 0%
447 | Formwork Dismantling |  | 37 | 37 | 2024-01-22 | 2024-02-27 | 2024-03-15 | 2024-03-15 | 2024-04-16 | 2024-04-16 | 100 | 0 | 0 | 100 | % | 100 |  | 9.973% | 100% | 100% | 0%
448 | Backfill with compaction |  | 37 | 37 | 2024-01-23 | 2024-02-28 | 2024-03-22 | 2024-03-22 | 2024-04-20 | 2024-04-20 | 100 | 0 | 0 | 100 | % | 100 |  | 9.973% | 100% | 100% | 0%
449 | Completion of Equipment Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-04-20 | 2024-04-20 | 2024-04-20 | 2024-04-20 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
450 | Completion of Compressor / Equipment and Pump Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-04-20 | 2024-04-20 | 2024-04-20 | 2024-04-20 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
451 | Completion of Substructure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-04-20 | 2024-04-20 | 2024-04-20 | 2024-04-20 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
452 | Completion of Unit 800 - Distillation Frame |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-04-20 | 2024-04-20 | 2024-04-20 | 2024-04-20 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
453 | Unit 800 - Pipe Gallery 2 |  | 755 | 80 | 2023-12-11 | 2024-02-28 | 2023-11-27 | 2023-11-27 | 2024-05-02 | 2024-05-02 |  | 0.01 | [5 empty] | 8.46% | 100% | 100% | 0%
454 | Piling (Cutting only) |  | 9 | 9 | 2023-12-11 | 2023-12-19 | 2023-12-11 | 2023-12-11 | 2023-12-19 | 2023-12-19 |  | 1 | [5 empty] | 1.192% | 100% | 100% | 0%
455 | Cutting off Pile to GL |  | 9 | 9 | 2023-12-11 | 2023-12-19 | 2023-12-11 | 2023-12-11 | 2023-12-19 | 2023-12-19 | 100 | 1 | 100 | 100 | % | 100 |  | 100% | 100% | 100% | 0%
456 | Completion of Piling |  | 0 | 1 | 2023-12-19 | 2023-12-19 | 2023-12-19 | 2023-12-19 | 2023-12-19 | 2023-12-19 | 100 | 1 | 100 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
457 | Pipe Gallery |  | 746 | 71 | 2023-12-20 | 2024-02-28 | 2023-11-27 | 2023-11-27 | 2024-05-02 | 2024-05-02 |  | 0 | [5 empty] | 98.81% | 100% | 100% | 0%
458 | Structure |  | 482 | 56 | 2023-12-20 | 2024-02-13 | 2023-11-27 | 2023-11-27 | 2024-04-18 | 2024-04-18 |  | 0 | [5 empty] | 64.61% | 100% | 100% | 0%
459 | Pile Cap |  | 188 | 41 | 2023-12-20 | 2024-01-29 | 2023-11-27 | 2023-11-27 | 2024-03-29 | 2024-03-29 |  | 0 | [5 empty] | 39% | 100% | 100% | 0%
460 | Excavation |  | 21 | 21 | 2023-12-20 | 2024-01-09 | 2023-11-27 | 2023-11-27 | 2024-02-20 | 2024-02-20 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
461 | Leveling and Compaction |  | 21 | 21 | 2023-12-22 | 2024-01-11 | 2023-12-04 | 2023-12-04 | 2024-02-21 | 2024-02-21 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
462 | Lean Concrete Pouring |  | 21 | 21 | 2023-12-23 | 2024-01-12 | 2023-12-05 | 2023-12-05 | 2024-02-23 | 2024-02-23 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
463 | Pile Cutting and Treatment |  | 21 | 21 | 2023-12-26 | 2024-01-15 | 2023-12-08 | 2023-12-08 | 2024-02-23 | 2024-02-23 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
464 | Reinforcement Bar Fixing |  | 21 | 21 | 2023-12-29 | 2024-01-18 | 2023-12-12 | 2023-12-12 | 2024-03-01 | 2024-03-01 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
465 | Formwork Fixing |  | 21 | 21 | 2024-01-02 | 2024-01-22 | 2023-12-12 | 2023-12-12 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
466 | Concrete Pouring |  | 21 | 21 | 2024-01-04 | 2024-01-24 | 2023-12-18 | 2023-12-18 | 2024-03-28 | 2024-03-28 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
467 | Formwork Dismantling |  | 20 | 20 | 2024-01-08 | 2024-01-27 | 2023-12-20 | 2023-12-20 | 2024-03-29 | 2024-03-29 | 100 | 0 | 0 | 100 | % | 100 |  | 10.64% | 100% | 100% | 0%
468 | Backfill with compaction |  | 21 | 21 | 2024-01-09 | 2024-01-29 | 2024-01-03 | 2024-01-03 | 2024-03-29 | 2024-03-29 | 100 | 0 | 0 | 100 | % | 100 |  | 11.17% | 100% | 100% | 0%
469 | Completion of Pile Cap |  | 0 | 1 | 2024-01-29 | 2024-01-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
470 | Stump |  | 126 | 34 | 2024-01-11 | 2024-02-13 | 2023-12-21 | 2023-12-21 | 2024-04-18 | 2024-04-18 |  | 0 | [5 empty] | 26.14% | 100% | 100% | 0%
471 | Reinforcement Bar Fixing |  | 21 | 21 | 2024-01-11 | 2024-01-31 | 2023-12-21 | 2023-12-21 | 2024-03-28 | 2024-03-28 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
472 | Formwork Fixing |  | 21 | 21 | 2024-01-13 | 2024-02-02 | 2024-01-11 | 2024-01-11 | 2024-03-29 | 2024-03-29 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
473 | Anchor Bolt Fixing |  | 21 | 21 | 2024-01-16 | 2024-02-05 | 2024-01-13 | 2024-01-13 | 2024-04-05 | 2024-04-05 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
474 | Concrete Pouring |  | 21 | 21 | 2024-01-19 | 2024-02-08 | 2024-01-29 | 2024-01-29 | 2024-04-16 | 2024-04-16 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
475 | Formwork Dismantling |  | 21 | 21 | 2024-01-23 | 2024-02-12 | 2024-01-31 | 2024-01-31 | 2024-04-17 | 2024-04-17 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
476 | Backfill with compaction |  | 21 | 21 | 2024-01-24 | 2024-02-13 | 2024-02-14 | 2024-02-14 | 2024-04-18 | 2024-04-18 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
477 | Completion of Stump |  | 0 | 1 | 2024-02-13 | 2024-02-13 | 2024-04-18 | 2024-04-18 | 2024-04-18 | 2024-04-18 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
478 | Ground Beam |  | 168 | 39 | 2023-12-23 | 2024-01-30 | 2023-11-27 | 2023-11-27 | 2024-03-29 | 2024-03-29 |  | 0 | [5 empty] | 34.85% | 100% | 100% | 0%
479 | Excavation |  | 21 | 21 | 2023-12-23 | 2024-01-12 | 2023-11-27 | 2023-11-27 | 2024-02-20 | 2024-02-20 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
480 | Leveling and Compaction |  | 21 | 21 | 2023-12-26 | 2024-01-15 | 2023-12-04 | 2023-12-04 | 2024-02-21 | 2024-02-21 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
481 | Lean Concrete Pouring |  | 21 | 21 | 2023-12-27 | 2024-01-16 | 2023-12-05 | 2023-12-05 | 2024-02-23 | 2024-02-23 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
482 | Reinforcement Bar Fixing |  | 21 | 21 | 2023-12-30 | 2024-01-19 | 2023-12-12 | 2023-12-12 | 2024-03-26 | 2024-03-26 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
483 | Formwork Fixing |  | 21 | 21 | 2024-01-03 | 2024-01-23 | 2023-12-12 | 2023-12-12 | 2024-03-27 | 2024-03-27 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
484 | Concrete Pouring |  | 21 | 21 | 2024-01-05 | 2024-01-25 | 2023-12-18 | 2023-12-18 | 2024-03-28 | 2024-03-28 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
485 | Formwork Dismantling |  | 21 | 21 | 2024-01-09 | 2024-01-29 | 2023-12-20 | 2023-12-20 | 2024-03-29 | 2024-03-29 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
486 | Backfill with compaction |  | 21 | 21 | 2024-01-10 | 2024-01-30 | 2024-01-03 | 2024-01-03 | 2024-03-29 | 2024-03-29 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
487 | Completion of Ground Beam |  | 0 | 1 | 2024-01-30 | 2024-01-30 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
488 | Completion of Structure |  | 0 | 1 | 2024-02-13 | 2024-02-13 | 2024-04-18 | 2024-04-18 | 2024-04-18 | 2024-04-18 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
489 | Underground Pits |  | 56 | 63 | 2023-12-22 | 2024-02-22 | 2023-12-28 | 2023-12-28 | 2024-04-26 | 2024-04-26 |  | 0 | [5 empty] | 7.507% | 100% | 100% | 0%
490 | Temporary Sheet Pile |  | 6 | 6 | 2023-12-22 | 2023-12-27 | 2023-12-28 | 2023-12-28 | 2024-01-02 | 2024-01-02 | 100 | 0 | 0 | 100 | % | 100 |  | 10.71% | 100% | 100% | 0%
491 | Excavation |  | 15 | 15 | 2023-12-28 | 2024-01-11 | 2024-01-10 | 2024-01-10 | 2024-01-26 | 2024-01-26 | 100 | 0 | 0 | 100 | % | 100 |  | 26.79% | 100% | 100% | 0%
492 | Leveling and Compaction |  | 3 | 3 | 2024-01-02 | 2024-01-04 | 2024-01-29 | 2024-01-29 | 2024-01-29 | 2024-01-29 | 100 | 0 | 0 | 100 | % | 100 |  | 5.357% | 100% | 100% | 0%
493 | Lean Concrete Pouring |  | 1 | 1 | 2024-01-12 | 2024-01-12 | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2024-01-30 | 100 | 0 | 0 | 100 | % | 100 |  | 1.786% | 100% | 100% | 0%
494 | Base |  | 8 | 8 | 2024-01-13 | 2024-01-20 | 2024-02-06 | 2024-02-06 | 2024-02-28 | 2024-02-28 |  | 0 | [5 empty] | 14.29% | 100% | 100% | 0%
495 | Reinforcement Bar Fixing |  | 5 | 5 | 2024-01-13 | 2024-01-17 | 2024-02-06 | 2024-02-06 | 2024-02-09 | 2024-02-09 | 100 | 0 | 0 | 100 | % | 100 |  | 62.5% | 100% | 100% | 0%
496 | Formwork Fixing |  | 2 | 2 | 2024-01-18 | 2024-01-19 | 2024-02-09 | 2024-02-09 | 2024-02-09 | 2024-02-09 | 100 | 0 | 0 | 100 | % | 100 |  | 25% | 100% | 100% | 0%
497 | Concrete Pouring |  | 1 | 1 | 2024-01-20 | 2024-01-20 | 2024-02-28 | 2024-02-28 | 2024-02-28 | 2024-02-28 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
498 | Wall |  | 19 | 19 | 2024-01-22 | 2024-02-09 | 2024-03-01 | 2024-03-01 | 2024-04-23 | 2024-04-23 |  | 0 | [5 empty] | 33.93% | 100% | 100%
499 | Reinforcement Bar Fixing |  | 9 | 9 | 2024-01-22 | 2024-01-30 | 2024-03-01 | 2024-03-01 | 2024-03-15 | 2024-03-15 | 100 | 0 | 0 | 100 | % | 100 |  | 47.37% | 100% | 100% | 0%
500 | Formwork Fixing |  | 9 | 9 | 2024-01-31 | 2024-02-08 | 2024-03-19 | 2024-03-19 | 2024-03-29 | 2024-03-29 | 100 | 0 | 0 | 100 | % | 100 |  | 47.37% | 100% | 100% | 0%
501 | Concrete Pouring |  | 1 | 1 | 2024-02-09 | 2024-02-09 | 2024-04-22 | 2024-04-22 | 2024-04-23 | 2024-04-23 | 100 | 0 | 0 | 100 | % | 100 |  | 5.263% | 100% | 100% | 0%
502 | Formwork Dismantling |  | 1 | 1 | 2024-02-19 | 2024-02-19 | 2024-04-24 | 2024-04-24 | 2024-04-25 | 2024-04-25 | 100 | 0 | 0 | 100 | % | 100 |  | 1.786% | 100% | 100% | 0%
503 | Backfill with compaction |  | 3 | 3 | 2024-02-20 | 2024-02-22 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 | 100 | % | 100 |  | 5.357% | 100% | 100% | 0%
504 | Completion of Underground Pits |  | 0 | 1 | 2024-02-22 | 2024-02-22 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
505 | Equipment Foundation |  | 208 | 44 | 2024-01-16 | 2024-02-28 | 2023-12-28 | 2023-12-28 | 2024-05-02 | 2024-05-02 |  | 0 | [5 empty] | 27.88% | 100% | 100% | 0%
506 | Equipment Foundation |  | 208 | 44 | 2024-01-16 | 2024-02-28 | 2023-12-28 | 2023-12-28 | 2024-05-02 | 2024-05-02 |  | 0 | [5 empty] | 100% | 100% | 100% | 0%
507 | Excavation |  | 21 | 21 | 2024-01-16 | 2024-02-05 | 2023-12-28 | 2023-12-28 | 2024-02-01 | 2024-02-01 | 100 | 0 | 0 | 100 | % | 100 |  | 10.1% | 100% | 100% | 0%
508 | Leveling and Compaction |  | 21 | 21 | 2024-01-18 | 2024-02-07 | 2023-12-30 | 2023-12-30 | 2024-02-01 | 2024-02-01 | 100 | 0 | 0 | 100 | % | 100 |  | 10.1% | 100% | 100% | 0%
509 | Lean Concrete Pouring |  | 21 | 21 | 2024-01-19 | 2024-02-08 | 2024-02-27 | 2024-02-27 | 2024-04-03 | 2024-04-03 | 100 | 0 | 0 | 100 | % | 100 |  | 10.1% | 100% | 100% | 0%
510 | Pile Cutting and Treatment |  | 20 | 20 | 2024-01-22 | 2024-02-10 | 2024-02-27 | 2024-02-27 | 2024-04-04 | 2024-04-04 | 100 | 0 | 0 | 100 | % | 100 |  | 9.615% | 100% | 100% | 0%
511 | Reinforcement Bar Fixing |  | 21 | 21 | 2024-01-25 | 2024-02-14 | 2024-02-28 | 2024-02-28 | 2024-04-05 | 2024-04-05 | 100 | 0 | 0 | 100 | % | 100 |  | 10.1% | 100% | 100% | 0%
512 | Formwork Fixing |  | 20 | 20 | 2024-01-29 | 2024-02-17 | 2024-02-29 | 2024-02-29 | 2024-04-05 | 2024-04-05 | 100 | 0 | 0 | 100 | % | 100 |  | 9.615% | 100% | 100% | 0%
513 | Anchor Bolt / Inserted Plate Fixing |  | 21 | 21 | 2024-01-31 | 2024-02-20 | 2024-03-14 | 2024-03-14 | 2024-04-30 | 2024-04-30 | 100 | 0 | 0 | 100 | % | 100 |  | 10.1% | 100% | 100% | 0%
514 | Concrete Pouring |  | 21 | 21 | 2024-02-03 | 2024-02-23 | 2024-03-15 | 2024-03-15 | 2024-04-30 | 2024-04-30 | 100 | 0 | 0 | 100 | % | 100 |  | 10.1% | 100% | 100% | 0%
515 | Formwork Dismantling |  | 21 | 21 | 2024-02-07 | 2024-02-27 | 2024-03-16 | 2024-03-16 | 2024-05-02 | 2024-05-02 | 100 | 0 | 0 | 100 | % | 100 |  | 10.1% | 100% | 100% | 0%
516 | Backfill with compaction |  | 21 | 21 | 2024-02-08 | 2024-02-28 | 2024-03-20 | 2024-03-20 | 2024-05-02 | 2024-05-02 | 100 | 0 | 0 | 100 | % | 100 |  | 10.1% | 100% | 100% | 0%
517 | Completion of Equipment Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-05-02 | 2024-05-02 | 2024-05-02 | 2024-05-02 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
518 | Completion of Compressor / Equipment and Pump Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-05-02 | 2024-05-02 | 2024-05-02 | 2024-05-02 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
519 | Completion of Substructure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-05-02 | 2024-05-02 | 2024-05-02 | 2024-05-02 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
520 | Completion of Unit 800 - Pipe Gallery 2 |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-05-02 | 2024-05-02 | 2024-05-02 | 2024-05-02 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
521 | Unit 800 - Pipe Gallery 3 & 4 |  | 930 | 76 | 2023-12-15 | 2024-02-28 | 2023-12-15 | 2023-12-15 | 2024-04-06 | 2024-04-06 |  | 0 | [5 empty] | 10.42% | 100% | 99.1% | -0.8978%
522 | Piling (Cutting only) |  | 9 | 9 | 2023-12-15 | 2023-12-23 | 2023-12-15 | 2023-12-15 | 2023-12-23 | 2023-12-23 |  | 0 | [5 empty] | 0.9677% | 100% | 100% | 0%
523 | Cutting off Pile to GL |  | 9 | 9 | 2023-12-15 | 2023-12-23 | 2023-12-15 | 2023-12-15 | 2023-12-23 | 2023-12-23 | 100 | 0 | 0 | 100 | % | 100 |  | 100% | 100% | 100% | 0%
524 | Completion of Piling |  | 0 | 1 | 2023-12-23 | 2023-12-23 | 2023-12-23 | 2023-12-23 | 2023-12-23 | 2023-12-23 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
525 | Pipe Gallery |  | 921 | 71 | 2023-12-20 | 2024-02-28 | 2023-12-27 | 2023-12-27 | 2024-04-06 | 2024-04-06 |  | 0 | [5 empty] | 99.03% | 100% | 99.09% | -0.9066%
526 | Structure |  | 643 | 63 | 2023-12-20 | 2024-02-20 | 2023-12-27 | 2023-12-27 | 2024-03-26 | 2024-03-26 |  | 0 | [5 empty] | 69.82% | 100% | 100% | 0%
527 | Pile Cap |  | 251 | 48 | 2023-12-20 | 2024-02-05 | 2023-12-27 | 2023-12-27 | 2024-03-22 | 2024-03-22 |  | 0 | [5 empty] | 39.04% | 100% | 100% | 0%
528 | Excavation |  | 28 | 28 | 2023-12-20 | 2024-01-16 | 2023-12-27 | 2023-12-27 | 2024-02-07 | 2024-02-07 | 100 | 0 | 0 | 100 | % | 100 |  | 11.16% | 100% | 100% | 0%
529 | Leveling and Compaction |  | 28 | 28 | 2023-12-22 | 2024-01-18 | 2023-12-29 | 2023-12-29 | 2024-02-09 | 2024-02-09 | 100 | 0 | 0 | 100 | % | 100 |  | 11.16% | 100% | 100% | 0%
530 | Lean Concrete Pouring |  | 28 | 28 | 2023-12-23 | 2024-01-19 | 2024-01-08 | 2024-01-08 | 2024-02-12 | 2024-02-12 | 100 | 0 | 0 | 100 | % | 100 |  | 11.16% | 100% | 100% | 0%
531 | Pile Cutting and Treatment |  | 28 | 28 | 2023-12-26 | 2024-01-22 | 2024-01-09 | 2024-01-09 | 2024-02-13 | 2024-02-13 | 100 | 0 | 0 | 100 | % | 100 |  | 11.16% | 100% | 100% | 0%
532 | Reinforcement Bar Fixing |  | 28 | 28 | 2023-12-29 | 2024-01-25 | 2024-01-19 | 2024-01-19 | 2024-03-01 | 2024-03-01 | 100 | 0 | 0 | 100 | % | 100 |  | 11.16% | 100% | 100% | 0%
533 | Formwork Fixing |  | 28 | 28 | 2024-01-02 | 2024-01-29 | 2024-01-18 | 2024-01-18 | 2024-03-01 | 2024-03-01 | 100 | 0 | 0 | 100 | % | 100 |  | 11.16% | 100% | 100% | 0%
534 | Concrete Pouring |  | 28 | 28 | 2024-01-04 | 2024-01-31 | 2024-01-27 | 2024-01-27 | 2024-03-21 | 2024-03-21 | 100 | 0 | 0 | 100 | % | 100 |  | 11.16% | 100% | 100% | 0%
535 | Formwork Dismantling |  | 27 | 27 | 2024-01-08 | 2024-02-03 | 2024-02-02 | 2024-02-02 | 2024-03-22 | 2024-03-22 | 100 | 0 | 0 | 100 | % | 100 |  | 10.76% | 100% | 100% | 0%
536 | Backfill with compaction |  | 28 | 28 | 2024-01-09 | 2024-02-05 | 2024-02-06 | 2024-02-06 | 2024-03-22 | 2024-03-22 | 100 | 0 | 0 | 100 | % | 100 |  | 11.16% | 100% | 100% | 0%
537 | Completion of Pile Cap |  | 0 | 1 | 2024-02-05 | 2024-02-05 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
538 | Stump |  | 168 | 41 | 2024-01-11 | 2024-02-20 | 2024-01-27 | 2024-01-27 | 2024-03-26 | 2024-03-26 |  | 0 | [5 empty] | 26.13% | 100% | 100% | 0%
539 | Reinforcement Bar Fixing |  | 28 | 28 | 2024-01-11 | 2024-02-07 | 2024-01-27 | 2024-01-27 | 2024-03-23 | 2024-03-23 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
540 | Formwork Fixing |  | 28 | 28 | 2024-01-13 | 2024-02-09 | 2024-03-19 | 2024-03-19 | 2024-03-24 | 2024-03-24 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
541 | Anchor Bolt Fixing |  | 28 | 28 | 2024-01-16 | 2024-02-12 | 2024-03-21 | 2024-03-21 | 2024-03-24 | 2024-03-24 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
542 | Concrete Pouring |  | 28 | 28 | 2024-01-19 | 2024-02-15 | 2024-03-23 | 2024-03-23 | 2024-03-24 | 2024-03-24 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
543 | Formwork Dismantling |  | 28 | 28 | 2024-01-23 | 2024-02-19 | 2024-03-25 | 2024-03-25 | 2024-03-26 | 2024-03-26 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
544 | Backfill with compaction |  | 28 | 28 | 2024-01-24 | 2024-02-20 | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-26 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
545 | Completion of Stump |  | 0 | 1 | 2024-02-20 | 2024-02-20 | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-26 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
546 | Ground Beam |  | 224 | 46 | 2023-12-23 | 2024-02-06 | 2023-12-30 | 2023-12-30 | 2024-03-22 | 2024-03-22 |  | 0 | [5 empty] | 34.84% | 100% | 100% | 0%
547 | Excavation |  | 28 | 28 | 2023-12-23 | 2024-01-19 | 2023-12-30 | 2023-12-30 | 2024-02-07 | 2024-02-07 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
548 | Leveling and Compaction |  | 28 | 28 | 2023-12-26 | 2024-01-22 | 2024-01-02 | 2024-01-02 | 2024-02-09 | 2024-02-09 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
549 | Lean Concrete Pouring |  | 28 | 28 | 2023-12-27 | 2024-01-23 | 2024-01-18 | 2024-01-18 | 2024-02-14 | 2024-02-14 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
550 | Reinforcement Bar Fixing |  | 28 | 28 | 2023-12-30 | 2024-01-26 | 2024-01-22 | 2024-01-22 | 2024-03-19 | 2024-03-19 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
551 | Formwork Fixing |  | 28 | 28 | 2024-01-03 | 2024-01-30 | 2024-01-25 | 2024-01-25 | 2024-03-20 | 2024-03-20 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
552 | Concrete Pouring |  | 28 | 28 | 2024-01-05 | 2024-02-01 | 2024-01-27 | 2024-01-27 | 2024-03-21 | 2024-03-21 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
553 | Formwork Dismantling |  | 28 | 28 | 2024-01-09 | 2024-02-05 | 2024-02-02 | 2024-02-02 | 2024-03-22 | 2024-03-22 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
554 | Backfill with compaction |  | 28 | 28 | 2024-01-10 | 2024-02-06 | 2024-02-03 | 2024-02-03 | 2024-03-22 | 2024-03-22 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
555 | Completion of Ground Beam |  | 0 | 1 | 2024-02-06 | 2024-02-06 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
556 | Completion of Structure |  | 0 | 1 | 2024-02-20 | 2024-02-20 | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-26 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
557 | Equipment Foundation |  | 278 | 51 | 2024-01-09 | 2024-02-28 | 2024-01-25 | 2024-01-25 | 2024-04-06 | 2024-04-06 |  | 0 | [5 empty] | 30.18% | 100% | 97% | -3.004%
558 | Equipment Foundation |  | 278 | 51 | 2024-01-09 | 2024-02-28 | 2024-01-25 | 2024-01-25 | 2024-04-06 | 2024-04-06 |  | 0 | [5 empty] | 100% | 100% | 97% | -3.004%
559 | Excavation |  | 28 | 28 | 2024-01-09 | 2024-02-05 | 2024-01-25 | 2024-01-25 | 2024-02-09 | 2024-02-09 | 100 | 0 | 0 | 100 | % | 100 |  | 10.07% | 100% | 100% | 0%
560 | Leveling and Compaction |  | 28 | 28 | 2024-01-11 | 2024-02-07 | 2024-01-25 | 2024-01-25 | 2024-02-12 | 2024-02-12 | 100 | 0 | 0 | 100 | % | 100 |  | 10.07% | 100% | 100% | 0%
561 | Lean Concrete Pouring |  | 28 | 28 | 2024-01-12 | 2024-02-08 | 2024-01-26 | 2024-01-26 | 2024-03-07 | 2024-03-07 | 100 | 0 | 0 | 100 | % | 100 |  | 10.07% | 100% | 100% | 0%
562 | Pile Cutting and Treatment |  | 27 | 27 | 2024-01-15 | 2024-02-10 | 2024-01-27 | 2024-01-27 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 9.712% | 100% | 100% | 0%
563 | Reinforcement Bar Fixing |  | 28 | 28 | 2024-01-18 | 2024-02-14 | 2024-02-06 | 2024-02-06 | 2024-03-04 | 2024-03-04 | 100 | 0 | 0 | 95 | % | 100 |  | 10.07% | 100% | 95% | -5%
564 | Formwork Fixing |  | 27 | 27 | 2024-01-22 | 2024-02-17 | 2024-02-09 | 2024-02-09 | 2024-03-07 | 2024-03-07 | 100 | 0 | 0 | 95 | % | 100 |  | 9.712% | 100% | 95% | -5%
565 | Anchor Bolt / Inserted Plate Fixing |  | 28 | 28 | 2024-01-24 | 2024-02-20 | 2024-02-26 | 2024-02-26 | 2024-03-23 | 2024-03-23 | 100 | 0 | 0 | 95 | % | 100 |  | 10.07% | 100% | 95% | -5%
566 | Concrete Pouring |  | 28 | 28 | 2024-01-27 | 2024-02-23 | 2024-02-27 | 2024-02-27 | 2024-03-27 | 2024-03-27 | 100 | 0 | 0 | 95 | % | 100 |  | 10.07% | 100% | 95% | -5%
567 | Formwork Dismantling |  | 28 | 28 | 2024-01-31 | 2024-02-27 | 2024-03-01 | 2024-03-01 | 2024-03-28 | 2024-03-28 | 100 | 0 | 0 | 95 | % | 100 |  | 10.07% | 100% | 95% | -5%
568 | Backfill with compaction |  | 28 | 28 | 2024-02-01 | 2024-02-28 | 2024-03-11 | 2024-03-11 | 2024-04-06 | 2024-04-06 | 100 | 0 | 0 | 95 | % | 100 |  | 10.07% | 100% | 95% | -5%
569 | Completion of Equipment Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
570 | Completion of Compressor / Equipment and Pump Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
571 | Completion of Substructure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
572 | Completion of Unit 800 - Pipe Gallery 3 & 4 |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
573 | Unit 800 - Reaction Frame (101-103) |  | 594 | 68 | 2023-12-15 | 2024-02-20 | 2023-12-15 | 2023-12-15 | 2024-04-01 | 2024-04-01 |  | 0 | [5 empty] | 6.656% | 100% | 100% | 0%
574 | Piling (Cutting only) |  | 21 | 21 | 2023-12-15 | 2024-01-04 | 2023-12-15 | 2023-12-15 | 2024-01-04 | 2024-01-04 |  | 0 | [5 empty] | 3.535% | 100% | 100% | 0%
575 | Cutting off Pile to GL |  | 21 | 21 | 2023-12-15 | 2024-01-04 | 2023-12-15 | 2023-12-15 | 2024-01-04 | 2024-01-04 | 100 | 0 | 0 | 100 | % | 100 |  | 100% | 100% | 100% | 0%
576 | Completion of Piling |  | 0 | 1 | 2024-01-04 | 2024-01-04 | 2024-01-04 | 2024-01-04 | 2024-01-04 | 2024-01-04 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
577 | Substructure |  | 573 | 61 | 2023-12-22 | 2024-02-20 | 2024-01-11 | 2024-01-11 | 2024-04-01 | 2024-04-01 |  | 0 | [5 empty] | 96.46% | 100% | 100% | 0%
578 | Structure |  | 398 | 53 | 2023-12-22 | 2024-02-12 | 2024-01-11 | 2024-01-11 | 2024-03-22 | 2024-03-22 |  | 0 | [5 empty] | 69.46% | 100% | 100% | 0%
579 | Pile Cap |  | 155 | 37 | 2023-12-22 | 2024-01-27 | 2024-01-11 | 2024-01-11 | 2024-03-08 | 2024-03-08 |  | 0 | [5 empty] | 38.94% | 100% | 100% | 0%
580 | Excavation |  | 18 | 18 | 2023-12-22 | 2024-01-08 | 2024-01-11 | 2024-01-11 | 2024-01-26 | 2024-01-26 | 100 | 0 | 0 | 100 | % | 100 |  | 11.61% | 100% | 100% | 0%
581 | Leveling and Compaction |  | 17 | 17 | 2023-12-25 | 2024-01-10 | 2024-01-17 | 2024-01-17 | 2024-01-30 | 2024-01-30 | 100 | 0 | 0 | 100 | % | 100 |  | 10.97% | 100% | 100% | 0%
582 | Lean Concrete Pouring |  | 17 | 17 | 2023-12-26 | 2024-01-11 | 2024-01-18 | 2024-01-18 | 2024-02-01 | 2024-02-01 | 100 | 0 | 0 | 100 | % | 100 |  | 10.97% | 100% | 100% | 0%
583 | Pile Cutting and Treatment |  | 17 | 17 | 2023-12-28 | 2024-01-13 | 2024-01-19 | 2024-01-19 | 2024-02-02 | 2024-02-02 | 100 | 0 | 0 | 100 | % | 100 |  | 10.97% | 100% | 100% | 0%
584 | Reinforcement Bar Fixing |  | 17 | 17 | 2024-01-01 | 2024-01-17 | 2024-02-08 | 2024-02-08 | 2024-02-27 | 2024-02-27 | 100 | 0 | 0 | 100 | % | 100 |  | 10.97% | 100% | 100% | 0%
585 | Formwork Fixing |  | 17 | 17 | 2024-01-04 | 2024-01-20 | 2024-02-08 | 2024-02-08 | 2024-02-28 | 2024-02-28 | 100 | 0 | 0 | 100 | % | 100 |  | 10.97% | 100% | 100% | 0%
586 | Concrete Pouring |  | 18 | 18 | 2024-01-06 | 2024-01-23 | 2024-02-28 | 2024-02-28 | 2024-03-01 | 2024-03-01 | 100 | 0 | 0 | 100 | % | 100 |  | 11.61% | 100% | 100% | 0%
587 | Formwork Dismantling |  | 17 | 17 | 2024-01-10 | 2024-01-26 | 2024-03-01 | 2024-03-01 | 2024-03-06 | 2024-03-06 | 100 | 0 | 0 | 100 | % | 100 |  | 10.97% | 100% | 100% | 0%
588 | Backfill with compaction |  | 17 | 17 | 2024-01-11 | 2024-01-27 | 2024-03-07 | 2024-03-07 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 10.97% | 100% | 100% | 0%
589 | Completion of Pile Cap |  | 0 | 1 | 2024-01-27 | 2024-01-27 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
590 | Stump |  | 104 | 31 | 2024-01-13 | 2024-02-12 | 2024-02-26 | 2024-02-26 | 2024-03-22 | 2024-03-22 |  | 0 | [5 empty] | 26.13% | 100% | 100% | 0%
591 | Reinforcement Bar Fixing |  | 18 | 18 | 2024-01-13 | 2024-01-30 | 2024-02-26 | 2024-02-26 | 2024-03-15 | 2024-03-15 | 100 | 0 | 0 | 100 | % | 100 |  | 17.31% | 100% | 100% | 0%
592 | Formwork Fixing |  | 17 | 17 | 2024-01-16 | 2024-02-01 | 2024-03-19 | 2024-03-19 | 2024-03-20 | 2024-03-20 | 100 | 0 | 0 | 100 | % | 100 |  | 16.35% | 100% | 100% | 0%
593 | Anchor Bolt Fixing |  | 17 | 17 | 2024-01-18 | 2024-02-03 | 2024-03-20 | 2024-03-20 | 2024-03-21 | 2024-03-21 | 100 | 0 | 0 | 100 | % | 100 |  | 16.35% | 100% | 100% | 0%
594 | Concrete Pouring |  | 17 | 17 | 2024-01-22 | 2024-02-07 | 2024-03-21 | 2024-03-21 | 2024-03-22 | 2024-03-22 | 100 | 0 | 0 | 100 | % | 100 |  | 16.35% | 100% | 100% | 0%
595 | Formwork Dismantling |  | 17 | 17 | 2024-01-25 | 2024-02-10 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 100 | 0 | 0 | 100 | % | 100 |  | 16.35% | 100% | 100% | 0%
596 | Backfill with compaction |  | 18 | 18 | 2024-01-26 | 2024-02-12 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 100 | 0 | 0 | 100 | % | 100 |  | 17.31% | 100% | 100% | 0%
597 | Completion of Stump |  | 0 | 1 | 2024-02-12 | 2024-02-12 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
598 | Ground Beam |  | 139 | 35 | 2023-12-26 | 2024-01-29 | 2024-01-15 | 2024-01-15 | 2024-03-08 | 2024-03-08 |  | 0 | [5 empty] | 34.92% | 100% | 100% | 0%
599 | Excavation |  | 17 | 17 | 2023-12-26 | 2024-01-11 | 2024-01-15 | 2024-01-15 | 2024-01-28 | 2024-01-28 | 100 | 0 | 0 | 100 | % | 100 |  | 12.23% | 100% | 100% | 0%
600 | Leveling and Compaction |  | 17 | 17 | 2023-12-28 | 2024-01-13 | 2024-01-17 | 2024-01-17 | 2024-01-31 | 2024-01-31 | 100 | 0 | 0 | 100 | % | 100 |  | 12.23% | 100% | 100% | 0%
601 | Lean Concrete Pouring |  | 18 | 18 | 2023-12-29 | 2024-01-15 | 2024-02-13 | 2024-02-13 | 2024-02-23 | 2024-02-23 | 100 | 0 | 0 | 100 | % | 100 |  | 12.95% | 100% | 100% | 0%
602 | Reinforcement Bar Fixing |  | 17 | 17 | 2024-01-02 | 2024-01-18 | 2024-02-16 | 2024-02-16 | 2024-02-26 | 2024-02-26 | 100 | 0 | 0 | 100 | % | 100 |  | 12.23% | 100% | 100% | 0%
603 | Formwork Fixing |  | 18 | 18 | 2024-01-05 | 2024-01-22 | 2024-02-24 | 2024-02-24 | 2024-02-27 | 2024-02-27 | 100 | 0 | 0 | 100 | % | 100 |  | 12.95% | 100% | 100% | 0%
604 | Concrete Pouring |  | 17 | 17 | 2024-01-08 | 2024-01-24 | 2024-02-28 | 2024-02-28 | 2024-03-01 | 2024-03-01 | 100 | 0 | 0 | 100 | % | 100 |  | 12.23% | 100% | 100% | 0%
605 | Formwork Dismantling |  | 17 | 17 | 2024-01-11 | 2024-01-27 | 2024-03-01 | 2024-03-01 | 2024-03-06 | 2024-03-06 | 100 | 0 | 0 | 100 | % | 100 |  | 12.23% | 100% | 100% | 0%
606 | Backfill with compaction |  | 18 | 18 | 2024-01-12 | 2024-01-29 | 2024-03-07 | 2024-03-07 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 12.95% | 100% | 100% | 0%
607 | Completion of Ground Beam |  | 0 | 1 | 2024-01-29 | 2024-01-29 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
608 | Completion of Structure |  | 0 | 1 | 2024-02-12 | 2024-02-12 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
609 | Equipment Foundation |  | 175 | 41 | 2024-01-11 | 2024-02-20 | 2024-01-30 | 2024-01-30 | 2024-04-01 | 2024-04-01 |  | 0 | [5 empty] | 30.54% | 100% | 100% | 0%
610 | Equipment Foundation |  | 175 | 41 | 2024-01-11 | 2024-02-20 | 2024-01-30 | 2024-01-30 | 2024-04-01 | 2024-04-01 |  | 0 | [5 empty] | 100% | 100% | 100% | 0%
611 | Excavation |  | 17 | 17 | 2024-01-11 | 2024-01-27 | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2024-01-30 | 100 | 0 | 0 | 100 | % | 100 |  | 9.714% | 100% | 100% | 0%
612 | Leveling and Compaction |  | 18 | 18 | 2024-01-13 | 2024-01-30 | 2024-02-02 | 2024-02-02 | 2024-02-17 | 2024-02-17 | 100 | 0 | 0 | 100 | % | 100 |  | 10.29% | 100% | 100% | 0%
613 | Lean Concrete Pouring |  | 17 | 17 | 2024-01-15 | 2024-01-31 | 2024-02-19 | 2024-02-19 | 2024-02-19 | 2024-02-19 | 100 | 0 | 0 | 100 | % | 100 |  | 9.714% | 100% | 100% | 0%
614 | Pile Cutting and Treatment |  | 17 | 17 | 2024-01-17 | 2024-02-02 | 2024-02-20 | 2024-02-20 | 2024-02-21 | 2024-02-21 | 100 | 0 | 0 | 100 | % | 100 |  | 9.714% | 100% | 100% | 0%
615 | Reinforcement Bar Fixing |  | 18 | 18 | 2024-01-20 | 2024-02-06 | 2024-02-20 | 2024-02-20 | 2024-03-28 | 2024-03-28 | 100 | 0 | 0 | 100 | % | 100 |  | 10.29% | 100% | 100% | 0%
616 | Formwork Fixing |  | 17 | 17 | 2024-01-24 | 2024-02-09 | 2024-02-21 | 2024-02-21 | 2024-03-28 | 2024-03-28 | 100 | 0 | 0 | 100 | % | 100 |  | 9.714% | 100% | 100% | 0%
617 | Anchor Bolt / Inserted Plate Fixing |  | 18 | 18 | 2024-01-26 | 2024-02-12 | 2024-02-23 | 2024-02-23 | 2024-03-28 | 2024-03-28 | 100 | 0 | 0 | 100 | % | 100 |  | 10.29% | 100% | 100% | 0%
618 | Concrete Pouring |  | 17 | 17 | 2024-01-30 | 2024-02-15 | 2024-03-01 | 2024-03-01 | 2024-03-29 | 2024-03-29 | 100 | 0 | 0 | 100 | % | 100 |  | 9.714% | 100% | 100% | 0%
619 | Formwork Dismantling |  | 18 | 18 | 2024-02-02 | 2024-02-19 | 2024-03-05 | 2024-03-05 | 2024-03-29 | 2024-03-29 | 100 | 0 | 0 | 100 | % | 100 |  | 10.29% | 100% | 100% | 0%
620 | Backfill with compaction |  | 18 | 18 | 2024-02-03 | 2024-02-20 | 2024-03-14 | 2024-03-14 | 2024-04-01 | 2024-04-01 | 100 | 0 | 0 | 100 | % | 100 |  | 10.29% | 100% | 100% | 0%
621 | Completion of Equipment Foundation |  | 0 | 1 | 2024-02-20 | 2024-02-20 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
622 | Completion of Equipment and Pump Foundation |  | 0 | 1 | 2024-02-20 | 2024-02-20 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
623 | Completion of Substructure |  | 0 | 1 | 2024-02-20 | 2024-02-20 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
624 | Completion of Unit 800 - Reaction Frame (101-103) |  | 0 | 1 | 2024-02-20 | 2024-02-20 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
625 | Unit 800 - Reaction Frame (103-116) |  | 1134 | 76 | 2023-12-15 | 2024-02-28 | 2023-12-11 | 2023-12-11 | 2024-04-19 | 2024-04-19 |  | 0 | [5 empty] | 12.71% | 100% | 100% | 0%
626 | Piling (Cutting only) |  | 28 | 28 | 2023-12-15 | 2024-01-11 | 2023-12-11 | 2023-12-11 | 2024-01-11 | 2024-01-11 |  | 0 | [5 empty] | 2.469% | 100% | 100% | 0%
627 | Cutting off Pile to GL |  | 28 | 28 | 2023-12-15 | 2024-01-11 | 2023-12-11 | 2023-12-11 | 2024-01-06 | 2024-01-06 | 100 | 0 | 0 | 100 | % | 100 |  | 100% | 100% | 100% | 0%
628 | Completion of Piling |  | 0 | 1 | 2024-01-11 | 2024-01-11 | 2024-01-11 | 2024-01-11 | 2024-01-11 | 2024-01-11 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
629 | Substructure |  | 1106 | 71 | 2023-12-20 | 2024-02-28 | 2023-12-19 | 2023-12-19 | 2024-04-19 | 2024-04-19 |  | 0 | [5 empty] | 97.53% | 100% | 100% | 0%
630 | Structure |  | 828 | 71 | 2023-12-20 | 2024-02-28 | 2023-12-19 | 2023-12-19 | 2024-03-15 | 2024-03-15 |  | 0 | [5 empty] | 74.86% | 100% | 100% | 0%
631 | Pile Cap |  | 324 | 56 | 2023-12-20 | 2024-02-13 | 2023-12-19 | 2023-12-19 | 2024-02-28 | 2024-02-28 |  | 0 | [5 empty] | 39.13% | 100% | 100% | 0%
632 | Excavation |  | 36 | 36 | 2023-12-20 | 2024-01-24 | 2023-12-19 | 2023-12-19 | 2024-01-26 | 2024-01-26 | 100 | 0 | 0 | 100 | % | 100 |  | 11.11% | 100% | 100% | 0%
633 | Leveling and Compaction |  | 36 | 36 | 2023-12-22 | 2024-01-26 | 2023-12-21 | 2023-12-21 | 2024-01-27 | 2024-01-27 | 100 | 0 | 0 | 100 | % | 100 |  | 11.11% | 100% | 100% | 0%
634 | Lean Concrete Pouring |  | 36 | 36 | 2023-12-23 | 2024-01-27 | 2024-01-03 | 2024-01-03 | 2024-02-01 | 2024-02-01 | 100 | 0 | 0 | 100 | % | 100 |  | 11.11% | 100% | 100% | 0%
635 | Pile Cutting and Treatment |  | 36 | 36 | 2023-12-26 | 2024-01-30 | 2024-01-08 | 2024-01-08 | 2024-02-02 | 2024-02-02 | 100 | 0 | 0 | 100 | % | 100 |  | 11.11% | 100% | 100% | 0%
636 | Reinforcement Bar Fixing |  | 36 | 36 | 2023-12-29 | 2024-02-02 | 2024-01-19 | 2024-01-19 | 2024-02-09 | 2024-02-09 | 100 | 0 | 0 | 100 | % | 100 |  | 11.11% | 100% | 100% | 0%
637 | Formwork Fixing |  | 36 | 36 | 2024-01-02 | 2024-02-06 | 2024-01-19 | 2024-01-19 | 2024-02-09 | 2024-02-09 | 100 | 0 | 0 | 100 | % | 100 |  | 11.11% | 100% | 100% | 0%
638 | Concrete Pouring |  | 36 | 36 | 2024-01-04 | 2024-02-08 | 2024-02-01 | 2024-02-01 | 2024-02-26 | 2024-02-26 | 100 | 0 | 0 | 100 | % | 100 |  | 11.11% | 100% | 100% | 0%
639 | Formwork Dismantling |  | 36 | 36 | 2024-01-08 | 2024-02-12 | 2024-02-05 | 2024-02-05 | 2024-02-27 | 2024-02-27 | 100 | 0 | 0 | 100 | % | 100 |  | 11.11% | 100% | 100% | 0%
640 | Backfill with compaction |  | 36 | 36 | 2024-01-09 | 2024-02-13 | 2024-02-07 | 2024-02-07 | 2024-02-28 | 2024-02-28 | 100 | 0 | 0 | 100 | % | 100 |  | 11.11% | 100% | 100% | 0%
641 | Completion of Pile Cap |  | 0 | 1 | 2024-02-13 | 2024-02-13 | 2024-02-28 | 2024-02-28 | 2024-02-28 | 2024-02-28 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
642 | Stump |  | 216 | 49 | 2024-01-11 | 2024-02-28 | 2024-02-08 | 2024-02-08 | 2024-03-15 | 2024-03-15 |  | 0 | [5 empty] | 26.09% | 100% | 100% | 0%
643 | Reinforcement Bar Fixing |  | 36 | 36 | 2024-01-11 | 2024-02-15 | 2024-02-08 | 2024-02-08 | 2024-03-06 | 2024-03-06 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
644 | Formwork Fixing |  | 36 | 36 | 2024-01-13 | 2024-02-17 | 2024-02-21 | 2024-02-21 | 2024-03-13 | 2024-03-13 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
645 | Anchor Bolt Fixing |  | 36 | 36 | 2024-01-16 | 2024-02-20 | 2024-02-23 | 2024-02-23 | 2024-03-14 | 2024-03-14 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
646 | Concrete Pouring |  | 36 | 36 | 2024-01-19 | 2024-02-23 | 2024-03-08 | 2024-03-08 | 2024-03-15 | 2024-03-15 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
647 | Formwork Dismantling |  | 36 | 36 | 2024-01-23 | 2024-02-27 | 2024-03-09 | 2024-03-09 | 2024-03-15 | 2024-03-15 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
648 | Backfill with compaction |  | 36 | 36 | 2024-01-24 | 2024-02-28 | 2024-03-10 | 2024-03-10 | 2024-03-15 | 2024-03-15 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
649 | Completion of Stump |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
650 | Ground Beam |  | 288 | 54 | 2023-12-23 | 2024-02-14 | 2023-12-22 | 2023-12-22 | 2024-02-28 | 2024-02-28 |  | 0 | [5 empty] | 34.78% | 100% | 100% | 0%
651 | Excavation |  | 36 | 36 | 2023-12-23 | 2024-01-27 | 2023-12-22 | 2023-12-22 | 2024-01-26 | 2024-01-26 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
652 | Leveling and Compaction |  | 36 | 36 | 2023-12-26 | 2024-01-30 | 2023-12-25 | 2023-12-25 | 2024-01-30 | 2024-01-30 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
653 | Lean Concrete Pouring |  | 36 | 36 | 2023-12-27 | 2024-01-31 | 2024-01-17 | 2024-01-17 | 2024-02-07 | 2024-02-07 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
654 | Reinforcement Bar Fixing |  | 36 | 36 | 2023-12-30 | 2024-02-03 | 2024-01-29 | 2024-01-29 | 2024-02-16 | 2024-02-16 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
655 | Formwork Fixing |  | 36 | 36 | 2024-01-03 | 2024-02-07 | 2024-01-29 | 2024-01-29 | 2024-02-16 | 2024-02-16 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
656 | Concrete Pouring |  | 36 | 36 | 2024-01-05 | 2024-02-09 | 2024-02-01 | 2024-02-01 | 2024-02-26 | 2024-02-26 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
657 | Formwork Dismantling |  | 36 | 36 | 2024-01-09 | 2024-02-13 | 2024-02-05 | 2024-02-05 | 2024-02-27 | 2024-02-27 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
658 | Backfill with compaction |  | 36 | 36 | 2024-01-10 | 2024-02-14 | 2024-02-06 | 2024-02-06 | 2024-02-28 | 2024-02-28 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
659 | Completion of Ground Beam |  | 0 | 1 | 2024-02-14 | 2024-02-14 | 2024-02-28 | 2024-02-28 | 2024-02-28 | 2024-02-28 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
660 | Completion of Structure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
661 | Equipment Foundation |  | 278 | 51 | 2024-01-09 | 2024-02-28 | 2024-01-08 | 2024-01-08 | 2024-04-19 | 2024-04-19 |  | 0 | [5 empty] | 25.14% | 100% | 100% | 0%
662 | Equipment Foundation |  | 278 | 51 | 2024-01-09 | 2024-02-28 | 2024-01-08 | 2024-01-08 | 2024-04-19 | 2024-04-19 |  | 0 | [5 empty] | 100% | 100% | 100% | 0%
663 | Excavation |  | 28 | 28 | 2024-01-09 | 2024-02-05 | 2024-01-08 | 2024-01-08 | 2024-01-30 | 2024-01-30 | 100 | 0 | 0 | 100 | % | 100 |  | 10.07% | 100% | 100% | 0%
664 | Leveling and Compaction |  | 28 | 28 | 2024-01-11 | 2024-02-07 | 2024-01-10 | 2024-01-10 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 10.07% | 100% | 100% | 0%
665 | Lean Concrete Pouring |  | 28 | 28 | 2024-01-12 | 2024-02-08 | 2024-02-06 | 2024-02-06 | 2024-04-05 | 2024-04-05 | 100 | 0 | 0 | 100 | % | 100 |  | 10.07% | 100% | 100% | 0%
666 | Pile Cutting and Treatment |  | 27 | 27 | 2024-01-15 | 2024-02-10 | 2024-02-08 | 2024-02-08 | 2024-04-05 | 2024-04-05 | 100 | 0 | 0 | 100 | % | 100 |  | 9.712% | 100% | 100% | 0%
667 | Reinforcement Bar Fixing |  | 28 | 28 | 2024-01-18 | 2024-02-14 | 2024-02-28 | 2024-02-28 | 2024-04-16 | 2024-04-16 | 100 | 0 | 0 | 100 | % | 100 |  | 10.07% | 100% | 100% | 0%
668 | Formwork Fixing |  | 27 | 27 | 2024-01-22 | 2024-02-17 | 2024-02-29 | 2024-02-29 | 2024-04-17 | 2024-04-17 | 100 | 0 | 0 | 100 | % | 100 |  | 9.712% | 100% | 100% | 0%
669 | Anchor Bolt / Inserted Plate Fixing |  | 28 | 28 | 2024-01-24 | 2024-02-20 | 2024-03-02 | 2024-03-02 | 2024-04-17 | 2024-04-17 | 100 | 0 | 0 | 100 | % | 100 |  | 10.07% | 100% | 100% | 0%
670 | Concrete Pouring |  | 28 | 28 | 2024-01-27 | 2024-02-23 | 2024-03-07 | 2024-03-07 | 2024-04-18 | 2024-04-18 | 100 | 0 | 0 | 100 | % | 100 |  | 10.07% | 100% | 100% | 0%
671 | Formwork Dismantling |  | 28 | 28 | 2024-01-31 | 2024-02-27 | 2024-03-08 | 2024-03-08 | 2024-04-19 | 2024-04-19 | 100 | 0 | 0 | 100 | % | 100 |  | 10.07% | 100% | 100% | 0%
672 | Backfill with compaction |  | 28 | 28 | 2024-02-01 | 2024-02-28 | 2024-03-21 | 2024-03-21 | 2024-04-19 | 2024-04-19 | 100 | 0 | 0 | 100 | % | 100 |  | 10.07% | 100% | 100% | 0%
673 | Completion of Equipment Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
674 | Completion of Equipment and Pump Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
675 | Completion of Substructure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
676 | Completion of Unit 800 - Reaction Frame (103-116) |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
677 | Unit 900 - HPU |  | 1156 | 87 | 2023-12-04 | 2024-02-28 | 2023-12-04 | 2023-12-04 | 2024-03-08 | 2024-03-08 |  | 0.02 | [5 empty] | 12.95% | 100% | 100% | 0%
678 | Piling (Cutting only) |  | 17 | 17 | 2023-12-04 | 2023-12-20 | 2023-12-04 | 2023-12-04 | 2023-12-20 | 2023-12-20 |  | 0.99 | [5 empty] | 1.471% | 100% | 100% | 0%
679 | Cutting off Pile to GL |  | 17 | 17 | 2023-12-04 | 2023-12-20 | 2023-12-04 | 2023-12-04 | 2023-12-20 | 2023-12-20 | 100 | 1 | 100 | 100 | % | 100 |  | 100% | 100% | 100% | 0%
680 | Completion of Piling |  | 0 | 1 | 2023-12-20 | 2023-12-20 | 2023-12-20 | 2023-12-20 | 2023-12-20 | 2023-12-20 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
681 | Substructure |  | 1139 | 70 | 2023-12-21 | 2024-02-28 | 2023-12-07 | 2023-12-07 | 2024-03-08 | 2024-03-08 |  | 0 | [5 empty] | 98.53% | 100% | 100% | 0%
682 | Structure |  | 801 | 70 | 2023-12-21 | 2024-02-28 | 2023-12-07 | 2023-12-07 | 2024-03-01 | 2024-03-01 |  | 0 | [5 empty] | 70.32% | 100% | 100% | 0%
683 | Pile Cap |  | 314 | 55 | 2023-12-21 | 2024-02-13 | 2023-12-07 | 2023-12-07 | 2024-02-08 | 2024-02-08 |  | 0 | [5 empty] | 39.2% | 100% | 100% | 0%
684 | Excavation |  | 35 | 35 | 2023-12-21 | 2024-01-24 | 2023-12-07 | 2023-12-07 | 2024-01-11 | 2024-01-11 | 100 | 0 | 0 | 100 | % | 100 |  | 11.15% | 100% | 100% | 0%
685 | Leveling and Compaction |  | 35 | 35 | 2023-12-23 | 2024-01-26 | 2023-12-09 | 2023-12-09 | 2024-01-12 | 2024-01-12 | 100 | 0 | 0 | 100 | % | 100 |  | 11.15% | 100% | 100% | 0%
686 | Lean Concrete Pouring |  | 34 | 34 | 2023-12-25 | 2024-01-27 | 2023-12-28 | 2023-12-28 | 2024-01-19 | 2024-01-19 | 100 | 0 | 0 | 100 | % | 100 |  | 10.83% | 100% | 100% | 0%
687 | Pile Cutting and Treatment |  | 35 | 35 | 2023-12-27 | 2024-01-30 | 2023-12-30 | 2023-12-30 | 2024-01-26 | 2024-01-26 | 100 | 0 | 0 | 100 | % | 100 |  | 11.15% | 100% | 100% | 0%
688 | Reinforcement Bar Fixing |  | 35 | 35 | 2023-12-30 | 2024-02-02 | 2024-01-03 | 2024-01-03 | 2024-01-29 | 2024-01-29 | 100 | 0 | 0 | 100 | % | 100 |  | 11.15% | 100% | 100% | 0%
689 | Formwork Fixing |  | 35 | 35 | 2024-01-03 | 2024-02-06 | 2024-01-06 | 2024-01-06 | 2024-01-29 | 2024-01-29 | 100 | 0 | 0 | 100 | % | 100 |  | 11.15% | 100% | 100% | 0%
690 | Concrete Pouring |  | 35 | 35 | 2024-01-05 | 2024-02-08 | 2024-01-12 | 2024-01-12 | 2024-01-30 | 2024-01-30 | 100 | 0 | 0 | 100 | % | 100 |  | 11.15% | 100% | 100% | 0%
691 | Formwork Dismantling |  | 35 | 35 | 2024-01-09 | 2024-02-12 | 2024-01-15 | 2024-01-15 | 2024-02-02 | 2024-02-02 | 100 | 0 | 0 | 100 | % | 100 |  | 11.15% | 100% | 100% | 0%
692 | Backfill with compaction |  | 35 | 35 | 2024-01-10 | 2024-02-13 | 2024-01-26 | 2024-01-26 | 2024-02-08 | 2024-02-08 | 100 | 0 | 0 | 100 | % | 100 |  | 11.15% | 100% | 100% | 0%
693 | Completion of Pile Cap |  | 0 | 1 | 2024-02-13 | 2024-02-13 | 2024-02-08 | 2024-02-08 | 2024-02-08 | 2024-02-08 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
694 | Stump |  | 209 | 48 | 2024-01-12 | 2024-02-28 | 2024-01-12 | 2024-01-12 | 2024-03-01 | 2024-03-01 |  | 0 | [5 empty] | 26.09% | 100% | 100% | 0%
695 | Reinforcement Bar Fixing |  | 35 | 35 | 2024-01-12 | 2024-02-15 | 2024-01-12 | 2024-01-12 | 2024-02-08 | 2024-02-08 | 100 | 0 | 0 | 100 | % | 100 |  | 16.75% | 100% | 100% | 0%
696 | Formwork Fixing |  | 34 | 34 | 2024-01-15 | 2024-02-17 | 2024-01-30 | 2024-01-30 | 2024-02-23 | 2024-02-23 | 100 | 0 | 0 | 100 | % | 100 |  | 16.27% | 100% | 100% | 0%
697 | Anchor Bolt Fixing |  | 35 | 35 | 2024-01-17 | 2024-02-20 | 2024-02-01 | 2024-02-01 | 2024-02-24 | 2024-02-24 | 100 | 0 | 0 | 100 | % | 100 |  | 16.75% | 100% | 100% | 0%
698 | Concrete Pouring |  | 35 | 35 | 2024-01-20 | 2024-02-23 | 2024-02-14 | 2024-02-14 | 2024-02-26 | 2024-02-26 | 100 | 0 | 0 | 100 | % | 100 |  | 16.75% | 100% | 100% | 0%
699 | Formwork Dismantling |  | 35 | 35 | 2024-01-24 | 2024-02-27 | 2024-02-16 | 2024-02-16 | 2024-02-28 | 2024-02-28 | 100 | 0 | 0 | 100 | % | 100 |  | 16.75% | 100% | 100% | 0%
700 | Backfill with compaction |  | 35 | 35 | 2024-01-25 | 2024-02-28 | 2024-02-23 | 2024-02-23 | 2024-03-01 | 2024-03-01 | 100 | 0 | 0 | 100 | % | 100 |  | 16.75% | 100% | 100% | 0%
701 | Completion of Stump |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
702 | Ground Beam |  | 278 | 52 | 2023-12-25 | 2024-02-14 | 2023-12-11 | 2023-12-11 | 2024-02-08 | 2024-02-08 |  | 0 | [5 empty] | 34.71% | 100% | 100% | 0%
703 | Excavation |  | 34 | 34 | 2023-12-25 | 2024-01-27 | 2023-12-11 | 2023-12-11 | 2024-01-11 | 2024-01-11 | 100 | 0 | 0 | 100 | % | 100 |  | 12.23% | 100% | 100% | 0%
704 | Leveling and Compaction |  | 35 | 35 | 2023-12-27 | 2024-01-30 | 2023-12-13 | 2023-12-13 | 2024-01-12 | 2024-01-12 | 100 | 0 | 0 | 100 | % | 100 |  | 12.59% | 100% | 100% | 0%
705 | Lean Concrete Pouring |  | 35 | 35 | 2023-12-28 | 2024-01-31 | 2024-01-05 | 2024-01-05 | 2024-01-24 | 2024-01-24 | 100 | 0 | 0 | 100 | % | 100 |  | 12.59% | 100% | 100% | 0%
706 | Reinforcement Bar Fixing |  | 34 | 34 | 2024-01-01 | 2024-02-03 | 2024-01-08 | 2024-01-08 | 2024-01-29 | 2024-01-29 | 100 | 0 | 0 | 100 | % | 100 |  | 12.23% | 100% | 100% | 0%
707 | Formwork Fixing |  | 35 | 35 | 2024-01-04 | 2024-02-07 | 2024-01-10 | 2024-01-10 | 2024-01-29 | 2024-01-29 | 100 | 0 | 0 | 100 | % | 100 |  | 12.59% | 100% | 100% | 0%
708 | Concrete Pouring |  | 35 | 35 | 2024-01-06 | 2024-02-09 | 2024-01-12 | 2024-01-12 | 2024-01-30 | 2024-01-30 | 100 | 0 | 0 | 100 | % | 100 |  | 12.59% | 100% | 100% | 0%
709 | Formwork Dismantling |  | 35 | 35 | 2024-01-10 | 2024-02-13 | 2024-01-16 | 2024-01-16 | 2024-02-02 | 2024-02-02 | 100 | 0 | 0 | 100 | % | 100 |  | 12.59% | 100% | 100% | 0%
710 | Backfill with compaction |  | 35 | 35 | 2024-01-11 | 2024-02-14 | 2024-01-26 | 2024-01-26 | 2024-02-08 | 2024-02-08 | 100 | 0 | 0 | 100 | % | 100 |  | 12.59% | 100% | 100% | 0%
711 | Completion of Ground Beam |  | 0 | 1 | 2024-02-14 | 2024-02-14 | 2024-02-08 | 2024-02-08 | 2024-02-08 | 2024-02-08 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
712 | Completion of Structure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
713 | Equipment Foundation |  | 338 | 57 | 2023-12-21 | 2024-02-15 | 2023-12-09 | 2023-12-09 | 2024-03-08 | 2024-03-08 |  | 0 | [5 empty] | 29.68% | 100% | 100% | 0%
714 | Equipment Foundation |  | 338 | 57 | 2023-12-21 | 2024-02-15 | 2023-12-09 | 2023-12-09 | 2024-03-08 | 2024-03-08 |  | 0 | [5 empty] | 100% | 100% | 100% | 0%
715 | Excavation |  | 34 | 34 | 2023-12-21 | 2024-01-23 | 2023-12-09 | 2023-12-09 | 2024-01-12 | 2024-01-12 | 100 | 0 | 0 | 100 | % | 100 |  | 10.06% | 100% | 100% | 0%
716 | Leveling and Compaction |  | 34 | 34 | 2023-12-23 | 2024-01-25 | 2023-12-10 | 2023-12-10 | 2024-01-12 | 2024-01-12 | 100 | 0 | 0 | 100 | % | 100 |  | 10.06% | 100% | 100% | 0%
717 | Lean Concrete Pouring |  | 33 | 33 | 2023-12-25 | 2024-01-26 | 2023-12-11 | 2023-12-11 | 2024-02-08 | 2024-02-08 | 100 | 0 | 0 | 100 | % | 100 |  | 9.763% | 100% | 100% | 0%
718 | Pile Cutting and Treatment |  | 34 | 34 | 2023-12-27 | 2024-01-29 | 2023-12-12 | 2023-12-12 | 2024-02-09 | 2024-02-09 | 100 | 0 | 0 | 100 | % | 100 |  | 10.06% | 100% | 100% | 0%
719 | Reinforcement Bar Fixing |  | 34 | 34 | 2023-12-30 | 2024-02-01 | 2023-12-15 | 2023-12-15 | 2024-03-01 | 2024-03-01 | 100 | 0 | 0 | 100 | % | 100 |  | 10.06% | 100% | 100% | 0%
720 | Formwork Fixing |  | 34 | 34 | 2024-01-03 | 2024-02-05 | 2023-12-19 | 2023-12-19 | 2024-03-01 | 2024-03-01 | 100 | 0 | 0 | 100 | % | 100 |  | 10.06% | 100% | 100% | 0%
721 | Anchor Bolt / Inserted Plate Fixing |  | 34 | 34 | 2024-01-05 | 2024-02-07 | 2023-12-21 | 2023-12-21 | 2024-03-07 | 2024-03-07 | 100 | 0 | 0 | 100 | % | 100 |  | 10.06% | 100% | 100% | 0%
722 | Concrete Pouring |  | 33 | 33 | 2024-01-09 | 2024-02-10 | 2024-01-09 | 2024-01-09 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 9.763% | 100% | 100% | 0%
723 | Formwork Dismantling |  | 34 | 34 | 2024-01-12 | 2024-02-14 | 2024-01-15 | 2024-01-15 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 10.06% | 100% | 100% | 0%
724 | Backfill with compaction |  | 34 | 34 | 2024-01-13 | 2024-02-15 | 2024-01-26 | 2024-01-26 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 10.06% | 100% | 100% | 0%
725 | Completion of Equipment Foundation |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
726 | Completion of Equipment and Pump Foundation |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
727 | Completion of Substructure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
728 | Completion of Unit 900 - HPU |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
729 | COMPLETION OF UNIT 700, 800 and 900 (SUBSTRUCTURE) |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
730 | UNIT FACILITIES (SUBSTRUCTURE) |  | 2471 | 78 | 2023-12-13 | 2024-02-28 | 2023-12-13 | 2023-12-13 | 2024-06-03 | 2024-06-03 |  | 0 | [5 empty] | 21.68% | 100% | 82.97% | -17.03%
731 | Unit 250 - Pipe Rack within Facility |  | 943 | 78 | 2023-12-13 | 2024-02-28 | 2024-01-12 | 2024-01-12 | 2024-04-24 | 2024-04-24 |  | 0 | [5 empty] | 38.16% | 100% | 85.56% | -14.44%
732 | Piling (Cutting only) |  | 7 | 7 | 2023-12-13 | 2023-12-19 | 2024-01-12 | 2024-01-12 | 2024-01-18 | 2024-01-18 |  | 0 | [5 empty] | 0.7423% | 100% | 100% | 0%
733 | Cutting off Pile to GL |  | 7 | 7 | 2023-12-13 | 2023-12-19 | 2024-01-12 | 2024-01-12 | 2024-01-18 | 2024-01-18 | 100 | 0 | 0 | 100 | % | 100 |  | 100% | 100% | 100% | 0%
734 | Completion of Piling |  | 0 | 1 | 2023-12-19 | 2023-12-19 | 2024-01-18 | 2024-01-18 | 2024-01-18 | 2024-01-18 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
735 | Substructure |  | 936 | 71 | 2023-12-20 | 2024-02-28 | 2024-01-19 | 2024-01-19 | 2024-04-24 | 2024-04-24 |  | 0 | [5 empty] | 99.26% | 100% | 85.45% | -14.55%
736 | Structure |  | 936 | 71 | 2023-12-20 | 2024-02-28 | 2024-01-19 | 2024-01-19 | 2024-04-24 | 2024-04-24 |  | 0 | [5 empty] | 100% | 100% | 85.45% | -14.55%
737 | Pile Cap |  | 365 | 60 | 2023-12-20 | 2024-02-17 | 2024-01-19 | 2024-01-19 | 2024-04-24 | 2024-04-24 |  | 0 | [5 empty] | 39% | 100% | 89.47% | -10.53%
738 | Excavation |  | 41 | 41 | 2023-12-20 | 2024-01-29 | 2024-01-19 | 2024-01-19 | 2024-02-22 | 2024-02-22 | 100 | 0 | 0 | 95 | % | 100 |  | 11.23% | 100% | 95% | -5%
739 | Leveling and Compaction |  | 41 | 41 | 2023-12-22 | 2024-01-31 | 2024-02-05 | 2024-02-05 | 2024-03-09 | 2024-03-09 | 100 | 0 | 0 | 95 | % | 100 |  | 11.23% | 100% | 95% | -5%
740 | Lean Concrete Pouring |  | 41 | 41 | 2023-12-23 | 2024-02-01 | 2024-02-06 | 2024-02-06 | 2024-03-11 | 2024-03-11 | 100 | 0 | 0 | 95 | % | 100 |  | 11.23% | 100% | 95% | -5%
741 | Pile Cutting and Treatment |  | 40 | 40 | 2023-12-26 | 2024-02-03 | 2024-02-08 | 2024-02-08 | 2024-03-13 | 2024-03-13 | 100 | 0 | 0 | 95 | % | 100 |  | 10.96% | 100% | 95% | -5%
742 | Reinforcement Bar Fixing |  | 41 | 41 | 2023-12-29 | 2024-02-07 | 2024-03-06 | 2024-03-06 | 2024-04-09 | 2024-04-09 | 100 | 0 | 0 | 85 | % | 100 |  | 11.23% | 100% | 85% | -15%
743 | Formwork Fixing |  | 40 | 40 | 2024-01-02 | 2024-02-10 | 2024-03-07 | 2024-03-07 | 2024-04-12 | 2024-04-12 | 100 | 0 | 0 | 85 | % | 100 |  | 10.96% | 100% | 85% | -15%
744 | Concrete Pouring |  | 41 | 41 | 2024-01-04 | 2024-02-13 | 2024-03-18 | 2024-03-18 | 2024-04-20 | 2024-04-20 | 100 | 0 | 0 | 85 | % | 100 |  | 11.23% | 100% | 85% | -15%
745 | Formwork Dismantling |  | 40 | 40 | 2024-01-08 | 2024-02-16 | 2024-03-19 | 2024-03-19 | 2024-04-24 | 2024-04-24 | 100 | 0 | 0 | 85 | % | 100 |  | 10.96% | 100% | 85% | -15%
746 | Backfill with compaction |  | 40 | 40 | 2024-01-09 | 2024-02-17 | 2024-03-20 | 2024-03-20 | 2024-04-23 | 2024-04-23 | 100 | 0 | 0 | 85 | % | 100 |  | 10.96% | 100% | 85% | -15%
747 | Completion of Pile Cap |  | 0 | 1 | 2024-02-17 | 2024-02-17 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
748 | Stump |  | 244 | 54 | 2024-01-06 | 2024-02-28 | 2024-03-16 | 2024-03-16 | 2024-04-23 | 2024-04-23 |  | 0 | [5 empty] | 26.07% | 100% | 75% | -25%
749 | Reinforcement Bar Fixing |  | 41 | 41 | 2024-01-06 | 2024-02-15 | 2024-03-16 | 2024-03-16 | 2024-04-16 | 2024-04-16 | 100 | 0 | 0 | 75 | % | 100 |  | 16.8% | 100% | 75% | -25%
750 | Formwork Fixing |  | 40 | 40 | 2024-01-09 | 2024-02-17 | 2024-03-20 | 2024-03-20 | 2024-04-16 | 2024-04-16 | 100 | 0 | 0 | 75 | % | 100 |  | 16.39% | 100% | 75% | -25%
751 | Anchor Bolt Fixing |  | 41 | 41 | 2024-01-11 | 2024-02-20 | 2024-03-21 | 2024-03-21 | 2024-04-18 | 2024-04-18 | 100 | 0 | 0 | 75 | % | 100 |  | 16.8% | 100% | 75% | -25%
752 | Concrete Pouring |  | 40 | 40 | 2024-01-15 | 2024-02-23 | 2024-03-22 | 2024-03-22 | 2024-04-20 | 2024-04-20 | 100 | 0 | 0 | 75 | % | 100 |  | 16.39% | 100% | 75% | -25%
753 | Formwork Dismantling |  | 41 | 41 | 2024-01-18 | 2024-02-27 | 2024-03-26 | 2024-03-26 | 2024-04-22 | 2024-04-22 | 100 | 0 | 0 | 75 | % | 100 |  | 16.8% | 100% | 75% | -25%
754 | Backfill with compaction |  | 41 | 41 | 2024-01-19 | 2024-02-28 | 2024-03-27 | 2024-03-27 | 2024-04-23 | 2024-04-23 | 100 | 0 | 0 | 75 | % | 100 |  | 16.8% | 100% | 75% | -25%
755 | Completion of Stump |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-04-23 | 2024-04-23 | 2024-04-23 | 2024-04-23 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
756 | Ground Beam |  | 327 | 58 | 2023-12-20 | 2024-02-15 | 2024-02-05 | 2024-02-05 | 2024-04-24 | 2024-04-24 |  | 0 | [5 empty] | 34.94% | 100% | 88.76% | -11.24%
757 | Excavation |  | 41 | 41 | 2023-12-20 | 2024-01-29 | 2024-02-05 | 2024-02-05 | 2024-03-09 | 2024-03-09 | 100 | 0 | 0 | 95 | % | 100 |  | 12.54% | 100% | 95% | -5%
758 | Leveling and Compaction |  | 41 | 41 | 2023-12-22 | 2024-01-31 | 2024-02-08 | 2024-02-08 | 2024-03-13 | 2024-03-13 | 100 | 0 | 0 | 95 | % | 100 |  | 12.54% | 100% | 95% | -5%
759 | Lean Concrete Pouring |  | 41 | 41 | 2023-12-23 | 2024-02-01 | 2024-03-09 | 2024-03-09 | 2024-04-12 | 2024-04-12 | 100 | 0 | 0 | 95 | % | 100 |  | 12.54% | 100% | 95% | -5%
760 | Reinforcement Bar Fixing |  | 41 | 41 | 2023-12-27 | 2024-02-05 | 2024-03-12 | 2024-03-12 | 2024-04-16 | 2024-04-16 | 100 | 0 | 0 | 85 | % | 100 |  | 12.54% | 100% | 85% | -15%
761 | Formwork Fixing |  | 41 | 41 | 2023-12-30 | 2024-02-08 | 2024-03-13 | 2024-03-13 | 2024-04-18 | 2024-04-18 | 100 | 0 | 0 | 85 | % | 100 |  | 12.54% | 100% | 85% | -15%
762 | Concrete Pouring |  | 40 | 40 | 2024-01-02 | 2024-02-10 | 2024-03-18 | 2024-03-18 | 2024-04-20 | 2024-04-20 | 100 | 0 | 0 | 85 | % | 100 |  | 12.23% | 100% | 85% | -15%
763 | Formwork Dismantling |  | 41 | 41 | 2024-01-05 | 2024-02-14 | 2024-03-19 | 2024-03-19 | 2024-04-24 | 2024-04-24 | 100 | 0 | 0 | 85 | % | 100 |  | 12.54% | 100% | 85% | -15%
764 | Backfill with compaction |  | 41 | 41 | 2024-01-06 | 2024-02-15 | 2024-03-20 | 2024-03-20 | 2024-04-23 | 2024-04-23 | 100 | 0 | 0 | 85 | % | 100 |  | 12.54% | 100% | 85% | -15%
765 | Completion of Ground Beam |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
766 | Completion of Structure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
767 | Completion of Substructure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
768 | Completion of Unit 250 - Pipe Rack Within Facility |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
769 | Unit 310 - City Water Tank |  | 277 | 78 | 2023-12-13 | 2024-02-28 | 2023-12-13 | 2023-12-13 | 2024-04-26 | 2024-04-26 |  | 0 | [5 empty] | 11.21% | 100% | 40.25% | -59.75%
770 | Piling (Cutting only) |  | 7 | 7 | 2023-12-13 | 2023-12-19 | 2023-12-13 | 2023-12-13 | 2023-12-19 | 2023-12-19 |  | 0 | [5 empty] | 2.527% | 100% | 100% | 0%
771 | Cutting off Pile to GL |  | 7 | 7 | 2023-12-13 | 2023-12-19 | 2023-12-13 | 2023-12-13 | 2023-12-19 | 2023-12-19 | 100 | 0 | 0 | 100 | % | 100 |  | 100% | 100% | 100% | 0%
772 | Completion of Piling |  | 0 | 1 | 2023-12-19 | 2023-12-19 | 2023-12-19 | 2023-12-19 | 2023-12-19 | 2023-12-19 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
773 | Substructure |  | 270 | 71 | 2023-12-20 | 2024-02-28 | 2024-01-24 | 2024-01-24 | 2024-04-26 | 2024-04-26 |  | 0 | [5 empty] | 97.47% | 100% | 38.7% | -61.3%
774 | Structure |  | 157 | 55 | 2023-12-20 | 2024-02-12 | 2024-01-24 | 2024-01-24 | 2024-03-27 | 2024-03-27 |  | 0 | [5 empty] | 58.15% | 100% | 17.2% | -82.8%
775 | Pile Cap |  | 62 | 27 | 2023-12-20 | 2024-01-15 | 2024-01-24 | 2024-01-24 | 2024-03-08 | 2024-03-08 |  | 0 | [5 empty] | 39.49% | 100% | 22.58% | -77.42%
776 | Excavation |  | 7 | 7 | 2023-12-20 | 2023-12-26 | 2024-01-24 | 2024-01-24 | 2024-03-05 | 2024-03-05 | 100 | 0 | 0 | 100 | % | 100 |  | 11.29% | 100% | 100% | 0%
777 | Leveling and Compaction |  | 7 | 7 | 2023-12-22 | 2023-12-28 | 2024-01-25 | 2024-01-25 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 11.29% | 100% | 100% | 0%
778 | Lean Concrete Pouring |  | 7 | 7 | 2023-12-23 | 2023-12-29 | 2024-01-26 | 2024-01-26 | 2024-02-01 | 2024-02-01 | 100 | 0 | 0 |  | % | 100 |  | 11.29% | 100% | 0% | -100%
779 | Pile Cutting and Treatment |  | 7 | 7 | 2023-12-26 | 2024-01-01 | 2024-01-29 | 2024-01-29 | 2024-02-03 | 2024-02-03 | 100 | 0 | 0 |  | % | 100 |  | 11.29% | 100% | 0% | -100%
780 | Reinforcement Bar Fixing |  | 7 | 7 | 2023-12-29 | 2024-01-04 | 2024-02-01 | 2024-02-01 | 2024-02-07 | 2024-02-07 | 100 | 0 | 0 |  | % | 100 |  | 11.29% | 100% | 0% | -100%
781 | Formwork Fixing |  | 7 | 7 | 2024-01-02 | 2024-01-08 | 2024-02-05 | 2024-02-05 | 2024-02-10 | 2024-02-10 | 100 | 0 | 0 |  | % | 100 |  | 11.29% | 100% | 0% | -100%
782 | Concrete Pouring |  | 7 | 7 | 2024-01-04 | 2024-01-10 | 2024-02-07 | 2024-02-07 | 2024-02-13 | 2024-02-13 | 100 | 0 | 0 |  | % | 100 |  | 11.29% | 100% | 0% | -100%
783 | Formwork Dismantling |  | 6 | 6 | 2024-01-08 | 2024-01-13 | 2024-02-10 | 2024-02-10 | 2024-02-16 | 2024-02-16 | 100 | 0 | 0 |  | % | 100 |  | 9.677% | 100% | 0% | -100%
784 | Backfill with compaction |  | 7 | 7 | 2024-01-09 | 2024-01-15 | 2024-02-12 | 2024-02-12 | 2024-02-17 | 2024-02-17 | 100 | 0 | 0 |  | % | 100 |  | 11.29% | 100% | 0% | -100%
785 | Completion of Pile Cap |  | 0 | 1 | 2024-01-15 | 2024-01-15 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
786 | Stump |  | 41 | 20 | 2024-01-06 | 2024-01-25 | 2024-02-09 | 2024-02-09 | 2024-02-28 | 2024-02-28 |  | 0 | [5 empty] | 26.11% | 100% | 0% | -100%
787 | Reinforcement Bar Fixing |  | 7 | 7 | 2024-01-06 | 2024-01-12 | 2024-02-09 | 2024-02-09 | 2024-02-15 | 2024-02-15 | 100 | 0 | 0 |  | % | 100 |  | 17.07% | 100% | 0% | -100%
788 | Formwork Fixing |  | 7 | 7 | 2024-01-09 | 2024-01-15 | 2024-02-12 | 2024-02-12 | 2024-02-17 | 2024-02-17 | 100 | 0 | 0 |  | % | 100 |  | 17.07% | 100% | 0% | -100%
789 | Anchor Bolt Fixing |  | 7 | 7 | 2024-01-11 | 2024-01-17 | 2024-02-14 | 2024-02-14 | 2024-02-20 | 2024-02-20 | 100 | 0 | 0 |  | % | 100 |  | 17.07% | 100% | 0% | -100%
790 | Concrete Pouring |  | 6 | 6 | 2024-01-15 | 2024-01-20 | 2024-02-17 | 2024-02-17 | 2024-02-23 | 2024-02-23 | 100 | 0 | 0 |  | % | 100 |  | 14.63% | 100% | 0% | -100%
791 | Formwork Dismantling |  | 7 | 7 | 2024-01-18 | 2024-01-24 | 2024-02-21 | 2024-02-21 | 2024-02-27 | 2024-02-27 | 100 | 0 | 0 |  | % | 100 |  | 17.07% | 100% | 0% | -100%
792 | Backfill with compaction |  | 7 | 7 | 2024-01-19 | 2024-01-25 | 2024-02-22 | 2024-02-22 | 2024-02-28 | 2024-02-28 | 100 | 0 | 0 |  | % | 100 |  | 17.07% | 100% | 0% | -100%
793 | Completion of Stump |  | 0 | 1 | 2024-01-25 | 2024-01-25 | 2024-02-28 | 2024-02-28 | 2024-02-28 | 2024-02-28 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
794 | Ground Beam |  | 54 | 25 | 2024-01-19 | 2024-02-12 | 2024-03-02 | 2024-03-02 | 2024-03-27 | 2024-03-27 |  | 0 | [5 empty] | 34.39% | 100% | 24.07% | -75.93%
795 | Excavation |  | 7 | 7 | 2024-01-19 | 2024-01-25 | 2024-03-02 | 2024-03-02 | 2024-03-07 | 2024-03-07 | 100 | 0 | 0 | 100 | % | 100 |  | 12.96% | 100% | 100% | 0%
796 | Leveling and Compaction |  | 6 | 6 | 2024-01-22 | 2024-01-27 | 2024-03-06 | 2024-03-06 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 11.11% | 100% | 100% | 0%
797 | Lean Concrete Pouring |  | 7 | 7 | 2024-01-23 | 2024-01-29 | 2024-03-07 | 2024-03-07 | 2024-03-13 | 2024-03-13 | 100 | 0 | 0 |  | % | 100 |  | 12.96% | 100% | 0% | -100%
798 | Reinforcement Bar Fixing |  | 7 | 7 | 2024-01-26 | 2024-02-01 | 2024-03-11 | 2024-03-11 | 2024-03-16 | 2024-03-16 | 100 | 0 | 0 |  | % | 100 |  | 12.96% | 100% | 0% | -100%
799 | Formwork Fixing |  | 7 | 7 | 2024-01-30 | 2024-02-05 | 2024-03-14 | 2024-03-14 | 2024-03-20 | 2024-03-20 | 100 | 0 | 0 |  | % | 100 |  | 12.96% | 100% | 0% | -100%
800 | Concrete Pouring |  | 7 | 7 | 2024-02-01 | 2024-02-07 | 2024-03-16 | 2024-03-16 | 2024-03-22 | 2024-03-22 | 100 | 0 | 0 |  | % | 100 |  | 12.96% | 100% | 0% | -100%
801 | Formwork Dismantling |  | 6 | 6 | 2024-02-05 | 2024-02-10 | 2024-03-20 | 2024-03-20 | 2024-03-26 | 2024-03-26 | 100 | 0 | 0 |  | % | 100 |  | 11.11% | 100% | 0% | -100%
802 | Backfill with compaction |  | 7 | 7 | 2024-02-06 | 2024-02-12 | 2024-03-21 | 2024-03-21 | 2024-03-27 | 2024-03-27 | 100 | 0 | 0 |  | % | 100 |  | 12.96% | 100% | 0% | -100%
803 | Completion of Ground Beam |  | 0 | 1 | 2024-02-12 | 2024-02-12 | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2024-03-27 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
804 | Completion of Structure |  | 0 | 1 | 2024-02-12 | 2024-02-12 | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2024-03-27 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
805 | Tank / Equipment and Pump Foundation |  | 113 | 51 | 2024-01-09 | 2024-02-28 | 2024-01-28 | 2024-01-28 | 2024-04-26 | 2024-04-26 |  | 0 | [5 empty] | 41.85% | 100% | 68.58% | -31.42%
806 | City Water Tank T3101 |  | 73 | 51 | 2024-01-09 | 2024-02-28 | 2024-01-28 | 2024-01-28 | 2024-04-26 | 2024-04-26 |  | 0 | [5 empty] | 64.6% | 100% | 100% | 0%
807 | Excavation |  | 10 | 10 | 2024-01-09 | 2024-01-18 | 2024-01-28 | 2024-01-28 | 2024-01-29 | 2024-01-29 | 100 | 0 | 0 | 100 | % | 100 |  | 13.7% | 100% | 100% | 0%
808 | Leveling and Compaction |  | 10 | 10 | 2024-01-09 | 2024-01-18 | 2024-01-29 | 2024-01-29 | 2024-01-30 | 2024-01-30 | 100 | 0 | 0 | 100 | % | 100 |  | 13.7% | 100% | 100% | 0%
809 | Lean Concrete Pouring |  | 11 | 11 | 2024-01-12 | 2024-01-22 | 2024-01-30 | 2024-01-30 | 2024-01-31 | 2024-01-31 | 100 | 0 | 0 | 100 | % | 100 |  | 15.07% | 100% | 100% | 0%
810 | Pile Cutting and Treatment |  | 7 | 7 | 2024-01-18 | 2024-01-24 | 2024-02-24 | 2024-02-24 | 2024-02-26 | 2024-02-26 | 100 | 0 | 0 | 100 | % | 100 |  | 9.589% | 100% | 100% | 0%
811 | Reinforcement Bar Fixing |  | 13 | 13 | 2024-01-22 | 2024-02-03 | 2024-02-29 | 2024-02-29 | 2024-03-26 | 2024-03-26 | 100 | 0 | 0 | 100 | % | 100 |  | 17.81% | 100% | 100% | 0%
812 | Formwork Fixing |  | 7 | 7 | 2024-02-01 | 2024-02-07 | 2024-03-26 | 2024-03-26 | 2024-03-27 | 2024-03-27 | 100 | 0 | 0 | 100 | % | 100 |  | 9.589% | 100% | 100% | 0%
813 | Anchor Bolt / Inserted Plate Fixing |  | 3 | 3 | 2024-02-08 | 2024-02-10 | 2024-04-22 | 2024-04-22 | 2024-04-23 | 2024-04-23 | 100 | 0 | 0 | 100 | % | 100 |  | 4.11% | 100% | 100% | 0%
814 | Concrete Pouring |  | 1 | 1 | 2024-02-12 | 2024-02-12 | 2024-04-23 | 2024-04-23 | 2024-04-24 | 2024-04-24 | 100 | 0 | 0 | 100 | % | 100 |  | 1.37% | 100% | 100% | 0%
815 | Formwork Dismantling |  | 4 | 4 | 2024-02-16 | 2024-02-19 | 2024-04-24 | 2024-04-24 | 2024-04-25 | 2024-04-25 | 100 | 0 | 0 | 100 | % | 100 |  | 5.479% | 100% | 100% | 0%
816 | Backfill with compaction |  | 7 | 7 | 2024-02-22 | 2024-02-28 | 2024-04-25 | 2024-04-25 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 | 100 | % | 100 |  | 9.589% | 100% | 100% | 0%
817 | Completion of City Water Tank |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
818 | Surge Transfer Water Tank T3107 |  | 20 | 25 | 2024-01-19 | 2024-02-12 | 2024-03-07 | 2024-03-07 | 2024-03-30 | 2024-03-30 |  | 0 | [5 empty] | 17.7% | 100% | 2.5% | -97.5%
819 | Excavation |  | 2 | 2 | 2024-01-19 | 2024-01-20 | 2024-03-07 | 2024-03-07 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 25 | % | 100 |  | 10% | 100% | 25% | -75%
820 | Leveling and Compaction |  | 2 | 2 | 2024-01-19 | 2024-01-20 | 2024-03-07 | 2024-03-07 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 |  | % | 100 |  | 10% | 100% | 0% | -100%
821 | Lean Concrete Pouring |  | 1 | 1 | 2024-01-22 | 2024-01-22 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 100 | 0 | 0 |  | % | 100 |  | 5% | 100% | 0% | -100%
822 | Pile Cutting and Treatment |  | 2 | 2 | 2024-01-23 | 2024-01-24 | 2024-03-11 | 2024-03-11 | 2024-03-12 | 2024-03-12 | 100 | 0 | 0 |  | % | 100 |  | 10% | 100% | 0% | -100%
823 | Reinforcement Bar Fixing |  | 5 | 5 | 2024-01-25 | 2024-01-29 | 2024-03-13 | 2024-03-13 | 2024-03-16 | 2024-03-16 | 100 | 0 | 0 |  | % | 100 |  | 25% | 100% | 0% | -100%
824 | Formwork Fixing |  | 1 | 1 | 2024-01-30 | 2024-01-30 | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | 100 | 0 | 0 |  | % | 100 |  | 5% | 100% | 0% | -100%
825 | Anchor Bolt / Inserted Plate Fixing |  | 2 | 2 | 2024-01-31 | 2024-02-01 | 2024-03-19 | 2024-03-19 | 2024-03-20 | 2024-03-20 | 100 | 0 | 0 |  | % | 100 |  | 10% | 100% | 0% | -100%
826 | Concrete Pouring |  | 1 | 1 | 2024-02-02 | 2024-02-02 | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2024-03-21 | 100 | 0 | 0 |  | % | 100 |  | 5% | 100% | 0% | -100%
827 | Formwork Dismantling |  | 1 | 1 | 2024-02-07 | 2024-02-07 | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-26 | 100 | 0 | 0 |  | % | 100 |  | 5% | 100% | 0% | -100%
828 | Backfill with compaction |  | 3 | 3 | 2024-02-10 | 2024-02-12 | 2024-03-29 | 2024-03-29 | 2024-03-30 | 2024-03-30 | 100 | 0 | 0 |  | % | 100 |  | 15% | 100% | 0% | -100%
829 | Completion of Surge Transfer Water Tank |  | 0 | 1 | 2024-02-12 | 2024-02-12 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
830 | City Water Tank Pump Plinth |  | 20 | 25 | 2024-01-19 | 2024-02-12 | 2024-03-02 | 2024-03-02 | 2024-03-30 | 2024-03-30 |  | 0 | [5 empty] | 17.7% | 100% | 20% | -80%
831 | Excavation |  | 2 | 2 | 2024-01-19 | 2024-01-20 | 2024-03-02 | 2024-03-02 | 2024-03-06 | 2024-03-06 | 100 | 0 | 0 | 100 | % | 100 |  | 10% | 100% | 100% | 0%
832 | Leveling and Compaction |  | 2 | 2 | 2024-01-19 | 2024-01-20 | 2024-03-06 | 2024-03-06 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 10% | 100% | 100% | 0%
833 | Lean Concrete Pouring |  | 1 | 1 | 2024-01-22 | 2024-01-22 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 100 | 0 | 0 |  | % | 100 |  | 5% | 100% | 0% | -100%
834 | Pile Cutting and Treatment |  | 2 | 2 | 2024-01-23 | 2024-01-24 | 2024-03-11 | 2024-03-11 | 2024-03-12 | 2024-03-12 | 100 | 0 | 0 |  | % | 100 |  | 10% | 100% | 0% | -100%
835 | Reinforcement Bar Fixing |  | 5 | 5 | 2024-01-25 | 2024-01-29 | 2024-03-13 | 2024-03-13 | 2024-03-16 | 2024-03-16 | 100 | 0 | 0 |  | % | 100 |  | 25% | 100% | 0% | -100%
836 | Formwork Fixing |  | 1 | 1 | 2024-01-30 | 2024-01-30 | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | 100 | 0 | 0 |  | % | 100 |  | 5% | 100% | 0% | -100%
837 | Anchor Bolt / Inserted Plate Fixing |  | 2 | 2 | 2024-01-31 | 2024-02-01 | 2024-03-19 | 2024-03-19 | 2024-03-20 | 2024-03-20 | 100 | 0 | 0 |  | % | 100 |  | 10% | 100% | 0% | -100%
838 | Concrete Pouring |  | 1 | 1 | 2024-02-02 | 2024-02-02 | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2024-03-21 | 100 | 0 | 0 |  | % | 100 |  | 5% | 100% | 0% | -100%
839 | Formwork Dismantling |  | 1 | 1 | 2024-02-07 | 2024-02-07 | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-26 | 100 | 0 | 0 |  | % | 100 |  | 5% | 100% | 0% | -100%
840 | Backfill with compaction |  | 3 | 3 | 2024-02-10 | 2024-02-12 | 2024-03-29 | 2024-03-29 | 2024-03-30 | 2024-03-30 | 100 | 0 | 0 |  | % | 100 |  | 15% | 100% | 0% | -100%
841 | Completion of Surge Transfer Water Tank |  | 0 | 1 | 2024-02-12 | 2024-02-12 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
842 | Completion of Tank / Equipment and Pump Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
843 | Completion of Substructure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
844 | Completion of Unit 310 - City Water Tank |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
845 | Unit 310 - Water Treatment |  | 201 | 71 | 2023-12-20 | 2024-02-28 | 2023-12-18 | 2023-12-18 | 2024-05-08 | 2024-05-08 |  | 0 | [5 empty] | 8.134% | 100% | 92.54% | -7.463%
846 | Piling (Cutting only) |  | 7 | 7 | 2023-12-20 | 2023-12-26 | 2023-12-18 | 2023-12-18 | 2023-12-23 | 2023-12-23 |  | 0 | [5 empty] | 3.483% | 100% | 100% | 0%
847 | Cutting off Pile to GL |  | 7 | 7 | 2023-12-20 | 2023-12-26 | 2023-12-18 | 2023-12-18 | 2023-12-23 | 2023-12-23 | 100 | 0 | 0 | 100 | % | 100 |  | 100% | 100% | 100% | 0%
848 | Completion of Piling |  | 0 | 1 | 2023-12-26 | 2023-12-26 | 2023-12-23 | 2023-12-23 | 2023-12-23 | 2023-12-23 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
849 | Substructure |  | 194 | 64 | 2023-12-27 | 2024-02-28 | 2023-12-28 | 2023-12-28 | 2024-05-08 | 2024-05-08 |  | 0 | [5 empty] | 96.52% | 100% | 92.27% | -7.732%
850 | Structure |  | 124 | 55 | 2023-12-27 | 2024-02-19 | 2023-12-28 | 2023-12-28 | 2024-01-30 | 2024-01-30 |  | 0 | [5 empty] | 63.92% | 100% | 100% | 0%
851 | Pile Raft |  | 117 | 27 | 2023-12-27 | 2024-01-22 | 2023-12-28 | 2023-12-28 | 2024-01-30 | 2024-01-30 |  | 0 | [5 empty] | 94.35% | 100% | 100% | 0%
852 | Excavation |  | 13 | 13 | 2023-12-27 | 2024-01-08 | 2023-12-28 | 2023-12-28 | 2024-01-04 | 2024-01-04 | 100 | 0 | 0 | 100 | % | 100 |  | 11.11% | 100% | 100% | 0%
853 | Leveling and Compaction |  | 13 | 13 | 2023-12-29 | 2024-01-10 | 2023-12-29 | 2023-12-29 | 2024-01-05 | 2024-01-05 | 100 | 0 | 0 | 100 | % | 100 |  | 11.11% | 100% | 100% | 0%
854 | Lean Concrete Pouring |  | 13 | 13 | 2023-12-30 | 2024-01-11 | 2024-01-01 | 2024-01-01 | 2024-01-03 | 2024-01-03 | 100 | 0 | 0 | 100 | % | 100 |  | 11.11% | 100% | 100% | 0%
855 | Pile Cutting and Treatment |  | 13 | 13 | 2024-01-02 | 2024-01-14 | 2024-01-03 | 2024-01-03 | 2024-01-05 | 2024-01-05 | 100 | 0 | 0 | 100 | % | 100 |  | 11.11% | 100% | 100% | 0%
856 | Reinforcement Bar Fixing |  | 13 | 13 | 2024-01-05 | 2024-01-17 | 2024-01-18 | 2024-01-18 | 2024-01-22 | 2024-01-22 | 100 | 0 | 0 | 100 | % | 100 |  | 11.11% | 100% | 100% | 0%
857 | Formwork Fixing |  | 13 | 13 | 2024-01-09 | 2024-01-21 | 2024-01-21 | 2024-01-21 | 2024-01-23 | 2024-01-23 | 100 | 0 | 0 | 100 | % | 100 |  | 11.11% | 100% | 100% | 0%
858 | Concrete Pouring |  | 13 | 13 | 2024-01-11 | 2024-01-23 | 2024-01-23 | 2024-01-23 | 2024-01-24 | 2024-01-24 | 100 | 0 | 0 | 100 | % | 100 |  | 11.11% | 100% | 100% | 0%
859 | Formwork Dismantling |  | 12 | 12 | 2024-01-15 | 2024-01-26 | 2024-01-26 | 2024-01-26 | 2024-01-26 | 2024-01-26 | 100 | 0 | 0 | 100 | % | 100 |  | 10.26% | 100% | 100% | 0%
860 | Backfill with compaction |  | 14 | 14 | 2024-01-16 | 2024-01-29 | 2024-01-29 | 2024-01-29 | 2024-01-30 | 2024-01-30 | 100 | 0 | 0 | 100 | % | 100 |  | 11.97% | 100% | 100% | 0%
861 | Completion of Pile Cap |  | 0 | 1 | 2024-01-28 | 2024-01-28 | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2024-01-30 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
862 | Column | Reinforcement Bar only (Starter bar) | 7 | 20 | 2024-01-13 | 2024-02-01 | 2024-01-22 | 2024-01-22 | 2024-01-22 | 2024-01-22 |  | 0 | [5 empty] | 5.645% | 100% | 100% | 0%
863 | Reinforcement Bar Fixing |  | 7 | 7 | 2024-01-13 | 2024-01-19 | 2024-01-22 | 2024-01-22 | 2024-01-22 | 2024-01-22 | 100 | 0 | 0 | 100 | % | 100 |  | 100% | 100% | 100% | 0%
864 | Completion of Stump |  | 0 | 1 | 2024-02-01 | 2024-02-01 | 2024-01-22 | 2024-01-22 | 2024-01-22 | 2024-01-22 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
865 | Completion of Structure |  | 0 | 1 | 2024-02-19 | 2024-02-19 | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2024-01-30 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
866 | Tank / Equipment and Pump Foundation |  | 70 | 44 | 2024-01-16 | 2024-02-28 | 2024-01-29 | 2024-01-29 | 2024-05-08 | 2024-05-08 |  | 0 | [5 empty] | 36.08% | 100% | 78.57% | -21.43%
867 | Tank T3104 |  | 44 | 44 | 2024-01-16 | 2024-02-28 | 2024-01-30 | 2024-01-30 | 2024-05-08 | 2024-05-08 |  | 0 | [5 empty] | 62.86% | 100% | 77.27% | -22.73%
868 | Excavation |  | 7 | 7 | 2024-01-16 | 2024-01-22 | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2024-01-30 | 100 | 0 | 0 | 100 | % | 100 |  | 15.91% | 100% | 100% | 0%
869 | Leveling and Compaction |  | 4 | 4 | 2024-01-20 | 2024-01-23 | 2024-01-30 | 2024-01-30 | 2024-01-31 | 2024-01-31 | 100 | 0 | 0 | 100 | % | 100 |  | 9.091% | 100% | 100% | 0%
870 | Lean Concrete Pouring |  | 2 | 2 | 2024-01-24 | 2024-01-25 | 2024-01-31 | 2024-01-31 | 2024-02-01 | 2024-02-01 | 100 | 0 | 0 | 100 | % | 100 |  | 4.545% | 100% | 100% | 0%
871 | Base |  | 13 | 13 | 2024-01-26 | 2024-02-07 | 2024-02-20 | 2024-02-20 | 2024-02-27 | 2024-02-27 |  | 0 | [5 empty] | 29.55% | 100% | 100% | 0%
872 | Reinforcement Bar Fixing |  | 8 | 8 | 2024-01-26 | 2024-02-02 | 2024-02-20 | 2024-02-20 | 2024-02-23 | 2024-02-23 | 100 | 0 | 0 | 100 | % | 100 |  | 61.54% | 100% | 100% | 0%
873 | Formwork Fixing |  | 4 | 4 | 2024-02-03 | 2024-02-06 | 2024-02-24 | 2024-02-24 | 2024-02-25 | 2024-02-25 | 100 | 0 | 0 | 100 | % | 100 |  | 30.77% | 100% | 100% | 0%
874 | Concrete Pouring |  | 1 | 1 | 2024-02-07 | 2024-02-07 | 2024-02-27 | 2024-02-27 | 2024-02-27 | 2024-02-27 | 100 | 0 | 0 | 100 | % | 100 |  | 7.692% | 100% | 100% | 0%
875 | Tank Ring |  | 14 | 14 | 2024-02-08 | 2024-02-21 | 2024-02-25 | 2024-02-25 | 2024-05-01 | 2024-05-01 |  | 0 | [5 empty] | 31.82% | 100% | 57.14% | -42.86%
876 | Reinforcement Bar Fixing |  | 8 | 8 | 2024-02-08 | 2024-02-15 | 2024-02-25 | 2024-02-25 | 2024-04-22 | 2024-04-22 | 100 | 0 | 0 | 100 | % | 100 |  | 57.14% | 100% | 100% | 0%
877 | Formwork Fixing |  | 5 | 5 | 2024-02-16 | 2024-02-20 | 2024-04-26 | 2024-04-26 | 2024-04-30 | 2024-04-30 | 100 | 0 | 0 |  | % | 100 |  | 35.71% | 100% | 0% | -100%
878 | Concrete Pouring |  | 1 | 1 | 2024-02-21 | 2024-02-21 | 2024-05-01 | 2024-05-01 | 2024-05-01 | 2024-05-01 | 100 | 0 | 0 |  | % | 100 |  | 7.143% | 100% | 0% | -100%
879 | Formwork Dismantling |  | 1 | 1 | 2024-02-24 | 2024-02-24 | 2024-05-04 | 2024-05-04 | 2024-05-04 | 2024-05-04 | 100 | 0 | 0 |  | % | 100 |  | 2.273% | 100% | 0% | -100%
880 | Backfill with compaction |  | 3 | 3 | 2024-02-26 | 2024-02-28 | 2024-05-06 | 2024-05-06 | 2024-05-08 | 2024-05-08 | 100 | 0 | 0 |  | % | 100 |  | 6.818% | 100% | 0% | -100%
881 | Completion of Tank T3104 |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-05-08 | 2024-05-08 | 2024-05-08 | 2024-05-08 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
882 | Tank T3102 and T3103 |  | 26 | 31 | 2024-01-23 | 2024-02-22 | 2024-01-29 | 2024-01-29 | 2024-05-08 | 2024-05-08 |  | 0 | [5 empty] | 37.14% | 100% | 80.77% | -19.23%
883 | Excavation |  | 3 | 3 | 2024-01-23 | 2024-01-25 | 2024-01-29 | 2024-01-29 | 2024-01-30 | 2024-01-30 | 100 | 0 | 0 | 100 | % | 100 |  | 11.54% | 100% | 100% | 0%
884 | Leveling and Compaction |  | 3 | 3 | 2024-01-23 | 2024-01-25 | 2024-01-31 | 2024-01-31 | 2024-01-31 | 2024-01-31 | 100 | 0 | 0 | 100 | % | 100 |  | 11.54% | 100% | 100% | 0%
885 | Lean Concrete Pouring |  | 2 | 2 | 2024-01-26 | 2024-01-27 | 2024-02-01 | 2024-02-01 | 2024-02-01 | 2024-02-01 | 100 | 0 | 0 | 100 | % | 100 |  | 7.692% | 100% | 100% | 0%
886 | Pile Cutting and Treatment |  | 2 | 2 | 2024-01-29 | 2024-01-30 | 2024-02-16 | 2024-02-16 | 2024-02-17 | 2024-02-17 | 100 | 0 | 0 | 100 | % | 100 |  | 7.692% | 100% | 100% | 0%
887 | Reinforcement Bar Fixing |  | 7 | 7 | 2024-01-31 | 2024-02-06 | 2024-02-20 | 2024-02-20 | 2024-02-23 | 2024-02-23 | 100 | 0 | 0 | 100 | % | 100 |  | 26.92% | 100% | 100% | 0%
888 | Formwork Fixing |  | 2 | 2 | 2024-02-07 | 2024-02-08 | 2024-02-26 | 2024-02-26 | 2024-02-28 | 2024-02-28 | 100 | 0 | 0 | 100 | % | 100 |  | 7.692% | 100% | 100% | 0%
889 | Anchor Bolt / Inserted Plate Fixing |  | 2 | 2 | 2024-02-09 | 2024-02-10 | 2024-02-29 | 2024-02-29 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 | 100 | % | 100 |  | 7.692% | 100% | 100% | 0%
890 | Concrete Pouring |  | 1 | 1 | 2024-02-12 | 2024-02-12 | 2024-04-27 | 2024-04-27 | 2024-04-27 | 2024-04-27 | 100 | 0 | 0 |  | % | 100 |  | 3.846% | 100% | 0% | -100%
891 | Formwork Dismantling |  | 1 | 1 | 2024-02-16 | 2024-02-16 | 2024-05-02 | 2024-05-02 | 2024-05-02 | 2024-05-02 | 100 | 0 | 0 |  | % | 100 |  | 3.846% | 100% | 0% | -100%
892 | Backfill with compaction |  | 3 | 3 | 2024-02-20 | 2024-02-22 | 2024-05-06 | 2024-05-06 | 2024-05-08 | 2024-05-08 | 100 | 0 | 0 |  | % | 100 |  | 11.54% | 100% | 0% | -100%
893 | Completion of Tank T3102 and T3103 |  | 0 | 1 | 2024-02-22 | 2024-02-22 | 2024-05-08 | 2024-05-08 | 2024-05-08 | 2024-05-08 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
894 | Completion of Tank / Equipment and Pump Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-05-08 | 2024-05-08 | 2024-05-08 | 2024-05-08 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
895 | Completion of Substructure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-05-08 | 2024-05-08 | 2024-05-08 | 2024-05-08 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
896 | Completion of Unit 310 - Water Treatment |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-05-08 | 2024-05-08 | 2024-05-08 | 2024-05-08 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
897 | Unit 330 - Cooling Tower |  | 139 | 49 | 2024-01-03 | 2024-02-20 | 2024-01-03 | 2024-01-03 | 2024-04-26 | 2024-04-26 |  | 0 | [5 empty] | 5.625% | 100% | 100% | 0%
898 | Piling (Cutting only) |  | 14 | 14 | 2024-01-03 | 2024-01-16 | 2024-01-03 | 2024-01-03 | 2024-01-16 | 2024-01-16 |  | 0 | [5 empty] | 10.07% | 100% | 100% | 0%
899 | Cutting off Pile to GL |  | 14 | 14 | 2024-01-03 | 2024-01-16 | 2024-01-03 | 2024-01-03 | 2024-01-16 | 2024-01-16 | 100 | 0 | 0 | 100 | % | 100 |  | 100% | 100% | 100% | 0%
900 | Completion of Piling |  | 0 | 1 | 2024-01-16 | 2024-01-16 | 2024-01-16 | 2024-01-16 | 2024-01-16 | 2024-01-16 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
901 | Substructure |  | 125 | 46 | 2024-01-06 | 2024-02-20 | 2024-01-10 | 2024-01-10 | 2024-04-26 | 2024-04-26 |  | 0 | [5 empty] | 89.93% | 100% | 100% | 0%
902 | Pile Raft |  | 125 | 34 | 2024-01-06 | 2024-02-08 | 2024-01-10 | 2024-01-10 | 2024-04-26 | 2024-04-26 |  | 0 | [5 empty] | 100% | 100% | 100% | 0%
903 | Excavation |  | 14 | 14 | 2024-01-06 | 2024-01-19 | 2024-01-10 | 2024-01-10 | 2024-02-05 | 2024-02-05 | 100 | 0 | 0 | 100 | % | 100 |  | 11.2% | 100% | 100% | 0%
904 | Leveling and Compaction |  | 14 | 14 | 2024-01-09 | 2024-01-22 | 2024-01-25 | 2024-01-25 | 2024-02-05 | 2024-02-05 | 100 | 0 | 0 | 100 | % | 100 |  | 11.2% | 100% | 100% | 0%
905 | Lean Concrete Pouring |  | 14 | 14 | 2024-01-10 | 2024-01-23 | 2024-01-26 | 2024-01-26 | 2024-02-06 | 2024-02-06 | 100 | 0 | 0 | 100 | % | 100 |  | 11.2% | 100% | 100% | 0%
906 | Pile Cutting and Treatment |  | 14 | 14 | 2024-01-12 | 2024-01-25 | 2024-01-26 | 2024-01-26 | 2024-02-06 | 2024-02-06 | 100 | 0 | 0 | 100 | % | 100 |  | 11.2% | 100% | 100% | 0%
907 | Reinforcement Bar Fixing |  | 14 | 14 | 2024-01-16 | 2024-01-29 | 2024-02-16 | 2024-02-16 | 2024-04-19 | 2024-04-19 | 100 | 0 | 0 | 100 | % | 100 |  | 11.2% | 100% | 100% | 0%
908 | Formwork Fixing |  | 14 | 14 | 2024-01-19 | 2024-02-01 | 2024-02-19 | 2024-02-19 | 2024-02-23 | 2024-02-23 | 100 | 0 | 0 | 100 | % | 100 |  | 11.2% | 100% | 100% | 0%
909 | Concrete Pouring |  | 13 | 13 | 2024-01-22 | 2024-02-03 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 2024-04-19 | 100 | 0 | 0 | 100 | % | 100 |  | 10.4% | 100% | 100% | 0%
910 | Formwork Dismantling |  | 14 | 14 | 2024-01-25 | 2024-02-07 | 2024-04-22 | 2024-04-22 | 2024-04-25 | 2024-04-25 | 100 | 0 | 0 | 100 | % | 100 |  | 11.2% | 100% | 100% | 0%
911 | Backfill with compaction |  | 14 | 14 | 2024-01-26 | 2024-02-08 | 2024-04-24 | 2024-04-24 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 | 100 | % | 100 |  | 11.2% | 100% | 100% | 0%
912 | Completion of Pile Raft |  | 0 | 1 | 2024-02-08 | 2024-02-08 | 2024-04-25 | 2024-04-25 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
913 | Completion of Substructure |  | 0 | 1 | 2024-02-20 | 2024-02-20 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
914 | Completion of Unit 330 - Cooling Tower |  | 0 | 1 | 2024-02-20 | 2024-02-20 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
915 | Unit 340 - Instrument Air & Plant Air System |  | 189 | 72 | 2023-12-13 | 2024-02-22 | 2023-12-26 | 2023-12-26 | 2024-05-10 | 2024-05-10 |  | 0 | [5 empty] | 7.649% | 100% | 97.35% | -2.646%
916 | Piling (Cutting only) |  | 14 | 14 | 2023-12-13 | 2023-12-26 | 2023-12-26 | 2023-12-26 | 2024-01-08 | 2024-01-08 |  | 0 | [5 empty] | 7.407% | 100% | 100% | 0%
917 | Cutting off Pile to GL |  | 14 | 14 | 2023-12-13 | 2023-12-26 | 2023-12-26 | 2023-12-26 | 2024-01-08 | 2024-01-08 | 100 | 0 | 0 | 100 | % | 100 |  | 100% | 100% | 100% | 0%
918 | Completion of Piling |  | 0 | 1 | 2023-12-26 | 2023-12-26 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
919 | Substructure |  | 175 | 58 | 2023-12-27 | 2024-02-22 | 2024-02-01 | 2024-02-01 | 2024-05-10 | 2024-05-10 |  | 0 | [5 empty] | 92.59% | 100% | 97.14% | -2.857%
920 | Equipment Foundation |  | 175 | 58 | 2023-12-27 | 2024-02-22 | 2024-02-01 | 2024-02-01 | 2024-05-10 | 2024-05-10 |  | 0 | [5 empty] | 100% | 100% | 97.14% | -2.857%
921 | V3401 and V3402 |  | 35 | 38 | 2023-12-27 | 2024-02-02 | 2024-02-06 | 2024-02-06 | 2024-04-26 | 2024-04-26 |  | 0 | [5 empty] | 20% | 100% | 100% | 0%
922 | Excavation |  | 4 | 4 | 2023-12-27 | 2023-12-30 | 2024-02-06 | 2024-02-06 | 2024-02-07 | 2024-02-07 | 100 | 0 | 0 | 100 | % | 100 |  | 11.43% | 100% | 100% | 0%
923 | Leveling and Compaction |  | 4 | 4 | 2023-12-27 | 2023-12-30 | 2024-02-07 | 2024-02-07 | 2024-02-08 | 2024-02-08 | 100 | 0 | 0 | 100 | % | 100 |  | 11.43% | 100% | 100% | 0%
924 | Lean Concrete Pouring |  | 2 | 2 | 2024-01-01 | 2024-01-02 | 2024-02-08 | 2024-02-08 | 2024-02-09 | 2024-02-09 | 100 | 0 | 0 | 100 | % | 100 |  | 5.714% | 100% | 100% | 0%
925 | Pile Cutting and Treatment |  | 3 | 3 | 2024-01-03 | 2024-01-05 | 2024-02-08 | 2024-02-08 | 2024-02-12 | 2024-02-12 | 100 | 0 | 0 | 100 | % | 100 |  | 8.571% | 100% | 100% | 0%
926 | Reinforcement Bar Fixing |  | 10 | 10 | 2024-01-06 | 2024-01-15 | 2024-02-15 | 2024-02-15 | 2024-02-23 | 2024-02-23 | 100 | 0 | 0 | 100 | % | 100 |  | 28.57% | 100% | 100% | 0%
927 | Formwork Fixing |  | 2 | 2 | 2024-01-16 | 2024-01-17 | 2024-02-19 | 2024-02-19 | 2024-02-21 | 2024-02-21 | 100 | 0 | 0 | 100 | % | 100 |  | 5.714% | 100% | 100% | 0%
928 | Anchor Bolt / Inserted Plate Fixing |  | 2 | 2 | 2024-01-18 | 2024-01-19 | 2024-02-28 | 2024-02-28 | 2024-02-29 | 2024-02-29 | 100 | 0 | 0 | 100 | % | 100 |  | 5.714% | 100% | 100% | 0%
929 | Concrete Pouring |  | 4 | 4 | 2024-01-20 | 2024-01-23 | 2024-03-07 | 2024-03-07 | 2024-04-25 | 2024-04-25 | 100 | 0 | 0 | 100 | % | 100 |  | 11.43% | 100% | 100% | 0%
930 | Formwork Dismantling |  | 1 | 1 | 2024-01-27 | 2024-01-27 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 | 100 | % | 100 |  | 2.857% | 100% | 100% | 0%
931 | Backfill with compaction |  | 3 | 3 | 2024-01-31 | 2024-02-02 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 | 100 | % | 100 |  | 8.571% | 100% | 100% | 0%
932 | Completion of V3401 and V3402 |  | 0 | 1 | 2024-02-02 | 2024-02-02 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
933 | K3401 A/B/C |  | 37 | 45 | 2024-01-01 | 2024-02-14 | 2024-02-01 | 2024-02-01 | 2024-05-03 | 2024-05-03 |  | 0 | [5 empty] | 21.14% | 100% | 100% | 0%
934 | Foundation |  | 23 | 22 | 2024-01-01 | 2024-01-22 | 2024-02-01 | 2024-02-01 | 2024-02-21 | 2024-02-21 |  | 0 | [5 empty] | 62.16% | 100% | 100% | 0%
935 | Excavation |  | 3 | 3 | 2024-01-01 | 2024-01-03 | 2024-02-01 | 2024-02-01 | 2024-02-08 | 2024-02-08 | 100 | 0 | 0 | 100 | % | 100 |  | 13.04% | 100% | 100% | 0%
936 | Leveling and Compaction |  | 3 | 3 | 2024-01-01 | 2024-01-03 | 2024-02-02 | 2024-02-02 | 2024-02-08 | 2024-02-08 | 100 | 0 | 0 | 100 | % | 100 |  | 13.04% | 100% | 100% | 0%
937 | Lean Concrete Pouring |  | 2 | 2 | 2024-01-04 | 2024-01-05 | 2024-02-12 | 2024-02-12 | 2024-02-13 | 2024-02-13 | 100 | 0 | 0 | 100 | % | 100 |  | 8.696% | 100% | 100% | 0%
938 | Reinforcement Bar Fixing |  | 8 | 8 | 2024-01-06 | 2024-01-13 | 2024-02-16 | 2024-02-16 | 2024-02-19 | 2024-02-19 | 100 | 0 | 0 | 100 | % | 100 |  | 34.78% | 100% | 100% | 0%
939 | Anchor Bolt / Inserted Plate Fixing |  | 3 | 3 | 2024-01-15 | 2024-01-17 | 2024-02-19 | 2024-02-19 | 2024-02-19 | 2024-02-19 | 100 | 0 | 0 | 100 | % | 100 |  | 13.04% | 100% | 100% | 0%
940 | Formwork Fixing |  | 3 | 3 | 2024-01-18 | 2024-01-20 | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-20 | 100 | 0 | 0 | 100 | % | 100 |  | 13.04% | 100% | 100% | 0%
941 | Concrete Pouring |  | 1 | 1 | 2024-01-22 | 2024-01-22 | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-21 | 100 | 0 | 0 | 100 | % | 100 |  | 4.348% | 100% | 100% | 0%
942 | Plinth |  | 10 | 10 | 2024-01-23 | 2024-02-01 | 2024-02-21 | 2024-02-21 | 2024-05-01 | 2024-05-01 |  | 0 | [5 empty] | 27.03% | 100% | 100% | 0%
943 | Reinforcement Bar Fixing |  | 4 | 4 | 2024-01-23 | 2024-01-26 | 2024-02-21 | 2024-02-21 | 2024-02-29 | 2024-02-29 | 100 | 0 | 0 | 100 | % | 100 |  | 40% | 100% | 100% | 0%
944 | Formwork Fixing |  | 5 | 5 | 2024-01-27 | 2024-01-31 | 2024-04-25 | 2024-04-25 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 | 100 | % | 100 |  | 50% | 100% | 100% | 0%
945 | Concrete Pouring |  | 1 | 1 | 2024-02-01 | 2024-02-01 | 2024-04-29 | 2024-04-29 | 2024-05-01 | 2024-05-01 | 100 | 0 | 0 | 100 | % | 100 |  | 10% | 100% | 100% | 0%
946 | Formwork Dismantling |  | 1 | 1 | 2024-02-10 | 2024-02-10 | 2024-04-30 | 2024-04-30 | 2024-05-02 | 2024-05-02 | 100 | 0 | 0 | 100 | % | 100 |  | 2.703% | 100% | 100% | 0%
947 | Backfill with compaction |  | 3 | 3 | 2024-02-12 | 2024-02-14 | 2024-05-01 | 2024-05-01 | 2024-05-03 | 2024-05-03 | 100 | 0 | 0 | 100 | % | 100 |  | 8.108% | 100% | 100% | 0%
948 | Completion of K3401 A/B/C |  | 0 | 1 | 2024-02-14 | 2024-02-14 | 2024-05-02 | 2024-05-02 | 2024-05-03 | 2024-05-03 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
949 | F3405 A/B/C |  | 73 | 37 | 2024-01-01 | 2024-02-06 | 2024-02-01 | 2024-02-01 | 2024-05-10 | 2024-05-10 |  | 0 | [5 empty] | 41.71% | 100% | 95.21% | -4.795%
950 | Pile Cap and Ground Beam |  | 31 | 23 | 2024-01-01 | 2024-01-23 | 2024-02-01 | 2024-02-01 | 2024-03-08 | 2024-03-08 |  | 0 | [5 empty] | 42.47% | 100% | 100% | 0%
951 | Excavation |  | 3 | 3 | 2024-01-01 | 2024-01-03 | 2024-02-01 | 2024-02-01 | 2024-02-07 | 2024-02-07 | 100 | 0 | 0 | 100 | % | 100 |  | 9.677% | 100% | 100% | 0%
952 | Leveling and Compaction |  | 3 | 3 | 2024-01-03 | 2024-01-05 | 2024-02-02 | 2024-02-02 | 2024-02-08 | 2024-02-08 | 100 | 0 | 0 | 100 | % | 100 |  | 9.677% | 100% | 100% | 0%
953 | Lean Concrete Pouring |  | 3 | 3 | 2024-01-04 | 2024-01-06 | 2024-02-13 | 2024-02-13 | 2024-02-15 | 2024-02-15 | 100 | 0 | 0 | 100 | % | 100 |  | 9.677% | 100% | 100% | 0%
954 | Pile Cutting and Treatment |  | 4 | 4 | 2024-01-06 | 2024-01-09 | 2024-02-14 | 2024-02-14 | 2024-02-15 | 2024-02-15 | 100 | 0 | 0 | 100 | % | 100 |  | 12.9% | 100% | 100% | 0%
955 | Reinforcement Bar Fixing |  | 3 | 3 | 2024-01-10 | 2024-01-12 | 2024-02-16 | 2024-02-16 | 2024-02-24 | 2024-02-24 | 100 | 0 | 0 | 100 | % | 100 |  | 9.677% | 100% | 100% | 0%
956 | Formwork Fixing |  | 4 | 4 | 2024-01-13 | 2024-01-16 | 2024-02-19 | 2024-02-19 | 2024-02-25 | 2024-02-25 | 100 | 0 | 0 | 100 | % | 100 |  | 12.9% | 100% | 100% | 0%
957 | Concrete Pouring |  | 3 | 3 | 2024-01-16 | 2024-01-18 | 2024-03-01 | 2024-03-01 | 2024-03-05 | 2024-03-05 | 100 | 0 | 0 | 100 | % | 100 |  | 9.677% | 100% | 100% | 0%
958 | Formwork Dismantling |  | 4 | 4 | 2024-01-19 | 2024-01-22 | 2024-03-06 | 2024-03-06 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 12.9% | 100% | 100% | 0%
959 | Backfill with compaction |  | 4 | 4 | 2024-01-20 | 2024-01-23 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 12.9% | 100% | 100% | 0%
960 | Completion of Pile Cap |  | 0 | 1 | 2024-01-23 | 2024-01-23 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
961 | Stump |  | 42 | 20 | 2024-01-18 | 2024-02-06 | 2024-02-26 | 2024-02-26 | 2024-05-10 | 2024-05-10 |  | 0 | [5 empty] | 57.53% | 100% | 91.67% | -8.333%
962 | Reinforcement Bar Fixing |  | 7 | 7 | 2024-01-18 | 2024-01-24 | 2024-02-26 | 2024-02-26 | 2024-03-07 | 2024-03-07 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
963 | Formwork Fixing |  | 7 | 7 | 2024-01-20 | 2024-01-26 | 2024-04-24 | 2024-04-24 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
964 | Anchor Bolt Fixing |  | 7 | 7 | 2024-01-23 | 2024-01-29 | 2024-04-26 | 2024-04-26 | 2024-05-02 | 2024-05-02 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
965 | Concrete Pouring |  | 7 | 7 | 2024-01-26 | 2024-02-01 | 2024-04-30 | 2024-04-30 | 2024-05-06 | 2024-05-06 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
966 | Formwork Dismantling |  | 7 | 7 | 2024-01-30 | 2024-02-05 | 2024-05-03 | 2024-05-03 | 2024-05-09 | 2024-05-09 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
967 | Backfill with compaction |  | 7 | 7 | 2024-01-31 | 2024-02-06 | 2024-05-04 | 2024-05-04 | 2024-05-10 | 2024-05-10 | 100 | 0 | 0 | 50 | % | 100 |  | 16.67% | 100% | 50% | -50%
968 | Completion of Stump |  | 0 | 1 | 2024-02-06 | 2024-02-06 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
969 | Completion of F3405 A/B/C |  | 0 | 1 | 2024-02-06 | 2024-02-06 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
970 | D3401 AB and D3402 AB |  | 30 | 23 | 2024-01-31 | 2024-02-22 | 2024-02-06 | 2024-02-06 | 2024-04-26 | 2024-04-26 |  | 0 | [5 empty] | 17.14% | 100% | 95% | -5%
971 | Pile Cap and Ground Beam |  | 30 | 23 | 2024-01-31 | 2024-02-22 | 2024-02-06 | 2024-02-06 | 2024-04-26 | 2024-04-26 |  | 0 | [5 empty] | 100% | 100% | 95% | -5%
972 | Excavation |  | 3 | 3 | 2024-01-31 | 2024-02-02 | 2024-02-06 | 2024-02-06 | 2024-02-08 | 2024-02-08 | 100 | 0 | 0 | 100 | % | 100 |  | 10% | 100% | 100% | 0%
973 | Leveling and Compaction |  | 4 | 4 | 2024-02-02 | 2024-02-05 | 2024-02-07 | 2024-02-07 | 2024-02-09 | 2024-02-09 | 100 | 0 | 0 | 100 | % | 100 |  | 13.33% | 100% | 100% | 0%
974 | Lean Concrete Pouring |  | 4 | 4 | 2024-02-03 | 2024-02-06 | 2024-02-13 | 2024-02-13 | 2024-02-14 | 2024-02-14 | 100 | 0 | 0 | 100 | % | 100 |  | 13.33% | 100% | 100% | 0%
975 | Pile Cutting and Treatment |  | 3 | 3 | 2024-02-06 | 2024-02-08 | 2024-02-14 | 2024-02-14 | 2024-02-15 | 2024-02-15 | 100 | 0 | 0 | 100 | % | 100 |  | 10% | 100% | 100% | 0%
976 | Reinforcement Bar Fixing |  | 4 | 4 | 2024-02-09 | 2024-02-12 | 2024-02-16 | 2024-02-16 | 2024-04-15 | 2024-04-15 | 100 | 0 | 0 | 100 | % | 100 |  | 13.33% | 100% | 100% | 0%
977 | Formwork Fixing |  | 3 | 3 | 2024-02-13 | 2024-02-15 | 2024-02-27 | 2024-02-27 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 | 100 | % | 100 |  | 10% | 100% | 100% | 0%
978 | Concrete Pouring |  | 3 | 3 | 2024-02-15 | 2024-02-17 | 2024-02-29 | 2024-02-29 | 2024-03-02 | 2024-03-02 | 100 | 0 | 0 | 100 | % | 100 |  | 10% | 100% | 100% | 0%
979 | Formwork Dismantling |  | 3 | 3 | 2024-02-19 | 2024-02-21 | 2024-03-04 | 2024-03-04 | 2024-03-06 | 2024-03-06 | 100 | 0 | 0 | 100 | % | 100 |  | 10% | 100% | 100% | 0%
980 | Backfill with compaction |  | 3 | 3 | 2024-02-20 | 2024-02-22 | 2024-03-05 | 2024-03-05 | 2024-03-07 | 2024-03-07 | 100 | 0 | 0 | 50 | % | 100 |  | 10% | 100% | 50% | -50%
981 | Completion of Pile Cap |  | 0 | 1 | 2024-02-22 | 2024-02-22 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
982 | Completion of D3401 AB and D3402 AB |  | 0 | 1 | 2024-02-22 | 2024-02-22 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
983 | Completion of Compressor / Equipment and Pump Foundation |  | 0 | 1 | 2024-02-22 | 2024-02-22 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
984 | Completion of Substructure |  | 0 | 1 | 2024-02-22 | 2024-02-22 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
985 | Completion of Unit 340 - Instrument Air & Plant Air System |  | 0 | 1 | 2024-02-22 | 2024-02-22 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
986 | Unit 350 - Nitrogen System |  | 431 | 78 | 2023-12-13 | 2024-02-28 | 2023-12-26 | 2023-12-26 | 2024-05-30 | 2024-05-30 |  | 0 | [5 empty] | 17.44% | 100% | 99.19% | -0.8121%
987 | Piling (Cutting only) |  | 14 | 14 | 2023-12-13 | 2023-12-26 | 2023-12-26 | 2023-12-26 | 2024-01-08 | 2024-01-08 |  | 0 | [5 empty] | 3.248% | 100% | 100% | 0%
988 | Cutting off Pile to GL |  | 14 | 14 | 2023-12-13 | 2023-12-26 | 2023-12-26 | 2023-12-26 | 2024-01-08 | 2024-01-08 | 100 | 0 | 0 | 100 | % | 100 |  | 100% | 100% | 100% | 0%
989 | Completion of Piling |  | 0 | 1 | 2023-12-26 | 2023-12-26 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
990 | Substructure |  | 417 | 64 | 2023-12-27 | 2024-02-28 | 2024-01-08 | 2024-01-08 | 2024-05-30 | 2024-05-30 |  | 0 | [5 empty] | 96.75% | 100% | 99.16% | -0.8393%
991 | Equipment Foundation |  | 417 | 64 | 2023-12-27 | 2024-02-28 | 2024-01-08 | 2024-01-08 | 2024-05-30 | 2024-05-30 |  | 0 | [5 empty] | 100% | 100% | 99.16% | -0.8393%
992 | V3506 / V3507 and V3508 |  | 40 | 42 | 2023-12-27 | 2024-02-06 | 2024-02-07 | 2024-02-07 | 2024-04-26 | 2024-04-26 |  | 0 | [5 empty] | 9.592% | 100% | 100% | 0%
993 | Excavation |  | 6 | 6 | 2023-12-27 | 2024-01-01 | 2024-02-07 | 2024-02-07 | 2024-02-09 | 2024-02-09 | 100 | 0 | 0 | 100 | % | 100 |  | 15% | 100% | 100% | 0%
994 | Leveling and Compaction |  | 6 | 6 | 2023-12-27 | 2024-01-01 | 2024-02-08 | 2024-02-08 | 2024-02-09 | 2024-02-09 | 100 | 0 | 0 | 100 | % | 100 |  | 15% | 100% | 100% | 0%
995 | Lean Concrete Pouring |  | 2 | 2 | 2024-01-02 | 2024-01-03 | 2024-02-09 | 2024-02-09 | 2024-02-09 | 2024-02-09 | 100 | 0 | 0 | 100 | % | 100 |  | 5% | 100% | 100% | 0%
996 | Pile Cutting and Treatment |  | 3 | 3 | 2024-01-04 | 2024-01-06 | 2024-02-13 | 2024-02-13 | 2024-02-15 | 2024-02-15 | 100 | 0 | 0 | 100 | % | 100 |  | 7.5% | 100% | 100% | 0%
997 | Reinforcement Bar Fixing |  | 11 | 11 | 2024-01-08 | 2024-01-18 | 2024-02-16 | 2024-02-16 | 2024-02-19 | 2024-02-19 | 100 | 0 | 0 | 100 | % | 100 |  | 27.5% | 100% | 100% | 0%
998 | Formwork Fixing |  | 2 | 2 | 2024-01-19 | 2024-01-20 | 2024-02-19 | 2024-02-19 | 2024-02-21 | 2024-02-21 | 100 | 0 | 0 | 100 | % | 100 |  | 5% | 100% | 100% | 0%
999 | Anchor Bolt / Inserted Plate Fixing |  | 2 | 2 | 2024-01-22 | 2024-01-23 | 2024-02-28 | 2024-02-28 | 2024-03-01 | 2024-03-01 | 100 | 0 | 0 | 100 | % | 100 |  | 5% | 100% | 100% | 0%
1000 | Concrete Pouring |  | 3 | 3 | 2024-01-24 | 2024-01-26 | 2024-03-06 | 2024-03-06 | 2024-04-25 | 2024-04-25 | 100 | 0 | 0 | 100 | % | 100 |  | 7.5% | 100% | 100% | 0%
1001 | Formwork Dismantling |  | 1 | 1 | 2024-01-31 | 2024-01-31 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 | 100 | % | 100 |  | 2.5% | 100% | 100% | 0%
1002 | Backfill with compaction |  | 4 | 4 | 2024-02-03 | 2024-02-06 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 | 100 | % | 100 |  | 10% | 100% | 100% | 0%
1003 | Completion of V3506 / V3507 and V3508 |  | 0 | 1 | 2024-02-06 | 2024-02-06 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
1004 | V3507 and V3508 |  | 44 | 45 | 2024-01-02 | 2024-02-15 | 2024-01-12 | 2024-01-12 | 2024-05-03 | 2024-05-03 |  | 0 | [5 empty] | 10.55% | 100% | 100% | 0%
1005 | Excavation |  | 7 | 7 | 2024-01-02 | 2024-01-08 | 2024-01-12 | 2024-01-12 | 2024-01-18 | 2024-01-18 | 100 | 0 | 0 | 100 | % | 100 |  | 15.91% | 100% | 100% | 0%
1006 | Leveling and Compaction |  | 7 | 7 | 2024-01-02 | 2024-01-08 | 2024-01-15 | 2024-01-15 | 2024-01-18 | 2024-01-18 | 100 | 0 | 0 | 100 | % | 100 |  | 15.91% | 100% | 100% | 0%
1007 | Lean Concrete Pouring |  | 2 | 2 | 2024-01-09 | 2024-01-10 | 2024-01-16 | 2024-01-16 | 2024-01-17 | 2024-01-17 | 100 | 0 | 0 | 100 | % | 100 |  | 4.545% | 100% | 100% | 0%
1008 | Pile Cutting and Treatment |  | 3 | 3 | 2024-01-11 | 2024-01-13 | 2024-01-18 | 2024-01-18 | 2024-01-20 | 2024-01-20 | 100 | 0 | 0 | 100 | % | 100 |  | 6.818% | 100% | 100% | 0%
1009 | Reinforcement Bar Fixing |  | 13 | 13 | 2024-01-15 | 2024-01-27 | 2024-01-31 | 2024-01-31 | 2024-02-02 | 2024-02-02 | 100 | 0 | 0 | 100 | % | 100 |  | 29.55% | 100% | 100% | 0%
1010 | Formwork Fixing |  | 2 | 2 | 2024-01-29 | 2024-01-30 | 2024-01-31 | 2024-01-31 | 2024-02-01 | 2024-02-01 | 100 | 0 | 0 | 100 | % | 100 |  | 4.545% | 100% | 100% | 0%
1011 | Anchor Bolt / Inserted Plate Fixing |  | 2 | 2 | 2024-01-31 | 2024-02-01 | 2024-02-29 | 2024-02-29 | 2024-03-01 | 2024-03-01 | 100 | 0 | 0 | 100 | % | 100 |  | 4.545% | 100% | 100% | 0%
1012 | Concrete Pouring |  | 4 | 4 | 2024-02-02 | 2024-02-05 | 2024-04-30 | 2024-04-30 | 2024-05-02 | 2024-05-02 | 100 | 0 | 0 | 100 | % | 100 |  | 9.091% | 100% | 100% | 0%
1013 | Formwork Dismantling |  | 1 | 1 | 2024-02-09 | 2024-02-09 | 2024-05-01 | 2024-05-01 | 2024-05-02 | 2024-05-02 | 100 | 0 | 0 | 100 | % | 100 |  | 2.273% | 100% | 100% | 0%
1014 | Backfill with compaction |  | 3 | 3 | 2024-02-13 | 2024-02-15 | 2024-05-02 | 2024-05-02 | 2024-05-03 | 2024-05-03 | 100 | 0 | 0 | 100 | % | 100 |  | 6.818% | 100% | 100% | 0%
1015 | Completion of V3501 A and V3501 B |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 2024-05-03 | 2024-05-03 | 2024-05-03 | 2024-05-03 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
1016 | V3501 A and V3501 B |  | 40 | 42 | 2024-01-09 | 2024-02-19 | 2024-01-08 | 2024-01-08 | 2024-05-07 | 2024-05-07 |  | 0 | [5 empty] | 9.592% | 100% | 100% | 0%
1017 | Excavation |  | 5 | 5 | 2024-01-09 | 2024-01-13 | 2024-01-08 | 2024-01-08 | 2024-01-09 | 2024-01-09 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
1018 | Leveling and Compaction |  | 5 | 5 | 2024-01-09 | 2024-01-13 | 2024-01-08 | 2024-01-08 | 2024-01-09 | 2024-01-09 | 100 | 0 | 0 | 100 | % | 100 |  | 12.5% | 100% | 100% | 0%
1019 | Lean Concrete Pouring |  | 2 | 2 | 2024-01-15 | 2024-01-16 | 2024-01-10 | 2024-01-10 | 2024-01-10 | 2024-01-10 | 100 | 0 | 0 | 100 | % | 100 |  | 5% | 100% | 100% | 0%
1020 | Pile Cutting and Treatment |  | 3 | 3 | 2024-01-17 | 2024-01-19 | 2024-01-11 | 2024-01-11 | 2024-01-12 | 2024-01-12 | 100 | 0 | 0 | 100 | % | 100 |  | 7.5% | 100% | 100% | 0%
1021 | Reinforcement Bar Fixing |  | 12 | 12 | 2024-01-20 | 2024-01-31 | 2024-01-29 | 2024-01-29 | 2024-01-31 | 2024-01-31 | 100 | 0 | 0 | 100 | % | 100 |  | 30% | 100% | 100% | 0%
1022 | Formwork Fixing |  | 2 | 2 | 2024-02-01 | 2024-02-02 | 2024-01-29 | 2024-01-29 | 2024-01-30 | 2024-01-30 | 100 | 0 | 0 | 100 | % | 100 |  | 5% | 100% | 100% | 0%
1023 | Anchor Bolt / Inserted Plate Fixing |  | 3 | 3 | 2024-02-03 | 2024-02-05 | 2024-02-29 | 2024-02-29 | 2024-03-01 | 2024-03-01 | 100 | 0 | 0 | 100 | % | 100 |  | 7.5% | 100% | 100% | 0%
1024 | Concrete Pouring |  | 3 | 3 | 2024-02-06 | 2024-02-08 | 2024-05-02 | 2024-05-02 | 2024-05-07 | 2024-05-07 | 100 | 0 | 0 | 100 | % | 100 |  | 7.5% | 100% | 100% | 0%
1025 | Formwork Dismantling |  | 1 | 1 | 2024-02-13 | 2024-02-13 | 2024-05-03 | 2024-05-03 | 2024-05-03 | 2024-05-03 | 100 | 0 | 0 | 100 | % | 100 |  | 2.5% | 100% | 100% | 0%
1026 | Backfill with compaction |  | 4 | 4 | 2024-02-16 | 2024-02-19 | 2024-05-03 | 2024-05-03 | 2024-05-03 | 2024-05-03 | 100 | 0 | 0 | 100 | % | 100 |  | 10% | 100% | 100% | 0%
1027 | Completion of V3501 A and V3501 B |  | 0 | 1 | 2024-02-19 | 2024-02-19 | 2024-05-03 | 2024-05-03 | 2024-05-03 | 2024-05-03 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
1028 | EX3501 A/B |  | 26 | 30 | 2024-01-15 | 2024-02-13 | 2024-01-08 | 2024-01-08 | 2024-02-16 | 2024-02-16 |  | 0 | [5 empty] | 6.235% | 100% | 100% | 0%
1029 | Excavation |  | 3 | 3 | 2024-01-15 | 2024-01-17 | 2024-01-08 | 2024-01-08 | 2024-01-09 | 2024-01-09 | 100 | 0 | 0 | 100 | % | 100 |  | 11.54% | 100% | 100% | 0%
1030 | Leveling and Compaction |  | 3 | 3 | 2024-01-15 | 2024-01-17 | 2024-01-08 | 2024-01-08 | 2024-01-09 | 2024-01-09 | 100 | 0 | 0 | 100 | % | 100 |  | 11.54% | 100% | 100% | 0%
1031 | Lean Concrete Pouring |  | 2 | 2 | 2024-01-18 | 2024-01-19 | 2024-01-10 | 2024-01-10 | 2024-01-10 | 2024-01-10 | 100 | 0 | 0 | 100 | % | 100 |  | 7.692% | 100% | 100% | 0%
1032 | Pile Cutting and Treatment |  | 3 | 3 | 2024-01-20 | 2024-01-22 | 2024-01-11 | 2024-01-11 | 2024-01-12 | 2024-01-12 | 100 | 0 | 0 | 100 | % | 100 |  | 11.54% | 100% | 100% | 0%
1033 | Reinforcement Bar Fixing |  | 7 | 7 | 2024-01-23 | 2024-01-29 | 2024-02-05 | 2024-02-05 | 2024-02-08 | 2024-02-08 | 100 | 0 | 0 | 100 | % | 100 |  | 26.92% | 100% | 100% | 0%
1034 | Formwork Fixing |  | 2 | 2 | 2024-01-30 | 2024-01-31 | 2024-02-07 | 2024-02-07 | 2024-02-09 | 2024-02-09 | 100 | 0 | 0 | 100 | % | 100 |  | 7.692% | 100% | 100% | 0%
1035 | Concrete Pouring |  | 1 | 1 | 2024-02-02 | 2024-02-02 | 2024-02-14 | 2024-02-14 | 2024-02-14 | 2024-02-14 | 100 | 0 | 0 | 100 | % | 100 |  | 3.846% | 100% | 100% | 0%
1036 | Formwork Dismantling |  | 1 | 1 | 2024-02-07 | 2024-02-07 | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-16 | 100 | 0 | 0 | 100 | % | 100 |  | 3.846% | 100% | 100% | 0%
1037 | Backfill with compaction |  | 4 | 4 | 2024-02-10 | 2024-02-13 | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-16 | 100 | 0 | 0 | 100 | % | 100 |  | 15.38% | 100% | 100% | 0%
1038 | Completion of EX3501 A/B |  | 0 | 1 | 2024-02-13 | 2024-02-13 | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-16 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
1039 | CU3501 and CU3502 |  | 33 | 38 | 2024-01-18 | 2024-02-24 | 2024-01-22 | 2024-01-22 | 2024-02-16 | 2024-02-16 |  | 0 | [5 empty] | 7.914% | 100% | 100% | 0%
1040 | Excavation |  | 5 | 5 | 2024-01-18 | 2024-01-22 | 2024-01-22 | 2024-01-22 | 2024-01-24 | 2024-01-24 | 100 | 0 | 0 | 100 | % | 100 |  | 15.15% | 100% | 100% | 0%
1041 | Leveling and Compaction |  | 5 | 5 | 2024-01-18 | 2024-01-22 | 2024-01-23 | 2024-01-23 | 2024-01-25 | 2024-01-25 | 100 | 0 | 0 | 100 | % | 100 |  | 15.15% | 100% | 100% | 0%
1042 | Lean Concrete Pouring |  | 2 | 2 | 2024-01-23 | 2024-01-24 | 2024-01-25 | 2024-01-25 | 2024-01-26 | 2024-01-26 | 100 | 0 | 0 | 100 | % | 100 |  | 6.061% | 100% | 100% | 0%
1043 | Pile Cutting and Treatment |  | 3 | 3 | 2024-01-25 | 2024-01-27 | 2024-01-25 | 2024-01-25 | 2024-01-26 | 2024-01-26 | 100 | 0 | 0 | 100 | % | 100 |  | 9.091% | 100% | 100% | 0%
1044 | Reinforcement Bar Fixing |  | 9 | 9 | 2024-01-29 | 2024-02-06 | 2024-02-02 | 2024-02-02 | 2024-02-05 | 2024-02-05 | 100 | 0 | 0 | 100 | % | 100 |  | 27.27% | 100% | 100% | 0%
1045 | Formwork Fixing |  | 4 | 4 | 2024-02-07 | 2024-02-10 | 2024-02-04 | 2024-02-04 | 2024-02-06 | 2024-02-06 | 100 | 0 | 0 | 100 | % | 100 |  | 12.12% | 100% | 100% | 0%
1046 | Concrete Pouring |  | 1 | 1 | 2024-02-14 | 2024-02-14 | 2024-02-14 | 2024-02-14 | 2024-02-14 | 2024-02-14 | 100 | 0 | 0 | 100 | % | 100 |  | 3.03% | 100% | 100% | 0%
1047 | Formwork Dismantling |  | 1 | 1 | 2024-02-19 | 2024-02-19 | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-16 | 100 | 0 | 0 | 100 | % | 100 |  | 3.03% | 100% | 100% | 0%
1048 | Backfill with compaction |  | 3 | 3 | 2024-02-22 | 2024-02-24 | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-16 | 100 | 0 | 0 | 100 | % | 100 |  | 9.091% | 100% | 100% | 0%
1049 | Completion of EX3501 A/B |  | 0 | 1 | 2024-02-24 | 2024-02-24 | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-16 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
1050 | K3501 |  | 33 | 37 | 2024-01-23 | 2024-02-28 | 2024-02-13 | 2024-02-13 | 2024-05-30 | 2024-05-30 |  | 0 | [5 empty] | 7.914% | 100% | 100% | 0%
1051 | Excavation |  | 4 | 4 | 2024-01-23 | 2024-01-26 | 2024-02-13 | 2024-02-13 | 2024-02-15 | 2024-02-15 | 100 | 0 | 0 | 100 | % | 100 |  | 12.12% | 100% | 100% | 0%
1052 | Leveling and Compaction |  | 4 | 4 | 2024-01-23 | 2024-01-26 | 2024-02-15 | 2024-02-15 | 2024-04-30 | 2024-04-30 | 100 | 0 | 0 | 100 | % | 100 |  | 12.12% | 100% | 100% | 0%
1053 | Lean Concrete Pouring |  | 3 | 3 | 2024-01-27 | 2024-01-29 | 2024-05-01 | 2024-05-01 | 2024-05-02 | 2024-05-02 | 100 | 0 | 0 | 100 | % | 100 |  | 9.091% | 100% | 100% | 0%
1054 | Pile Cutting and Treatment |  | 3 | 3 | 2024-01-30 | 2024-02-01 | 2024-05-02 | 2024-05-02 | 2024-05-03 | 2024-05-03 | 100 | 0 | 0 | 100 | % | 100 |  | 9.091% | 100% | 100% | 0%
1055 | Reinforcement Bar Fixing |  | 9 | 9 | 2024-02-02 | 2024-02-10 | 2024-05-03 | 2024-05-03 | 2024-05-13 | 2024-05-13 | 100 | 0 | 0 | 100 | % | 100 |  | 27.27% | 100% | 100% | 0%
1056 | Formwork Fixing |  | 4 | 4 | 2024-02-12 | 2024-02-15 | 2024-05-03 | 2024-05-03 | 2024-05-17 | 2024-05-17 | 100 | 0 | 0 | 100 | % | 100 |  | 12.12% | 100% | 100% | 0%
1057 | Anchor Bolt / Inserted Plate Fixing |  | 2 | 2 | 2024-02-16 | 2024-02-17 | 2024-05-18 | 2024-05-18 | 2024-05-20 | 2024-05-20 | 100 | 0 | 0 | 100 | % | 100 |  | 6.061% | 100% | 100% | 0%
1058 | Concrete Pouring |  | 1 | 1 | 2024-02-19 | 2024-02-19 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 100 | 0 | 0 | 100 | % | 100 |  | 3.03% | 100% | 100% | 0%
1059 | Formwork Dismantling |  | 1 | 1 | 2024-02-23 | 2024-02-23 | 2024-05-25 | 2024-05-25 | 2024-05-25 | 2024-05-25 | 100 | 0 | 0 | 100 | % | 100 |  | 3.03% | 100% | 100% | 0%
1060 | Backfill with compaction |  | 2 | 2 | 2024-02-27 | 2024-02-28 | 2024-05-29 | 2024-05-29 | 2024-05-30 | 2024-05-30 | 100 | 0 | 0 | 100 | % | 100 |  | 6.061% | 100% | 100% | 0%
1061 | Completion of K3501 |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-05-30 | 2024-05-30 | 2024-05-30 | 2024-05-30 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
1062 | MS3501A/B HT3501 CPK3501 and SIL3501 |  | 57 | 64 | 2023-12-27 | 2024-02-28 | 2024-01-24 | 2024-01-24 | 2024-05-17 | 2024-05-17 |  | 0 | [5 empty] | 13.67% | 100% | 100% | 0%
1063 | Foundation |  | 33 | 30 | 2023-12-27 | 2024-01-25 | 2024-01-24 | 2024-01-24 | 2024-04-26 | 2024-04-26 |  | 0 | [5 empty] | 57.89% | 100% | 100% | 0%
1064 | Excavation |  | 4 | 4 | 2023-12-27 | 2023-12-30 | 2024-01-24 | 2024-01-24 | 2024-01-26 | 2024-01-26 | 100 | 0 | 0 | 100 | % | 100 |  | 12.12% | 100% | 100% | 0%
1065 | Leveling and Compaction |  | 4 | 4 | 2023-12-27 | 2023-12-30 | 2024-01-26 | 2024-01-26 | 2024-02-06 | 2024-02-06 | 100 | 0 | 0 | 100 | % | 100 |  | 12.12% | 100% | 100% | 0%
1066 | Lean Concrete Pouring |  | 2 | 2 | 2024-01-01 | 2024-01-02 | 2024-02-06 | 2024-02-06 | 2024-02-08 | 2024-02-08 | 100 | 0 | 0 | 100 | % | 100 |  | 6.061% | 100% | 100% | 0%
1067 | Reinforcement Bar Fixing |  | 14 | 14 | 2024-01-03 | 2024-01-16 | 2024-02-26 | 2024-02-26 | 2024-04-23 | 2024-04-23 | 100 | 0 | 0 | 100 | % | 100 |  | 42.42% | 100% | 100% | 0%
1068 | Anchor Bolt / Inserted Plate Fixing |  | 3 | 3 | 2024-01-17 | 2024-01-19 | 2024-04-24 | 2024-04-24 | 2024-04-25 | 2024-04-25 | 100 | 0 | 0 | 100 | % | 100 |  | 9.091% | 100% | 100% | 0%
1069 | Formwork Fixing |  | 5 | 5 | 2024-01-20 | 2024-01-24 | 2024-04-25 | 2024-04-25 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 | 100 | % | 100 |  | 15.15% | 100% | 100% | 0%
1070 | Concrete Pouring |  | 1 | 1 | 2024-01-25 | 2024-01-25 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 | 100 | % | 100 |  | 3.03% | 100% | 100% | 0%
1071 | Plinth |  | 21 | 22 | 2024-01-26 | 2024-02-16 | 2024-04-29 | 2024-04-29 | 2024-05-06 | 2024-05-06 |  | 0 | [5 empty] | 36.84% | 100% | 100% | 0%
1072 | Reinforcement Bar Fixing |  | 11 | 11 | 2024-01-26 | 2024-02-05 | 2024-04-29 | 2024-04-29 | 2024-05-02 | 2024-05-02 | 100 | 0 | 0 | 100 | % | 100 |  | 52.38% | 100% | 100% | 0%
1073 | Formwork Fixing |  | 5 | 5 | 2024-02-06 | 2024-02-10 | 2024-04-30 | 2024-04-30 | 2024-05-03 | 2024-05-03 | 100 | 0 | 0 | 100 | % | 100 |  | 23.81% | 100% | 100% | 0%
1074 | Anchor Bolt / Inserted Plate Fixing |  | 3 | 3 | 2024-02-12 | 2024-02-14 | 2024-05-02 | 2024-05-02 | 2024-05-03 | 2024-05-03 | 100 | 0 | 0 | 100 | % | 100 |  | 14.29% | 100% | 100% | 0%
1075 | Concrete Pouring |  | 2 | 2 | 2024-02-15 | 2024-02-16 | 2024-05-04 | 2024-05-04 | 2024-05-06 | 2024-05-06 | 100 | 0 | 0 | 100 | % | 100 |  | 9.524% | 100% | 100% | 0%
1076 | Formwork Dismantling |  | 1 | 1 | 2024-02-26 | 2024-02-26 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 100 | 0 | 0 | 100 | % | 100 |  | 1.754% | 100% | 100% | 0%
1077 | Backfill with compaction |  | 2 | 2 | 2024-02-27 | 2024-02-28 | 2024-05-16 | 2024-05-16 | 2024-05-17 | 2024-05-17 | 100 | 0 | 0 | 100 | % | 100 |  | 3.509% | 100% | 100% | 0%
1078 | Completion of MS3501A/B HT3501 CPK3501 & SIL3501 |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-05-17 | 2024-05-17 | 2024-05-17 | 2024-05-17 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
1079 | CPK3503 |  | 73 | 37 | 2024-01-01 | 2024-02-06 | 2024-01-23 | 2024-01-23 | 2024-05-15 | 2024-05-15 |  | 0 | [5 empty] | 17.51% | 100% | 100% | 0%
1080 | Foundation |  | 31 | 23 | 2024-01-01 | 2024-01-23 | 2024-01-23 | 2024-01-23 | 2024-02-16 | 2024-02-16 |  | 0 | [5 empty] | 42.47% | 100% | 100% | 0%
1081 | Excavation |  | 3 | 3 | 2024-01-01 | 2024-01-03 | 2024-01-23 | 2024-01-23 | 2024-01-25 | 2024-01-25 | 100 | 0 | 0 | 100 | % | 100 |  | 9.677% | 100% | 100% | 0%
1082 | Leveling and Compaction |  | 3 | 3 | 2024-01-03 | 2024-01-05 | 2024-01-24 | 2024-01-24 | 2024-01-26 | 2024-01-26 | 100 | 0 | 0 | 100 | % | 100 |  | 9.677% | 100% | 100% | 0%
1083 | Lean Concrete Pouring |  | 3 | 3 | 2024-01-04 | 2024-01-06 | 2024-01-26 | 2024-01-26 | 2024-01-26 | 2024-01-26 | 100 | 0 | 0 | 100 | % | 100 |  | 9.677% | 100% | 100% | 0%
1084 | Pile Cutting and Treatment |  | 4 | 4 | 2024-01-06 | 2024-01-09 | 2024-01-26 | 2024-01-26 | 2024-01-26 | 2024-01-26 | 100 | 0 | 0 | 100 | % | 100 |  | 12.9% | 100% | 100% | 0%
1085 | Reinforcement Bar Fixing |  | 3 | 3 | 2024-01-10 | 2024-01-12 | 2024-02-03 | 2024-02-03 | 2024-02-06 | 2024-02-06 | 100 | 0 | 0 | 100 | % | 100 |  | 9.677% | 100% | 100% | 0%
1086 | Formwork Fixing |  | 4 | 4 | 2024-01-13 | 2024-01-16 | 2024-02-06 | 2024-02-06 | 2024-02-07 | 2024-02-07 | 100 | 0 | 0 | 100 | % | 100 |  | 12.9% | 100% | 100% | 0%
1087 | Concrete Pouring |  | 3 | 3 | 2024-01-16 | 2024-01-18 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 100 | 0 | 0 | 100 | % | 100 |  | 9.677% | 100% | 100% | 0%
1088 | Formwork Dismantling |  | 4 | 4 | 2024-01-19 | 2024-01-22 | 2024-02-13 | 2024-02-13 | 2024-02-15 | 2024-02-15 | 100 | 0 | 0 | 100 | % | 100 |  | 12.9% | 100% | 100% | 0%
1089 | Backfill with compaction |  | 4 | 4 | 2024-01-20 | 2024-01-23 | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-16 | 100 | 0 | 0 | 100 | % | 100 |  | 12.9% | 100% | 100% | 0%
1090 | Completion of Pile Cap |  | 0 | 1 | 2024-01-23 | 2024-01-23 | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-16 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
1091 | Stump / Plinth |  | 42 | 20 | 2024-01-18 | 2024-02-06 | 2024-02-24 | 2024-02-24 | 2024-05-15 | 2024-05-15 |  | 0 | [5 empty] | 57.53% | 100% | 100% | 0%
1092 | Reinforcement Bar Fixing |  | 7 | 7 | 2024-01-18 | 2024-01-24 | 2024-02-24 | 2024-02-24 | 2024-02-28 | 2024-02-28 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
1093 | Formwork Fixing |  | 7 | 7 | 2024-01-20 | 2024-01-26 | 2024-02-27 | 2024-02-27 | 2024-04-25 | 2024-04-25 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
1094 | Anchor Bolt Fixing |  | 7 | 7 | 2024-01-23 | 2024-01-29 | 2024-05-01 | 2024-05-01 | 2024-05-03 | 2024-05-03 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
1095 | Concrete Pouring |  | 7 | 7 | 2024-01-26 | 2024-02-01 | 2024-05-04 | 2024-05-04 | 2024-05-10 | 2024-05-10 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
1096 | Formwork Dismantling |  | 7 | 7 | 2024-01-30 | 2024-02-05 | 2024-05-08 | 2024-05-08 | 2024-05-14 | 2024-05-14 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
1097 | Backfill with compaction |  | 7 | 7 | 2024-01-31 | 2024-02-06 | 2024-05-09 | 2024-05-09 | 2024-05-15 | 2024-05-15 | 100 | 0 | 0 | 100 | % | 100 |  | 16.67% | 100% | 100% | 0%
1098 | Completion of Stump |  | 0 | 1 | 2024-02-06 | 2024-02-06 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
1099 | Completion of CPK3503 |  | 0 | 1 | 2024-02-06 | 2024-02-06 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
1100 | E3501, E3505 and E3506 |  | 71 | 37 | 2024-01-04 | 2024-02-09 | 2024-01-08 | 2024-01-08 | 2024-03-16 | 2024-03-16 |  | 0 | [5 empty] | 17.03% | 100% | 95.07% | -4.93%
1101 | Foundation |  | 30 | 23 | 2024-01-04 | 2024-01-26 | 2024-01-08 | 2024-01-08 | 2024-03-01 | 2024-03-01 |  | 0 | [5 empty] | 42.25% | 100% | 100% | 0%
1102 | Excavation |  | 3 | 3 | 2024-01-04 | 2024-01-06 | 2024-01-08 | 2024-01-08 | 2024-01-09 | 2024-01-09 | 100 | 0 | 0 | 100 | % | 100 |  | 10% | 100% | 100% | 0%
1103 | Leveling and Compaction |  | 4 | 4 | 2024-01-06 | 2024-01-09 | 2024-01-08 | 2024-01-08 | 2024-01-09 | 2024-01-09 | 100 | 0 | 0 | 100 | % | 100 |  | 13.33% | 100% | 100% | 0%
1104 | Lean Concrete Pouring |  | 3 | 3 | 2024-01-08 | 2024-01-10 | 2024-01-10 | 2024-01-10 | 2024-01-10 | 2024-01-10 | 100 | 0 | 0 | 100 | % | 100 |  | 10% | 100% | 100% | 0%
1105 | Pile Cutting and Treatment |  | 3 | 3 | 2024-01-10 | 2024-01-12 | 2024-02-03 | 2024-02-03 | 2024-02-07 | 2024-02-07 | 100 | 0 | 0 | 100 | % | 100 |  | 10% | 100% | 100% | 0%
1106 | Reinforcement Bar Fixing |  | 4 | 4 | 2024-01-13 | 2024-01-16 | 2024-02-06 | 2024-02-06 | 2024-02-27 | 2024-02-27 | 100 | 0 | 0 | 100 | % | 100 |  | 13.33% | 100% | 100% | 0%
1107 | Formwork Fixing |  | 3 | 3 | 2024-01-17 | 2024-01-19 | 2024-02-07 | 2024-02-07 | 2024-03-01 | 2024-03-01 | 100 | 0 | 0 | 100 | % | 100 |  | 10% | 100% | 100% | 0%
1108 | Concrete Pouring |  | 4 | 4 | 2024-01-19 | 2024-01-22 | 2024-02-07 | 2024-02-07 | 2024-02-12 | 2024-02-12 | 100 | 0 | 0 | 100 | % | 100 |  | 13.33% | 100% | 100% | 0%
1109 | Formwork Dismantling |  | 3 | 3 | 2024-01-23 | 2024-01-25 | 2024-02-10 | 2024-02-10 | 2024-02-13 | 2024-02-13 | 100 | 0 | 0 | 100 | % | 100 |  | 10% | 100% | 100% | 0%
1110 | Backfill with compaction |  | 3 | 3 | 2024-01-24 | 2024-01-26 | 2024-02-12 | 2024-02-12 | 2024-02-14 | 2024-02-14 | 100 | 0 | 0 | 100 | % | 100 |  | 10% | 100% | 100% | 0%
1111 | Completion of Pile Cap |  | 0 | 1 | 2024-01-26 | 2024-01-26 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
1112 | Stump / Plinth |  | 41 | 19 | 2024-01-22 | 2024-02-09 | 2024-02-27 | 2024-02-27 | 2024-03-16 | 2024-03-16 |  | 0 | [5 empty] | 57.75% | 100% | 91.46% | -8.537%
1113 | Reinforcement Bar Fixing |  | 6 | 6 | 2024-01-22 | 2024-01-27 | 2024-02-27 | 2024-02-27 | 2024-03-04 | 2024-03-04 | 100 | 0 | 0 | 100 | % | 100 |  | 14.63% | 100% | 100% | 0%
1114 | Formwork Fixing |  | 7 | 7 | 2024-01-24 | 2024-01-30 | 2024-02-29 | 2024-02-29 | 2024-03-06 | 2024-03-06 | 100 | 0 | 0 | 100 | % | 100 |  | 17.07% | 100% | 100% | 0%
1115 | Anchor Bolt Fixing |  | 7 | 7 | 2024-01-26 | 2024-02-01 | 2024-03-02 | 2024-03-02 | 2024-03-08 | 2024-03-08 | 100 | 0 | 0 | 100 | % | 100 |  | 17.07% | 100% | 100% | 0%
1116 | Concrete Pouring |  | 7 | 7 | 2024-01-30 | 2024-02-05 | 2024-03-06 | 2024-03-06 | 2024-03-12 | 2024-03-12 | 100 | 0 | 0 | 100 | % | 100 |  | 17.07% | 100% | 100% | 0%
1117 | Formwork Dismantling |  | 7 | 7 | 2024-02-02 | 2024-02-08 | 2024-03-09 | 2024-03-09 | 2024-03-15 | 2024-03-15 | 100 | 0 | 0 | 100 | % | 100 |  | 17.07% | 100% | 100% | 0%
1118 | Backfill with compaction |  | 7 | 7 | 2024-02-03 | 2024-02-09 | 2024-03-11 | 2024-03-11 | 2024-03-16 | 2024-03-16 | 100 | 0 | 0 | 50 | % | 100 |  | 17.07% | 100% | 50% | -50%
1119 | Completion of Stump |  | 0 | 1 | 2024-02-09 | 2024-02-09 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
1120 | Completion of E3501, E3505 and E3506 |  | 0 | 1 | 2024-02-09 | 2024-02-09 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
1121 | Completion of Equipment and Pump Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-05-30 | 2024-05-30 | 2024-05-30 | 2024-05-30 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
1122 | Completion of Substructure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-05-30 | 2024-05-30 | 2024-05-30 | 2024-05-30 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
1123 | Completion of Unit 340 - Instrument Air & Plant Air System |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-05-30 | 2024-05-30 | 2024-05-30 | 2024-05-30 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
1124 | Unit 380 - Excess Steam Recovery System |  | 216 | 58 | 2023-12-27 | 2024-02-22 | 2024-02-02 | 2024-02-02 | 2024-05-24 | 2024-05-24 |  | 0 | [5 empty] | 8.741% | 100% | 68.06% | -31.94%
1125 | Piling (Cutting only) |  | 9 | 9 | 2023-12-27 | 2024-01-04 | 2024-02-02 | 2024-02-02 | 2024-02-06 | 2024-02-06 |  | 0 | [5 empty] | 4.167% | 100% | 100% | 0%
1126 | Cutting off Pile to GL |  | 9 | 9 | 2023-12-27 | 2024-01-04 | 2024-02-02 | 2024-02-02 | 2024-02-06 | 2024-02-06 | 100 | 0 | 0 | 100 | % | 100 |  | 100% | 100% | 100% | 0%
1127 | Completion of Piling |  | 0 | 1 | 2024-01-04 | 2024-01-04 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
1128 | Substructure |  | 207 | 49 | 2024-01-05 | 2024-02-22 | 2024-02-07 | 2024-02-07 | 2024-05-24 | 2024-05-24 |  | 0 | [5 empty] | 95.83% | 100% | 66.67% | -33.33%
1129 | Structure |  | 207 | 49 | 2024-01-05 | 2024-02-22 | 2024-02-07 | 2024-02-07 | 2024-05-24 | 2024-05-24 |  | 0 | [5 empty] | 100% | 100% | 66.67% | -33.33%
1130 | Pipe Raft |  | 124 | 34 | 2024-01-05 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-05-02 | 2024-05-02 |  | 0 | [5 empty] | 59.9% | 100% | 100% | 0%
1131 | Excavation |  | 14 | 14 | 2024-01-05 | 2024-01-18 | 2024-02-07 | 2024-02-07 | 2024-02-20 | 2024-02-20 | 100 | 0 | 0 | 100 | % | 100 |  | 11.29% | 100% | 100% | 0%
1132 | Leveling and Compaction |  | 13 | 13 | 2024-01-08 | 2024-01-20 | 2024-02-08 | 2024-02-08 | 2024-02-20 | 2024-02-20 | 100 | 0 | 0 | 100 | % | 100 |  | 10.48% | 100% | 100% | 0%
1133 | Lean Concrete Pouring |  | 14 | 14 | 2024-01-09 | 2024-01-22 | 2024-02-21 | 2024-02-21 | 2024-02-22 | 2024-02-22 | 100 | 0 | 0 | 100 | % | 100 |  | 11.29% | 100% | 100% | 0%
1134 | Pile Cutting and Treatment |  | 14 | 14 | 2024-01-11 | 2024-01-24 | 2024-02-22 | 2024-02-22 | 2024-02-23 | 2024-02-23 | 100 | 0 | 0 | 100 | % | 100 |  | 11.29% | 100% | 100% | 0%
1135 | Reinforcement Bar Fixing |  | 13 | 13 | 2024-01-15 | 2024-01-27 | 2024-04-22 | 2024-04-22 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 | 100 | % | 100 |  | 10.48% | 100% | 100% | 0%
1136 | Formwork Fixing |  | 14 | 14 | 2024-01-18 | 2024-01-31 | 2024-04-23 | 2024-04-23 | 2024-04-26 | 2024-04-26 | 100 | 0 | 0 | 100 | % | 100 |  | 11.29% | 100% | 100% | 0%
1137 | Concrete Pouring |  | 14 | 14 | 2024-01-20 | 2024-02-02 | 2024-04-29 | 2024-04-29 | 2024-04-30 | 2024-04-30 | 100 | 0 | 0 | 100 | % | 100 |  | 11.29% | 100% | 100% | 0%
1138 | Formwork Dismantling |  | 14 | 14 | 2024-01-24 | 2024-02-06 | 2024-04-30 | 2024-04-30 | 2024-05-01 | 2024-05-01 | 100 | 0 | 0 | 100 | % | 100 |  | 11.29% | 100% | 100% | 0%
1139 | Backfill with compaction |  | 14 | 14 | 2024-01-25 | 2024-02-07 | 2024-05-01 | 2024-05-01 | 2024-05-02 | 2024-05-02 | 100 | 0 | 0 | 100 | % | 100 |  | 11.29% | 100% | 100% | 0%
1140 | Completion of Pile Cap |  | 0 | 1 | 2024-02-07 | 2024-02-07 | 2024-05-02 | 2024-05-02 | 2024-05-02 | 2024-05-02 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
1141 | Stump | Rebar only | 83 | 27 | 2024-01-27 | 2024-02-22 | 2024-04-29 | 2024-04-29 | 2024-05-24 | 2024-05-24 |  | 0 | [5 empty] | 40.1% | 100% | 16.87% | -83.13%
1142 | Reinforcement Bar Fixing |  | 14 | 14 | 2024-01-27 | 2024-02-09 | 2024-04-29 | 2024-04-29 | 2024-05-16 | 2024-05-16 | 100 | 0 | 0 | 100 | % | 100 |  | 16.87% | 100% | 100% | 0%
1143 | Formwork Fixing |  | 14 | 14 | 2024-01-30 | 2024-02-12 | 2024-05-01 | 2024-05-01 | 2024-05-14 | 2024-05-14 | 100 | 0 | 0 |  | % | 100 |  | 16.87% | 100% | 0% | -100%
1144 | Anchor Bolt Fixing |  | 14 | 14 | 2024-02-01 | 2024-02-14 | 2024-05-03 | 2024-05-03 | 2024-05-16 | 2024-05-16 | 100 | 0 | 0 |  | % | 100 |  | 16.87% | 100% | 0% | -100%
1145 | Concrete Pouring |  | 13 | 13 | 2024-02-05 | 2024-02-17 | 2024-05-07 | 2024-05-07 | 2024-05-20 | 2024-05-20 | 100 | 0 | 0 |  | % | 100 |  | 15.66% | 100% | 0% | -100%
1146 | Formwork Dismantling |  | 14 | 14 | 2024-02-08 | 2024-02-21 | 2024-05-10 | 2024-05-10 | 2024-05-23 | 2024-05-23 | 100 | 0 | 0 |  | % | 100 |  | 16.87% | 100% | 0% | -100%
1147 | Backfill with compaction |  | 14 | 14 | 2024-02-09 | 2024-02-22 | 2024-05-11 | 2024-05-11 | 2024-05-24 | 2024-05-24 | 100 | 0 | 0 |  | % | 100 |  | 16.87% | 100% | 0% | -100%
1148 | Completion of Stump |  | 0 | 1 | 2024-02-22 | 2024-02-22 | 2024-05-24 | 2024-05-24 | 2024-05-24 | 2024-05-24 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
1149 | Completion of Structure |  | 0 | 1 | 2024-02-22 | 2024-02-22 | 2024-05-24 | 2024-05-24 | 2024-05-24 | 2024-05-24 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
1150 | Completion of Substructure |  | 0 | 1 | 2024-02-22 | 2024-02-22 | 2024-05-24 | 2024-05-24 | 2024-05-24 | 2024-05-24 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
1151 | Completion of Unit 380 - Excess Steam Recovery System |  | 0 | 1 | 2024-02-22 | 2024-02-22 | 2024-05-24 | 2024-05-24 | 2024-05-24 | 2024-05-24 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
1152 | Unit 510 - Fire Water Tank |  | 75 | 55 | 2024-01-05 | 2024-02-28 | 2024-01-18 | 2024-01-18 | 2024-06-03 | 2024-06-03 |  | 0 | [5 empty] | 3.035% | 100% | 64.67% | -35.33%
1153 | Piling (Cutting only) |  | 7 | 7 | 2024-01-05 | 2024-01-11 | 2024-01-18 | 2024-01-18 | 2024-01-24 | 2024-01-24 |  | 0 | [5 empty] | 9.333% | 100% | 100% | 0%
1154 | Cutting off Pile to GL |  | 7 | 7 | 2024-01-05 | 2024-01-11 | 2024-01-18 | 2024-01-18 | 2024-01-24 | 2024-01-24 | 100 | 0 | 0 | 100 | % | 100 |  | 100% | 100% | 100% | 0%
1155 | Completion of Piling |  | 0 | 1 | 2024-01-11 | 2024-01-11 | 2024-01-24 | 2024-01-24 | 2024-01-24 | 2024-01-24 | 100 | 0 | 0 | 100 | % | 100 |  | 0% | 100% | 100% | 0%
1156 | Substructure |  | 68 | 48 | 2024-01-12 | 2024-02-28 | 2024-01-24 | 2024-01-24 | 2024-06-03 | 2024-06-03 |  | 0 | [5 empty] | 90.67% | 100% | 61.03% | -38.97%
1157 | Tank / Equipment and Pump Foundation |  | 68 | 48 | 2024-01-12 | 2024-02-28 | 2024-01-24 | 2024-01-24 | 2024-06-03 | 2024-06-03 |  | 0 | [5 empty] | 100% | 100% | 61.03% | -38.97%
1158 | Fire Water Tank |  | 68 | 48 | 2024-01-12 | 2024-02-28 | 2024-01-24 | 2024-01-24 | 2024-06-03 | 2024-06-03 |  | 0 | [5 empty] | 100% | 100% | 61.03% | -38.97%
1159 | Excavation |  | 11 | 11 | 2024-01-12 | 2024-01-22 | 2024-01-24 | 2024-01-24 | 2024-01-29 | 2024-01-29 | 100 | 0 | 0 | 100 | % | 100 |  | 16.18% | 100% | 100% | 0%
1160 | Leveling and Compaction |  | 11 | 11 | 2024-01-12 | 2024-01-22 | 2024-01-24 | 2024-01-24 | 2024-01-29 | 2024-01-29 | 100 | 0 | 0 | 100 | % | 100 |  | 16.18% | 100% | 100% | 0%
1161 | Lean Concrete Pouring |  | 10 | 10 | 2024-01-16 | 2024-01-25 | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2024-01-30 | 100 | 0 | 0 | 100 | % | 100 |  | 14.71% | 100% | 100% | 0%
1162 | Pile Cutting and Treatment |  | 6 | 6 | 2024-01-22 | 2024-01-27 | 2024-01-31 | 2024-01-31 | 2024-02-01 | 2024-02-01 | 100 | 0 | 0 | 100 | % | 100 |  | 8.824% | 100% | 100% | 0%
1163 | Reinforcement Bar Fixing |  | 14 | 14 | 2024-01-25 | 2024-02-07 | 2024-04-30 | 2024-04-30 | 2024-05-13 | 2024-05-13 | 100 | 0 | 0 | 25 | % | 100 |  | 20.59% | 100% | 25% | -75%
1164 | Formwork Fixing |  | 6 | 6 | 2024-02-05 | 2024-02-10 | 2024-05-10 | 2024-05-10 | 2024-05-16 | 2024-05-16 | 100 | 0 | 0 |  | % | 100 |  | 8.824% | 100% | 0% | -100%
1165 | Anchor Bolt / Inserted Plate Fixing |  | 3 | 3 | 2024-02-12 | 2024-02-14 | 2024-05-17 | 2024-05-17 | 2024-05-20 | 2024-05-20 | 100 | 0 | 0 |  | % | 100 |  | 4.412% | 100% | 0% | -100%
1166 | Concrete Pouring |  | 1 | 1 | 2024-02-15 | 2024-02-15 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 100 | 0 | 0 |  | % | 100 |  | 1.471% | 100% | 0% | -100%
1167 | Formwork Dismantling |  | 3 | 3 | 2024-02-20 | 2024-02-22 | 2024-05-25 | 2024-05-25 | 2024-05-28 | 2024-05-28 | 100 | 0 | 0 |  | % | 100 |  | 4.412% | 100% | 0% | -100%
1168 | Backfill with compaction |  | 3 | 3 | 2024-02-26 | 2024-02-28 | 2024-05-31 | 2024-05-31 | 2024-06-03 | 2024-06-03 | 100 | 0 | 0 |  | % | 100 |  | 4.412% | 100% | 0% | -100%
1169 | Completion of Fire Water Tank |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
1170 | Completion of Tank / Equipment and Pump Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
1171 | Completion of Substructure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
1172 | Completion of Unit 510 - Fire Water Tank |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
1173 | COMPLETION OF OTHER UNIT (SUBSTRUCTURE) |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
1174 | MECHANICAL COMPLETION |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 100 | 0 | 0 |  | % | 100 |  | 0% | 100% | 0% | -100%
| x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
Formulas:
Actual / Forecast Start = MIN([Actual / Forecast Start, row below]:H1036)
Actual / Forecast Start = [For Dyna Only]
SPI = MAX([SPI, row below]:K1036)
SPI = [For Dyna Only]

## S-Curve - Overall
Date | 2023-10-20 | 2023-10-27 | 2023-11-03 | 2023-11-10 | 2023-11-17 | 2023-11-24 | 2023-12-01 | 2023-12-08 | 2023-12-15 | 2023-12-22 | 2023-12-29 | 2024-01-05 | 2024-01-12 | 2024-01-19 | 2024-01-26 | 2024-02-02 | 2024-02-09 | 2024-02-16 | 2024-02-23 | 2024-03-01 | 2024-03-08 | 2024-03-15 | 2024-03-22 | 2024-03-29 | 2024-04-05 | 2024-04-12 | 2024-04-19 | 2024-04-26 | 2024-05-03 | 2024-05-10 | 2024-05-17 | 2024-05-24 | 2024-05-31
Work Week | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33
Plan | 0% | 0% | 0% | 0% | 0% | 0% | 0.01777% | 0.3022% | 1.155% | 2.808% | 6.337% | 9.98% | 13.49% | 15.69% | 16.14% | 13.76% | 10.24% | 6.026% | 2.915% | 1.146% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Actual | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.35% | 1% | 4.724% | 3.424% | 2.84% | 4.534% | 6.248% | 4.645% | 6.675% | 5.675% | 6.214% | 6.988% | 5.137% | 5.592% | 4.287% | 5.98% | 4.24% | 2.82% | 1.855% | 0.9584% | 1.744% | 1.762% | 3.566% | -91.26% | 0% | 0%
Plan Cum | 0% | 0% | 0% | 0% | 0% | 0% | 0.01777% | 0.3199% | 1.475% | 4.284% | 10.62% | 20.6% | 34.09% | 49.78% | 65.92% | 79.67% | 89.91% | 95.94% | 98.85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Actual Cum | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.35% | 1.35% | 6.074% | 9.498% | 12.34% | 16.87% | 23.12% | 27.76% | 34.44% | 40.11% | 46.33% | 53.32% | 58.45% | 64.04% | 68.33% | 74.31% | 78.55% | 81.37% | 83.23% | 84.18% | 85.93% | 87.69% | 91.26%
Variance | 0% | 0% | 0% | 0% | 0% | 0% | -0.01777% | 0.03006% | -0.1253% | 1.79% | -1.123% | -8.264% | -17.22% | -26.66% | -38.15% | -45.24% | -49.8% | -49.61% | -45.54% | -41.55% | -35.96% | -31.67% | -25.69% | -21.45% | -18.63% | -16.77% | -15.82% | -14.07% | -12.31% | -8.743% | -100% | -100% | -100%
CUMULATIVE

## Resource Loading
| 2023-10-20 | 2023-10-27 | 2023-11-03 | 2023-11-10 | 2023-11-17 | 2023-11-24 | 2023-12-01 | 2023-12-08 | 2023-12-15 | 2023-12-22 | 2023-12-29 | 2024-01-05 | 2024-01-12 | 2024-01-19 | 2024-01-26 | 2024-02-02 | 2024-02-09 | 2024-02-16 | 2024-02-23 | 2024-03-01 | 2024-03-08 | 2024-03-15 | 2024-03-22 | 2024-03-29 | 2024-04-05 | 2024-04-12 | 2024-04-19 | 2024-04-26 | 2024-05-03 | 2024-05-10
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30
P - Site | 0 | 0 | 0 | 0 | 20 | 79 | 75 | 77 | 117 | 149 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 195 | 65
P - W/S | 0 | 0 | 0 | 0 | 10 | 15 | 30 | 35 | 33 | 61 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 0
Plan | 0 | 0 | 0 | 0 | 30 | 94 | 105 | 112 | 150 | 210 | 264 | 264 | 264 | 264 | 264 | 264 | 264 | 264 | 264 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A - Site | 0 | 0 | 0 | 0 | 23 | 18 | 45 | 85 | 122 | 152 | 174 | 184 | 292 | 294 | 321 | 321 | 361 | 361 | 376 | 376 | 322 | 303 | 312 | 265 | 265 | 240 | 205 | 205 | 198 | 198
A - W/S | 0 | 0 | 0 | 0 | 10 | 15 | 30 | 30 | 33 | 45 | 52 | 52 | 33 | 35 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual | 0 | 0 | 0 | 0 | 33 | 33 | 75 | 115 | 155 | 197 | 226 | 236 | 325 | 329 | 360 | 360 | 400 | 400 | 415 | 415 | 361 | 303 | 312 | 265 | 265 | 240 | 205 | 205 | 198 | 198
Management | 0 | 0 | 0 | 5 | 8 | 12 | 15 | 18 | 21 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 24 | 24 | 24 | 24 | 24 | 22

## Curve Data (hidden)
| PROJECT : ECOCERES SUBSTRUCTURE WORKS | [11 empty] | Updated On : | 2024-03-15 |  |  | 2023-10-20 |  | 2023-10-27 |  | 2023-11-03 |  | 2023-11-10 |  | 2023-11-17 |  | 2023-11-24 |  | 2023-12-01 |  | 2023-12-08 |  | 2023-12-15 |  | 2023-12-22 |  | 2023-12-29 |  | 2024-01-05 |  | 2024-01-12 |  | 2024-01-19 |  | 2024-01-26 |  | 2024-02-02 |  | 2024-02-09 |  | 2024-02-16 |  | 2024-02-23 |  | 2024-03-01 |  | 2024-03-08 |  | 2024-03-15 |  | 2024-03-22 |  | 2024-03-29 |  | 2024-04-05 |  | 2024-04-12 |  | 2024-04-19 |  | 2024-04-26 |  | 2024-05-03 |  | 2024-05-10 |  | 2024-05-17 |  | 2024-05-24 |  | 2024-05-31 |  | 2024-06-07 |  | 2024-06-14 |  | 2024-06-21
WEEKLY SCHEDULE & PROGRESS UPDATE
| CONTRACTOR | PACKAGE NO |  |  | Plan Start | Plan Finish
| DYNACIATE | ECOCERES SUBSTRUCTURE PACKAGE |  |  | 2023-11-29 | 2024-02-28
| Activity ID | Activity Description | Sub sum | Plan Duration | Baseline Start | Baseline Finish | Total Quantity | Installed Quantity | Unit | Plan Units | Weightage | Plan Prog % | Actual Prog % | Delta | Remark | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog % | Plan Units | Plan Prog %
0.1 | PELICAN S01B SITE ESTABLISHMENT |  | 11252 | 92 | 2023-11-29 | 2024-02-28 |  |  |  |  | 100% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.01777% |  | 0.3199% |  | 1.475% |  | 4.284% |  | 10.62% |  | 20.6% |  | 34.09% |  | 49.78% |  | 65.92% |  | 79.67% |  | 89.91% |  | 95.94% |  | 98.85% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
147 | UNIT 700, 800 and 900 (SUBSTRUCTURE) |  | 8781 | 92 | 2023-11-29 | 2024-02-28 |  |  |  |  | 78.04% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.02278% |  | 0.41% |  | 1.799% |  | 5.034% |  | 12.05% |  | 22.82% |  | 36.67% |  | 52.34% |  | 67.62% |  | 80.74% |  | 90.41% |  | 96.11% |  | 98.91% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
148 | Unit 700 - Auxillary & Tank Yard |  | 819 | 73 | 2023-12-05 | 2024-02-15 |  |  |  |  | 9.327% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.3663% |  | 0.8547% |  | 2.442% |  | 9.035% |  | 19.54% |  | 35.16% |  | 53.11% |  | 72.77% |  | 87.42% |  | 96.34% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
149 | Piling (Cutting only) |  | 7 | 7 | 2023-12-05 | 2023-12-11 |  |  |  |  | 0.8547% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 42.86% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
150 | Cutting off Pile to GL |  | 7 | 7 | 2023-12-05 | 2023-12-11 | 100 | 100 | % | 100 | 100% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
151 | Completion of Piling |  | 0 | 1 | 2023-12-11 | 2023-12-11 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
152 | Substructure |  | 812 | 62 | 2023-12-16 | 2024-02-15 |  |  |  |  | 99.15% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 1.601% |  | 8.251% |  | 18.84% |  | 34.61% |  | 52.71% |  | 72.54% |  | 87.32% |  | 96.31% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
153 | Structure |  | 313 | 56 | 2023-12-16 | 2024-02-09 |  |  |  |  | 38.55% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 3.514% |  | 13.42% |  | 28.43% |  | 46.96% |  | 64.86% |  | 82.75% |  | 93.93% |  | 99.68% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
154 | Pile Cap |  | 188 | 41 | 2023-12-16 | 2024-01-25 |  |  |  |  | 60.06% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 5.851% |  | 22.34% |  | 47.34% |  | 75% |  | 92.02% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
155 | Excavation |  | 21 | 21 | 2023-12-16 | 2024-01-05 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 28.5714 | 28.57% | 61.9048 | 61.9% | 95.2381 | 95.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
156 | Leveling and Compaction |  | 21 | 21 | 2023-12-19 | 2024-01-08 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 47.619 | 47.62% | 80.9524 | 80.95% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
157 | Lean Concrete Pouring |  | 21 | 21 | 2023-12-20 | 2024-01-09 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 9.5238 | 9.524% | 42.8571 | 42.86% | 76.1905 | 76.19% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
158 | Pile Cutting and Treatment |  | 21 | 21 | 2023-12-22 | 2024-01-11 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
159 | Reinforcement Bar Fixing |  | 21 | 21 | 2023-12-26 | 2024-01-15 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 47.619 | 47.62% | 80.9524 | 80.95% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
160 | Formwork Fixing |  | 21 | 21 | 2023-12-29 | 2024-01-18 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
161 | Concrete Pouring |  | 20 | 20 | 2024-01-01 | 2024-01-20 | 100 | 100 | % | 100 | 10.64% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 20 | 20% | 55 | 55% | 90 | 90% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
162 | Formwork Dismantling |  | 21 | 21 | 2024-01-04 | 2024-01-24 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4.7619 | 4.762% | 38.0952 | 38.1% | 71.4286 | 71.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
163 | Backfill with compaction |  | 21 | 21 | 2024-01-05 | 2024-01-25 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
164 | Completion of Pile Cap |  | 0 | 1 | 2024-01-25 | 2024-01-25 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
165 | Stump |  | 125 | 33 | 2024-01-08 | 2024-02-09 |  |  |  |  | 39.94% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 4.8% |  | 24% |  | 56.8% |  | 84.8% |  | 99.2% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
166 | Reinforcement Bar Fixing |  | 20 | 20 | 2024-01-08 | 2024-01-27 | 100 | 100 | % | 100 | 16% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 20 | 20% | 55 | 55% | 90 | 90% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
167 | Formwork Fixing |  | 21 | 21 | 2024-01-10 | 2024-01-30 | 100 | 100 | % | 100 | 16.8% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 9.5238 | 9.524% | 42.8571 | 42.86% | 76.1905 | 76.19% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
168 | Anchor Bolt Fixing |  | 21 | 21 | 2024-01-12 | 2024-02-01 | 100 | 100 | % | 100 | 16.8% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
169 | Concrete Pouring |  | 21 | 21 | 2024-01-16 | 2024-02-05 | 100 | 100 | % | 100 | 16.8% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 47.619 | 47.62% | 80.9524 | 80.95% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
170 | Formwork Dismantling |  | 21 | 21 | 2024-01-19 | 2024-02-08 | 100 | 100 | % | 100 | 16.8% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
171 | Backfill with compaction |  | 21 | 21 | 2024-01-20 | 2024-02-09 | 100 | 100 | % | 100 | 16.8% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 28.5714 | 28.57% | 61.9048 | 61.9% | 95.2381 | 95.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
172 | Completion of Stump |  | 0 | 1 | 2024-02-09 | 2024-02-09 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
173 | Completion of Structure |  | 0 | 1 | 2024-02-09 | 2024-02-09 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
174 | Tank / Equipment and Pump Foundation |  | 185 | 42 | 2024-01-05 | 2024-02-15 |  |  |  |  | 22.78% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 8.108% |  | 25.95% |  | 51.89% |  | 75.14% |  | 91.89% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
175 | Tank / Equipment Foundation |  | 185 | 42 | 2024-01-05 | 2024-02-15 |  |  |  |  | 100% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 8.108% |  | 25.95% |  | 51.89% |  | 75.14% |  | 91.89% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
176 | Excavation |  | 19 | 19 | 2024-01-05 | 2024-01-23 | 100 | 100 | % | 100 | 10.27% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 36.8421 | 36.84% | 73.6842 | 73.68% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
177 | Leveling and Compaction |  | 18 | 18 | 2024-01-08 | 2024-01-25 | 100 | 100 | % | 100 | 9.73% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 22.2222 | 22.22% | 61.1111 | 61.11% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
178 | Lean Concrete Pouring |  | 18 | 18 | 2024-01-09 | 2024-01-26 | 100 | 100 | % | 100 | 9.73% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 16.6667 | 16.67% | 55.5556 | 55.56% | 94.4444 | 94.44% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
179 | Pile Cutting and Treatment |  | 19 | 19 | 2024-01-11 | 2024-01-29 | 100 | 100 | % | 100 | 10.27% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5.2632 | 5.263% | 42.1053 | 42.11% | 78.9474 | 78.95% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
180 | Reinforcement Bar Fixing |  | 18 | 18 | 2024-01-15 | 2024-02-01 | 100 | 100 | % | 100 | 9.73% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 22.2222 | 22.22% | 61.1111 | 61.11% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
181 | Formwork Fixing |  | 19 | 19 | 2024-01-18 | 2024-02-05 | 100 | 100 | % | 100 | 10.27% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5.2632 | 5.263% | 42.1053 | 42.11% | 78.9474 | 78.95% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
182 | Anchor Bolt / Inserted Plate Fixing |  | 19 | 19 | 2024-01-20 | 2024-02-07 | 100 | 100 | % | 100 | 10.27% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 31.5789 | 31.58% | 68.4211 | 68.42% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
183 | Concrete Pouring |  | 18 | 18 | 2024-01-24 | 2024-02-10 | 100 | 100 | % | 100 | 9.73% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 11.1111 | 11.11% | 50 | 50% | 88.8889 | 88.89% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
184 | Formwork Dismantling |  | 19 | 19 | 2024-01-27 | 2024-02-14 | 100 | 100 | % | 100 | 10.27% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 31.5789 | 31.58% | 68.4211 | 68.42% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
185 | Backfill with compaction |  | 18 | 18 | 2024-01-29 | 2024-02-15 | 100 | 100 | % | 100 | 9.73% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 22.2222 | 22.22% | 61.1111 | 61.11% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
186 | Completion of Tank / Equipment |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
187 | Completion of Tank / Equipment and Pump Foundation |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
188 | General |  | 314 | 58 | 2023-12-20 | 2024-02-15 |  |  |  |  | 38.67% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.6369% |  | 7.962% |  | 20.38% |  | 37.9% |  | 56.37% |  | 74.52% |  | 87.9% |  | 95.54% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
189 | Pipe Gallery |  | 188 | 56 | 2023-12-20 | 2024-02-13 |  |  |  |  | 59.87% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 1.064% |  | 13.3% |  | 34.04% |  | 62.77% |  | 84.04% |  | 96.81% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
190 | Pile Cap |  | 188 | 41 | 2023-12-20 | 2024-01-29 |  |  |  |  | 100% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 1.064% |  | 13.3% |  | 34.04% |  | 62.77% |  | 84.04% |  | 96.81% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
191 | Excavation |  | 21 | 21 | 2023-12-20 | 2024-01-09 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 9.5238 | 9.524% | 42.8571 | 42.86% | 76.1905 | 76.19% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
192 | Leveling and Compaction |  | 21 | 21 | 2023-12-22 | 2024-01-11 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
193 | Lean Concrete Pouring |  | 21 | 21 | 2023-12-23 | 2024-01-12 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 28.5714 | 28.57% | 61.9048 | 61.9% | 95.2381 | 95.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
194 | Pile Cutting and Treatment |  | 21 | 21 | 2023-12-26 | 2024-01-15 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 47.619 | 47.62% | 80.9524 | 80.95% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
195 | Reinforcement Bar Fixing |  | 21 | 21 | 2023-12-29 | 2024-01-18 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
196 | Formwork Fixing |  | 21 | 21 | 2024-01-02 | 2024-01-22 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 47.619 | 47.62% | 80.9524 | 80.95% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
197 | Concrete Pouring |  | 21 | 21 | 2024-01-04 | 2024-01-24 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4.7619 | 4.762% | 38.0952 | 38.1% | 71.4286 | 71.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
198 | Formwork Dismantling |  | 20 | 20 | 2024-01-08 | 2024-01-27 | 100 | 100 | % | 100 | 10.64% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 20 | 20% | 55 | 55% | 90 | 90% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
199 | Backfill with compaction |  | 21 | 21 | 2024-01-09 | 2024-01-29 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 47.619 | 47.62% | 80.9524 | 80.95% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
200 | Completion of Pile Cap |  | 0 | 1 | 2024-01-29 | 2024-01-29 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
201 | Completion of Pipe Gallery |  | 0 | 1 | 2024-02-13 | 2024-02-13 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
202 | Tank Yard Slab with Cofferdam |  | 126 | 36 | 2024-01-11 | 2024-02-15 |  |  |  |  | 40.13% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.7937% |  | 15.08% |  | 41.27% |  | 69.84% |  | 88.89% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
203 | Tank Yard Slab |  | 98 | 31 | 2024-01-11 | 2024-02-10 |  |  |  |  | 77.78% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 1.02% |  | 19.39% |  | 53.06% |  | 83.67% |  | 97.96% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
204 | Leveling and Compaction |  | 14 | 14 | 2024-01-11 | 2024-01-24 | 100 | 100 | % | 100 | 14.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.1429 | 7.143% | 57.1429 | 57.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
205 | Sub Base Laying and Compaction |  | 14 | 14 | 2024-01-13 | 2024-01-26 | 100 | 100 | % | 100 | 14.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 92.8571 | 92.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
206 | Lean Concrete Pouring |  | 14 | 14 | 2024-01-16 | 2024-01-29 | 100 | 100 | % | 100 | 14.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 21.4286 | 21.43% | 71.4286 | 71.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
207 | Reinforcement Bar Fixing |  | 14 | 14 | 2024-01-17 | 2024-01-30 | 100 | 100 | % | 100 | 14.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 64.2857 | 64.29% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
208 | Formwork Fixing |  | 13 | 13 | 2024-01-22 | 2024-02-03 | 100 | 100 | % | 100 | 13.27% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 30.7692 | 30.77% | 84.6154 | 84.62% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
209 | Concrete Pouring |  | 14 | 14 | 2024-01-24 | 2024-02-06 | 100 | 100 | % | 100 | 14.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 64.2857 | 64.29% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
210 | Formwork Dismantling |  | 14 | 14 | 2024-01-27 | 2024-02-09 | 100 | 100 | % | 100 | 14.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 92.8571 | 92.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
211 | Backfill with compaction |  | 1 | 1 | 2024-02-10 | 2024-02-10 | 100 | 100 | % | 100 | 1.02% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
212 | Cofferdam Wall |  | 28 | 20 | 2024-01-27 | 2024-02-15 |  |  |  |  | 22.22% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 21.43% |  | 57.14% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
213 | Reinforcement Bar Fixing |  | 7 | 7 | 2024-01-27 | 2024-02-02 | 100 | 100 | % | 100 | 25% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
214 | Formwork Fixing |  | 7 | 7 | 2024-02-03 | 2024-02-09 | 100 | 100 | % | 100 | 25% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
215 | Concrete Pouring |  | 7 | 7 | 2024-02-06 | 2024-02-12 | 100 | 100 | % | 100 | 25% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
216 | Formwork Dismantling |  | 7 | 7 | 2024-02-09 | 2024-02-15 | 100 | 100 | % | 100 | 25% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
217 | Completion of Tank Yard Slab with Cofferdam |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
218 | Completion of General |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
219 | Completion of Substructure |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
220 | Completion of Unit 700 - Auxillary & Tank Yard |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
221 | Unit 700 - Frame & Auxillary Room |  | 409 | 73 | 2023-12-05 | 2024-02-15 |  |  |  |  | 4.658% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.7335% |  | 2.2% |  | 6.357% |  | 16.14% |  | 29.58% |  | 51.1% |  | 71.15% |  | 86.31% |  | 97.07% |  | 99.27% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
222 | Piling (Cutting only) |  | 9 | 9 | 2023-12-05 | 2023-12-13 |  |  |  |  | 2.2% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 33.33% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
223 | Cutting off Pile to GL |  | 9 | 9 | 2023-12-05 | 2023-12-13 | 100 | 100 | % | 100 | 100% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
224 | Completion of Piling |  | 0 | 1 | 2023-12-13 | 2023-12-13 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
225 | Substructure |  | 400 | 62 | 2023-12-16 | 2024-02-15 |  |  |  |  | 97.8% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 4.25% |  | 14.25% |  | 28% |  | 50% |  | 70.5% |  | 86% |  | 97% |  | 99.25% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
226 | Structure |  | 266 | 62 | 2023-12-16 | 2024-02-15 |  |  |  |  | 66.5% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 4.135% |  | 15.79% |  | 33.46% |  | 58.65% |  | 78.95% |  | 92.48% |  | 99.62% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
227 | Pile Cap |  | 240 | 47 | 2023-12-16 | 2024-01-31 |  |  |  |  | 90.23% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 4.583% |  | 17.5% |  | 37.08% |  | 63.33% |  | 82.92% |  | 95% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
228 | Excavation |  | 27 | 27 | 2023-12-16 | 2024-01-11 | 100 | 100 | % | 100 | 11.25% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 22.2222 | 22.22% | 48.1481 | 48.15% | 74.0741 | 74.07% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
229 | Leveling and Compaction |  | 26 | 26 | 2023-12-19 | 2024-01-13 | 100 | 100 | % | 100 | 10.83% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 11.5385 | 11.54% | 38.4615 | 38.46% | 65.3846 | 65.38% | 92.3077 | 92.31% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
230 | Lean Concrete Pouring |  | 27 | 27 | 2023-12-20 | 2024-01-15 | 100 | 100 | % | 100 | 11.25% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.4074 | 7.407% | 33.3333 | 33.33% | 59.2593 | 59.26% | 85.1852 | 85.19% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
231 | Pile Cutting and Treatment |  | 27 | 27 | 2023-12-22 | 2024-01-17 | 100 | 100 | % | 100 | 11.25% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 25.9259 | 25.93% | 51.8519 | 51.85% | 77.7778 | 77.78% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
232 | Reinforcement Bar Fixing |  | 26 | 26 | 2023-12-26 | 2024-01-20 | 100 | 100 | % | 100 | 10.83% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 11.5385 | 11.54% | 38.4615 | 38.46% | 65.3846 | 65.38% | 92.3077 | 92.31% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
233 | Formwork Fixing |  | 27 | 27 | 2023-12-29 | 2024-01-24 | 100 | 100 | % | 100 | 11.25% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 25.9259 | 25.93% | 51.8519 | 51.85% | 77.7778 | 77.78% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
234 | Concrete Pouring |  | 26 | 26 | 2024-01-01 | 2024-01-26 | 100 | 100 | % | 100 | 10.83% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 15.3846 | 15.38% | 42.3077 | 42.31% | 69.2308 | 69.23% | 96.1538 | 96.15% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
235 | Formwork Dismantling |  | 27 | 27 | 2024-01-04 | 2024-01-30 | 100 | 100 | % | 100 | 11.25% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 3.7037 | 3.704% | 29.6296 | 29.63% | 55.5556 | 55.56% | 81.4815 | 81.48% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
236 | Backfill with compaction |  | 27 | 27 | 2024-01-05 | 2024-01-31 | 100 | 100 | % | 100 | 11.25% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 25.9259 | 25.93% | 51.8519 | 51.85% | 77.7778 | 77.78% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
237 | Completion of Pile Cap |  | 0 | 1 | 2024-01-31 | 2024-01-31 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
238 | Stump | Reinforcement Bar only | 26 | 39 | 2024-01-08 | 2024-02-15 |  |  |  |  | 9.774% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 15.38% |  | 42.31% |  | 69.23% |  | 96.15% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
239 | Reinforcement Bar Fixing |  | 26 | 26 | 2024-01-08 | 2024-02-02 | 100 | 100 | % | 100 | 100% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 15.3846 | 15.38% | 42.3077 | 42.31% | 69.2308 | 69.23% | 96.1538 | 96.15% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
240 | Completion of Stump |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
241 | Completion of Structure |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
242 | Underground Pits (RV 7903 and 7902) |  | 54 | 62 | 2023-12-16 | 2024-02-15 |  |  |  |  | 13.5% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 11.11% |  | 27.78% |  | 42.59% |  | 53.7% |  | 64.81% |  | 77.78% |  | 90.74% |  | 94.44% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
243 | Temporary Sheet Pile |  | 6 | 6 | 2023-12-16 | 2023-12-21 | 100 | 100 | % | 100 | 11.11% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
244 | Excavation |  | 15 | 15 | 2023-12-22 | 2024-01-05 | 100 | 100 | % | 100 | 27.78% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 46.6667 | 46.67% | 93.3333 | 93.33% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
245 | Leveling and Compaction |  | 3 | 3 | 2023-12-27 | 2023-12-29 | 100 | 100 | % | 100 | 5.556% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
246 | Lean Concrete Pouring |  | 1 | 1 | 2024-01-06 | 2024-01-06 | 100 | 100 | % | 100 | 1.852% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
247 | Base |  | 7 | 8 | 2024-01-08 | 2024-01-15 |  |  |  |  | 12.96% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 57.14% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
248 | Reinforcement Bar Fixing |  | 4 | 4 | 2024-01-08 | 2024-01-11 | 100 | 100 | % | 100 | 57.14% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
249 | Formwork Fixing |  | 2 | 2 | 2024-01-12 | 2024-01-13 | 100 | 100 | % | 100 | 28.57% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
250 | Concrete Pouring |  | 1 | 1 | 2024-01-15 | 2024-01-15 | 100 | 100 | % | 100 | 14.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
251 | Wall |  | 19 | 19 | 2024-01-16 | 2024-02-03 |  |  |  |  | 35.19% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 15.79% |  | 52.63% |  | 89.47% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
252 | Reinforcement Bar Fixing |  | 9 | 9 | 2024-01-16 | 2024-01-24 | 100 | 100 | % | 100 | 47.37% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
253 | Formwork Fixing |  | 9 | 9 | 2024-01-25 | 2024-02-02 | 100 | 100 | % | 100 | 47.37% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 11.1111 | 11.11% | 88.8889 | 88.89% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
254 | Concrete Pouring |  | 1 | 1 | 2024-02-03 | 2024-02-03 | 100 | 100 | % | 100 | 5.263% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
255 | Formwork Dismantling |  | 1 | 1 | 2024-02-13 | 2024-02-13 | 100 | 100 | % | 100 | 1.852% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
256 | Backfill with compaction |  | 2 | 2 | 2024-02-14 | 2024-02-15 | 100 | 100 | % | 100 | 3.704% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
257 | Completion of Underground Pits |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
258 | Tank / Equipment and Pump Foundation |  | 80 | 42 | 2024-01-05 | 2024-02-15 |  |  |  |  | 20% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 18.75% |  | 46.25% |  | 70% |  | 92.5% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
259 | Tank / Equipment Foundation |  | 80 | 32 | 2024-01-05 | 2024-02-15 |  |  |  |  | 100% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 18.75% |  | 46.25% |  | 70% |  | 92.5% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
260 | Excavation |  | 32 | 32 | 2024-01-05 | 2024-01-27 | 100 | 100 | % | 100 | 40% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 21.875 | 21.88% | 43.75 | 43.75% | 65.625 | 65.62% | 87.5 | 87.5% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
261 | Leveling and Compaction |  | 5 | 5 | 2024-01-08 | 2024-01-30 | 100 | 100 | % | 100 | 6.25% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 80 | 80% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
262 | Lean Concrete Pouring |  | 7 | 7 | 2024-01-09 | 2024-01-31 | 100 | 100 | % | 100 | 8.75% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
263 | Pile Cutting and Treatment |  | 6 | 6 | 2024-01-11 | 2024-02-02 | 100 | 100 | % | 100 | 7.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 16.6667 | 16.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
264 | Reinforcement Bar Fixing |  | 4 | 4 | 2024-01-15 | 2024-02-06 | 100 | 100 | % | 100 | 5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
265 | Formwork Fixing |  | 5 | 5 | 2024-01-18 | 2024-02-09 | 100 | 100 | % | 100 | 6.25% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 20 | 20% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
266 | Anchor Bolt / Inserted Plate Fixing |  | 6 | 6 | 2024-01-20 | 2024-02-12 | 100 | 100 | % | 100 | 7.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
267 | Concrete Pouring |  | 4 | 4 | 2024-01-24 | 2024-02-15 | 100 | 100 | % | 100 | 5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 50 | 50% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
268 | Formwork Dismantling |  | 5 | 5 | 2024-01-27 | 2024-02-15 | 100 | 100 | % | 100 | 6.25% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
269 | Backfill with compaction |  | 6 | 6 | 2024-01-29 | 2024-02-15 | 100 | 100 | % | 100 | 7.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
270 | Completion of Tank / Equipment |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
271 | Completion of Tank / Equipment and Pump Foundation |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
272 | Completion of Substructure |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
273 | Completion of Unit 700 - Frame & Auxillary Room |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
274 | Unit 800 - Compressor Shed |  | 1429 | 92 | 2023-11-29 | 2024-02-28 |  |  |  |  | 16.27% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.14% |  | 1.54% |  | 6.508% |  | 14.91% |  | 27.92% |  | 43.39% |  | 58.29% |  | 72.15% |  | 82.02% |  | 89.43% |  | 94.19% |  | 97.2% |  | 99.16% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
275 | Piling (Cutting only) |  | 21 | 21 | 2023-11-29 | 2023-12-19 |  |  |  |  | 1.47% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 9.524% |  | 42.86% |  | 76.19% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
276 | Cutting off Pile to GL |  | 21 | 21 | 2023-11-29 | 2023-12-19 | 100 | 100 | % | 100 | 100% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 9.5238 | 9.524% | 42.8571 | 42.86% | 76.1905 | 76.19% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
277 | Completion of Piling |  | 0 | 1 | 2023-12-19 | 2023-12-19 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
278 | Substructure |  | 1408 | 89 | 2023-12-02 | 2024-02-28 |  |  |  |  | 98.53% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.9233% |  | 5.469% |  | 13.64% |  | 26.85% |  | 42.54% |  | 57.67% |  | 71.73% |  | 81.75% |  | 89.28% |  | 94.11% |  | 97.16% |  | 99.15% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
279 | Structure |  | 642 | 63 | 2023-12-02 | 2024-02-02 |  |  |  |  | 45.6% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 2.025% |  | 10.28% |  | 23.36% |  | 42.68% |  | 62.93% |  | 79.6% |  | 91.43% |  | 97.04% |  | 99.84% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
280 | Pile Cap |  | 251 | 48 | 2023-12-02 | 2024-01-18 |  |  |  |  | 39.1% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 4.382% |  | 16.73% |  | 35.46% |  | 60.56% |  | 81.27% |  | 94.02% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
281 | Excavation |  | 28 | 28 | 2023-12-02 | 2023-12-29 | 100 | 100 | % | 100 | 11.16% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 21.4286 | 21.43% | 46.4286 | 46.43% | 71.4286 | 71.43% | 96.4286 | 96.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
282 | Leveling and Compaction |  | 28 | 28 | 2023-12-05 | 2024-01-01 | 100 | 100 | % | 100 | 11.16% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 10.7143 | 10.71% | 35.7143 | 35.71% | 60.7143 | 60.71% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
283 | Lean Concrete Pouring |  | 28 | 28 | 2023-12-06 | 2024-01-02 | 100 | 100 | % | 100 | 11.16% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.1429 | 7.143% | 32.1429 | 32.14% | 57.1429 | 57.14% | 82.1429 | 82.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
284 | Pile Cutting and Treatment |  | 28 | 28 | 2023-12-08 | 2024-01-04 | 100 | 100 | % | 100 | 11.16% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 25 | 25% | 50 | 50% | 75 | 75% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
285 | Reinforcement Bar Fixing |  | 28 | 28 | 2023-12-12 | 2024-01-08 | 100 | 100 | % | 100 | 11.16% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 10.7143 | 10.71% | 35.7143 | 35.71% | 60.7143 | 60.71% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
286 | Formwork Fixing |  | 28 | 28 | 2023-12-15 | 2024-01-11 | 100 | 100 | % | 100 | 11.16% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 25 | 25% | 50 | 50% | 75 | 75% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
287 | Concrete Pouring |  | 27 | 27 | 2023-12-18 | 2024-01-13 | 100 | 100 | % | 100 | 10.76% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.8148 | 14.81% | 40.7407 | 40.74% | 66.6667 | 66.67% | 92.5926 | 92.59% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
288 | Formwork Dismantling |  | 28 | 28 | 2023-12-21 | 2024-01-17 | 100 | 100 | % | 100 | 11.16% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 3.5714 | 3.571% | 28.5714 | 28.57% | 53.5714 | 53.57% | 78.5714 | 78.57% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
289 | Backfill with compaction |  | 28 | 28 | 2023-12-22 | 2024-01-18 | 100 | 100 | % | 100 | 11.16% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 25 | 25% | 50 | 50% | 75 | 75% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
290 | Completion of Pile Cap |  | 0 | 1 | 2024-01-18 | 2024-01-18 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
291 | Stump |  | 167 | 40 | 2023-12-25 | 2024-02-02 |  |  |  |  | 26.01% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 3.593% |  | 17.96% |  | 42.51% |  | 67.66% |  | 88.62% |  | 99.4% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
292 | Reinforcement Bar Fixing |  | 27 | 27 | 2023-12-25 | 2024-01-20 | 100 | 100 | % | 100 | 16.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.8148 | 14.81% | 40.7407 | 40.74% | 66.6667 | 66.67% | 92.5926 | 92.59% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
293 | Formwork Fixing |  | 28 | 28 | 2023-12-27 | 2024-01-23 | 100 | 100 | % | 100 | 16.77% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.1429 | 7.143% | 32.1429 | 32.14% | 57.1429 | 57.14% | 82.1429 | 82.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
294 | Anchor Bolt Fixing |  | 28 | 28 | 2023-12-29 | 2024-01-25 | 100 | 100 | % | 100 | 16.77% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 25 | 25% | 50 | 50% | 75 | 75% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
295 | Concrete Pouring |  | 28 | 28 | 2024-01-02 | 2024-01-29 | 100 | 100 | % | 100 | 16.77% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 10.7143 | 10.71% | 35.7143 | 35.71% | 60.7143 | 60.71% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
296 | Formwork Dismantling |  | 28 | 28 | 2024-01-05 | 2024-02-01 | 100 | 100 | % | 100 | 16.77% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 25 | 25% | 50 | 50% | 75 | 75% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
297 | Backfill with compaction |  | 28 | 28 | 2024-01-06 | 2024-02-02 | 100 | 100 | % | 100 | 16.77% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 21.4286 | 21.43% | 46.4286 | 46.43% | 71.4286 | 71.43% | 96.4286 | 96.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
298 | Completion of Stump |  | 0 | 1 | 2024-02-02 | 2024-02-02 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
299 | Ground Beam |  | 224 | 45 | 2023-12-06 | 2024-01-19 |  |  |  |  | 34.89% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.8929% |  | 10.71% |  | 27.23% |  | 51.79% |  | 75.89% |  | 91.07% |  | 99.55% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
300 | Excavation |  | 28 | 28 | 2023-12-06 | 2024-01-02 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.1429 | 7.143% | 32.1429 | 32.14% | 57.1429 | 57.14% | 82.1429 | 82.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
301 | Leveling and Compaction |  | 28 | 28 | 2023-12-08 | 2024-01-04 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 25 | 25% | 50 | 50% | 75 | 75% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
302 | Lean Concrete Pouring |  | 28 | 28 | 2023-12-09 | 2024-01-05 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 21.4286 | 21.43% | 46.4286 | 46.43% | 71.4286 | 71.43% | 96.4286 | 96.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
303 | Reinforcement Bar Fixing |  | 28 | 28 | 2023-12-13 | 2024-01-09 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.1429 | 7.143% | 32.1429 | 32.14% | 57.1429 | 57.14% | 82.1429 | 82.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
304 | Formwork Fixing |  | 28 | 28 | 2023-12-16 | 2024-01-12 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 21.4286 | 21.43% | 46.4286 | 46.43% | 71.4286 | 71.43% | 96.4286 | 96.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
305 | Concrete Pouring |  | 28 | 28 | 2023-12-19 | 2024-01-15 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 10.7143 | 10.71% | 35.7143 | 35.71% | 60.7143 | 60.71% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
306 | Formwork Dismantling |  | 28 | 28 | 2023-12-22 | 2024-01-18 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 25 | 25% | 50 | 50% | 75 | 75% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
307 | Backfill with compaction |  | 28 | 28 | 2023-12-23 | 2024-01-19 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 21.4286 | 21.43% | 46.4286 | 46.43% | 71.4286 | 71.43% | 96.4286 | 96.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
308 | Completion of Ground Beam |  | 0 | 1 | 2024-01-19 | 2024-01-19 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
309 | Completion of Structure |  | 0 | 1 | 2024-02-02 | 2024-02-02 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
310 | Compressor / Equipment Foundation |  | 453 | 69 | 2023-12-22 | 2024-02-28 |  |  |  |  | 32.17% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 3.311% |  | 10.6% |  | 21.63% |  | 36.2% |  | 51.66% |  | 67.11% |  | 81.68% |  | 91.17% |  | 97.35% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
311 | Equipment Foundation |  | 453 | 69 | 2023-12-22 | 2024-02-28 |  |  |  |  | 100% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 3.311% |  | 10.6% |  | 21.63% |  | 36.2% |  | 51.66% |  | 67.11% |  | 81.68% |  | 91.17% |  | 97.35% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
312 | Excavation |  | 46 | 46 | 2023-12-22 | 2024-02-05 | 100 | 100 | % | 100 | 10.15% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 15.2174 | 15.22% | 30.4348 | 30.43% | 45.6522 | 45.65% | 60.8696 | 60.87% | 76.087 | 76.09% | 91.3043 | 91.3% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
313 | Leveling and Compaction |  | 45 | 45 | 2023-12-25 | 2024-02-07 | 100 | 100 | % | 100 | 9.934% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 8.8889 | 8.889% | 24.4444 | 24.44% | 40 | 40% | 55.5556 | 55.56% | 71.1111 | 71.11% | 86.6667 | 86.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
314 | Lean Concrete Pouring |  | 45 | 45 | 2023-12-26 | 2024-02-08 | 100 | 100 | % | 100 | 9.934% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 6.6667 | 6.667% | 22.2222 | 22.22% | 37.7778 | 37.78% | 53.3333 | 53.33% | 68.8889 | 68.89% | 84.4444 | 84.44% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
315 | Pile Cutting and Treatment |  | 45 | 45 | 2023-12-28 | 2024-02-10 | 100 | 100 | % | 100 | 9.934% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 2.2222 | 2.222% | 17.7778 | 17.78% | 33.3333 | 33.33% | 48.8889 | 48.89% | 64.4444 | 64.44% | 80 | 80% | 95.5556 | 95.56% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
316 | Reinforcement Bar Fixing |  | 45 | 45 | 2024-01-01 | 2024-02-14 | 100 | 100 | % | 100 | 9.934% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 8.8889 | 8.889% | 24.4444 | 24.44% | 40 | 40% | 55.5556 | 55.56% | 71.1111 | 71.11% | 86.6667 | 86.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
317 | Formwork Fixing |  | 45 | 45 | 2024-01-04 | 2024-02-17 | 100 | 100 | % | 100 | 9.934% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 2.2222 | 2.222% | 17.7778 | 17.78% | 33.3333 | 33.33% | 48.8889 | 48.89% | 64.4444 | 64.44% | 80 | 80% | 95.5556 | 95.56% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
318 | Anchor Bolt / Inserted Plate Fixing |  | 46 | 46 | 2024-01-06 | 2024-02-20 | 100 | 100 | % | 100 | 10.15% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 13.0435 | 13.04% | 28.2609 | 28.26% | 43.4783 | 43.48% | 58.6957 | 58.7% | 73.913 | 73.91% | 89.1304 | 89.13% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
319 | Concrete Pouring |  | 45 | 45 | 2024-01-10 | 2024-02-23 | 100 | 100 | % | 100 | 9.934% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4.4444 | 4.444% | 20 | 20% | 35.5556 | 35.56% | 51.1111 | 51.11% | 66.6667 | 66.67% | 82.2222 | 82.22% | 97.7778 | 97.78% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
320 | Formwork Dismantling |  | 46 | 46 | 2024-01-13 | 2024-02-27 | 100 | 100 | % | 100 | 10.15% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 13.0435 | 13.04% | 28.2609 | 28.26% | 43.4783 | 43.48% | 58.6957 | 58.7% | 73.913 | 73.91% | 89.1304 | 89.13% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
321 | Backfill with compaction |  | 45 | 45 | 2024-01-15 | 2024-02-28 | 100 | 100 | % | 100 | 9.934% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 8.8889 | 8.889% | 24.4444 | 24.44% | 40 | 40% | 55.5556 | 55.56% | 71.1111 | 71.11% | 86.6667 | 86.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
322 | Completion of Equipment Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
323 | Completion of Compressor / Equipment and Pump Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
324 | General |  | 313 | 56 | 2023-12-09 | 2024-02-02 |  |  |  |  | 22.23% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 3.514% |  | 13.42% |  | 28.43% |  | 46.96% |  | 64.86% |  | 82.75% |  | 93.93% |  | 99.68% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
325 | Pipe Gallery |  | 313 | 56 | 2023-12-09 | 2024-02-02 |  |  |  |  | 100% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 3.514% |  | 13.42% |  | 28.43% |  | 46.96% |  | 64.86% |  | 82.75% |  | 93.93% |  | 99.68% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
326 | Pile Cap |  | 188 | 41 | 2023-12-09 | 2024-01-18 |  |  |  |  | 60.06% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 5.851% |  | 22.34% |  | 47.34% |  | 75% |  | 92.02% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
327 | Excavation |  | 21 | 21 | 2023-12-09 | 2023-12-29 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 28.5714 | 28.57% | 61.9048 | 61.9% | 95.2381 | 95.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
328 | Leveling and Compaction |  | 21 | 21 | 2023-12-12 | 2024-01-01 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 47.619 | 47.62% | 80.9524 | 80.95% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
329 | Lean Concrete Pouring |  | 21 | 21 | 2023-12-13 | 2024-01-02 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 9.5238 | 9.524% | 42.8571 | 42.86% | 76.1905 | 76.19% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
330 | Pile Cutting and Treatment |  | 21 | 21 | 2023-12-15 | 2024-01-04 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
331 | Reinforcement Bar Fixing |  | 21 | 21 | 2023-12-19 | 2024-01-08 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 47.619 | 47.62% | 80.9524 | 80.95% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
332 | Formwork Fixing |  | 21 | 21 | 2023-12-22 | 2024-01-11 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
333 | Concrete Pouring |  | 20 | 20 | 2023-12-25 | 2024-01-13 | 100 | 100 | % | 100 | 10.64% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 20 | 20% | 55 | 55% | 90 | 90% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
334 | Formwork Dismantling |  | 21 | 21 | 2023-12-28 | 2024-01-17 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4.7619 | 4.762% | 38.0952 | 38.1% | 71.4286 | 71.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
335 | Backfill with compaction |  | 21 | 21 | 2023-12-29 | 2024-01-18 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
336 | Completion of Pile Cap |  | 0 | 1 | 2024-01-18 | 2024-01-18 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
337 | Stump |  | 125 | 33 | 2024-01-01 | 2024-02-02 |  |  |  |  | 39.94% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 4.8% |  | 24% |  | 56.8% |  | 84.8% |  | 99.2% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
338 | Reinforcement Bar Fixing |  | 20 | 20 | 2024-01-01 | 2024-01-20 | 100 | 100 | % | 100 | 16% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 20 | 20% | 55 | 55% | 90 | 90% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
339 | Formwork Fixing |  | 21 | 21 | 2024-01-03 | 2024-01-23 | 100 | 100 | % | 100 | 16.8% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 9.5238 | 9.524% | 42.8571 | 42.86% | 76.1905 | 76.19% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
340 | Anchor Bolt Fixing |  | 21 | 21 | 2024-01-05 | 2024-01-25 | 100 | 100 | % | 100 | 16.8% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
341 | Concrete Pouring |  | 21 | 21 | 2024-01-09 | 2024-01-29 | 100 | 100 | % | 100 | 16.8% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 47.619 | 47.62% | 80.9524 | 80.95% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
342 | Formwork Dismantling |  | 21 | 21 | 2024-01-12 | 2024-02-01 | 100 | 100 | % | 100 | 16.8% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
343 | Backfill with compaction |  | 21 | 21 | 2024-01-13 | 2024-02-02 | 100 | 100 | % | 100 | 16.8% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 28.5714 | 28.57% | 61.9048 | 61.9% | 95.2381 | 95.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
344 | Completion of Stump |  | 0 | 1 | 2024-02-02 | 2024-02-02 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
345 | Completion of Pipe Gallery |  | 0 | 1 | 2024-02-02 | 2024-02-02 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
346 | Completion of General |  | 0 | 1 | 2024-02-02 | 2024-02-02 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
347 | Completion of Substructure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
348 | Completion of Unit 800 - Compressor Shed |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
349 | Unit 800 - Desulfurization Frame |  | 697 | 85 | 2023-12-06 | 2024-02-28 |  |  |  |  | 7.938% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.2869% |  | 2.439% |  | 9.182% |  | 19.08% |  | 30.7% |  | 44.05% |  | 56.24% |  | 68.15% |  | 78.62% |  | 88.09% |  | 94.26% |  | 98.28% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
350 | Piling (Cutting only) |  | 9 | 9 | 2023-12-06 | 2023-12-14 |  |  |  |  | 1.291% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 22.22% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
351 | Cutting off Pile to GL |  | 9 | 9 | 2023-12-06 | 2023-12-14 | 100 | 100 | % | 100 | 100% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 22.2222 | 22.22% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
352 | Completion of Piling |  | 0 | 1 | 2023-12-14 | 2023-12-14 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
353 | Substructure |  | 688 | 80 | 2023-12-11 | 2024-02-28 |  |  |  |  | 98.71% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 1.163% |  | 7.994% |  | 18.02% |  | 29.8% |  | 43.31% |  | 55.67% |  | 67.73% |  | 78.34% |  | 87.94% |  | 94.19% |  | 98.26% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
354 | Structure |  | 317 | 48 | 2023-12-11 | 2024-01-27 |  |  |  |  | 46.08% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 2.524% |  | 17.35% |  | 39.12% |  | 61.2% |  | 80.76% |  | 92.74% |  | 99.05% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
355 | Pile Cap |  | 125 | 33 | 2023-12-11 | 2024-01-12 |  |  |  |  | 39.43% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 5.6% |  | 28.8% |  | 57.6% |  | 84% |  | 99.2% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
356 | Excavation |  | 13 | 13 | 2023-12-11 | 2023-12-23 | 100 | 100 | % | 100 | 10.4% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 30.7692 | 30.77% | 84.6154 | 84.62% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
357 | Leveling and Compaction |  | 14 | 14 | 2023-12-13 | 2023-12-26 | 100 | 100 | % | 100 | 11.2% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 64.2857 | 64.29% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
358 | Lean Concrete Pouring |  | 14 | 14 | 2023-12-14 | 2023-12-27 | 100 | 100 | % | 100 | 11.2% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.1429 | 7.143% | 57.1429 | 57.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
359 | Pile Cutting and Treatment |  | 14 | 14 | 2023-12-16 | 2023-12-29 | 100 | 100 | % | 100 | 11.2% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 92.8571 | 92.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
360 | Reinforcement Bar Fixing |  | 14 | 14 | 2023-12-20 | 2024-01-02 | 100 | 100 | % | 100 | 11.2% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 64.2857 | 64.29% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
361 | Formwork Fixing |  | 14 | 14 | 2023-12-23 | 2024-01-05 | 100 | 100 | % | 100 | 11.2% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 92.8571 | 92.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
362 | Concrete Pouring |  | 14 | 14 | 2023-12-26 | 2024-01-08 | 100 | 100 | % | 100 | 11.2% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 21.4286 | 21.43% | 71.4286 | 71.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
363 | Formwork Dismantling |  | 14 | 14 | 2023-12-29 | 2024-01-11 | 100 | 100 | % | 100 | 11.2% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 50 | 50% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
364 | Backfill with compaction |  | 14 | 14 | 2023-12-30 | 2024-01-12 | 100 | 100 | % | 100 | 11.2% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 92.8571 | 92.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
365 | Completion of Pile Cap |  | 0 | 1 | 2024-01-12 | 2024-01-12 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
366 | Stump |  | 83 | 26 | 2024-01-02 | 2024-01-27 |  |  |  |  | 26.18% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 4.819% |  | 31.33% |  | 72.29% |  | 96.39% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
367 | Reinforcement Bar Fixing |  | 14 | 14 | 2024-01-02 | 2024-01-15 | 100 | 100 | % | 100 | 16.87% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 21.4286 | 21.43% | 71.4286 | 71.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
368 | Formwork Fixing |  | 14 | 14 | 2024-01-04 | 2024-01-17 | 100 | 100 | % | 100 | 16.87% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.1429 | 7.143% | 57.1429 | 57.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
369 | Anchor Bolt Fixing |  | 14 | 14 | 2024-01-06 | 2024-01-19 | 100 | 100 | % | 100 | 16.87% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 92.8571 | 92.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
370 | Concrete Pouring |  | 14 | 14 | 2024-01-10 | 2024-01-23 | 100 | 100 | % | 100 | 16.87% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 64.2857 | 64.29% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
371 | Formwork Dismantling |  | 14 | 14 | 2024-01-13 | 2024-01-26 | 100 | 100 | % | 100 | 16.87% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 92.8571 | 92.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
372 | Backfill with compaction |  | 13 | 13 | 2024-01-15 | 2024-01-27 | 100 | 100 | % | 100 | 15.66% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 30.7692 | 30.77% | 84.6154 | 84.62% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
373 | Completion of Stump |  | 0 | 1 | 2024-01-27 | 2024-01-27 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
374 | Ground Beam |  | 109 | 31 | 2023-12-14 | 2024-01-13 |  |  |  |  | 34.38% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.9174% |  | 17.43% |  | 47.71% |  | 77.98% |  | 97.25% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
375 | Excavation |  | 14 | 14 | 2023-12-14 | 2023-12-27 | 100 | 100 | % | 100 | 12.84% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.1429 | 7.143% | 57.1429 | 57.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
376 | Leveling and Compaction |  | 14 | 14 | 2023-12-16 | 2023-12-29 | 100 | 100 | % | 100 | 12.84% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 92.8571 | 92.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
377 | Lean Concrete Pouring |  | 13 | 13 | 2023-12-18 | 2023-12-30 | 100 | 100 | % | 100 | 11.93% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 30.7692 | 30.77% | 84.6154 | 84.62% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
378 | Reinforcement Bar Fixing |  | 14 | 14 | 2023-12-21 | 2024-01-03 | 100 | 100 | % | 100 | 12.84% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.1429 | 7.143% | 57.1429 | 57.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
379 | Formwork Fixing |  | 13 | 13 | 2023-12-25 | 2024-01-06 | 100 | 100 | % | 100 | 11.93% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 30.7692 | 30.77% | 84.6154 | 84.62% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
380 | Concrete Pouring |  | 14 | 14 | 2023-12-27 | 2024-01-09 | 100 | 100 | % | 100 | 12.84% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 64.2857 | 64.29% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
381 | Formwork Dismantling |  | 14 | 14 | 2023-12-30 | 2024-01-12 | 100 | 100 | % | 100 | 12.84% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 92.8571 | 92.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
382 | Backfill with compaction |  | 13 | 13 | 2024-01-01 | 2024-01-13 | 100 | 100 | % | 100 | 11.93% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 30.7692 | 30.77% | 84.6154 | 84.62% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
383 | Completion of Ground Beam |  | 0 | 1 | 2024-01-13 | 2024-01-13 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
384 | Completion of Structure |  | 0 | 1 | 2024-01-27 | 2024-01-27 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
385 | Equipment Foundation |  | 371 | 61 | 2023-12-30 | 2024-02-28 |  |  |  |  | 53.92% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 2.965% |  | 11.32% |  | 23.99% |  | 40.97% |  | 59.84% |  | 77.63% |  | 89.22% |  | 96.77% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
386 | Equipment Foundation |  | 371 | 61 | 2023-12-30 | 2024-02-28 |  |  |  |  | 100% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 2.965% |  | 11.32% |  | 23.99% |  | 40.97% |  | 59.84% |  | 77.63% |  | 89.22% |  | 96.77% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
387 | Excavation |  | 38 | 38 | 2023-12-30 | 2024-02-05 | 100 | 100 | % | 100 | 10.24% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 15.7895 | 15.79% | 34.2105 | 34.21% | 52.6316 | 52.63% | 71.0526 | 71.05% | 89.4737 | 89.47% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
388 | Leveling and Compaction |  | 37 | 37 | 2024-01-02 | 2024-02-07 | 100 | 100 | % | 100 | 9.973% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 8.1081 | 8.108% | 27.027 | 27.03% | 45.9459 | 45.95% | 64.8649 | 64.86% | 83.7838 | 83.78% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
389 | Lean Concrete Pouring |  | 37 | 37 | 2024-01-03 | 2024-02-08 | 100 | 100 | % | 100 | 9.973% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5.4054 | 5.405% | 24.3243 | 24.32% | 43.2432 | 43.24% | 62.1622 | 62.16% | 81.0811 | 81.08% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
390 | Pile Cutting and Treatment |  | 37 | 37 | 2024-01-05 | 2024-02-10 | 100 | 100 | % | 100 | 9.973% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 18.9189 | 18.92% | 37.8378 | 37.84% | 56.7568 | 56.76% | 75.6757 | 75.68% | 94.5946 | 94.59% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
391 | Reinforcement Bar Fixing |  | 37 | 37 | 2024-01-09 | 2024-02-14 | 100 | 100 | % | 100 | 9.973% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 8.1081 | 8.108% | 27.027 | 27.03% | 45.9459 | 45.95% | 64.8649 | 64.86% | 83.7838 | 83.78% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
392 | Formwork Fixing |  | 37 | 37 | 2024-01-12 | 2024-02-17 | 100 | 100 | % | 100 | 9.973% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 18.9189 | 18.92% | 37.8378 | 37.84% | 56.7568 | 56.76% | 75.6757 | 75.68% | 94.5946 | 94.59% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
393 | Anchor Bolt / Inserted Plate Fixing |  | 37 | 37 | 2024-01-15 | 2024-02-20 | 100 | 100 | % | 100 | 9.973% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 10.8108 | 10.81% | 29.7297 | 29.73% | 48.6486 | 48.65% | 67.5676 | 67.57% | 86.4865 | 86.49% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
394 | Concrete Pouring |  | 37 | 37 | 2024-01-18 | 2024-02-23 | 100 | 100 | % | 100 | 9.973% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 2.7027 | 2.703% | 21.6216 | 21.62% | 40.5405 | 40.54% | 59.4595 | 59.46% | 78.3784 | 78.38% | 97.2973 | 97.3% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
395 | Formwork Dismantling |  | 37 | 37 | 2024-01-22 | 2024-02-27 | 100 | 100 | % | 100 | 9.973% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 10.8108 | 10.81% | 29.7297 | 29.73% | 48.6486 | 48.65% | 67.5676 | 67.57% | 86.4865 | 86.49% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
396 | Backfill with compaction |  | 37 | 37 | 2024-01-23 | 2024-02-28 | 100 | 100 | % | 100 | 9.973% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 8.1081 | 8.108% | 27.027 | 27.03% | 45.9459 | 45.95% | 64.8649 | 64.86% | 83.7838 | 83.78% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
397 | Completion of Equipment Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
398 | Completion of Compressor / Equipment and Pump Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
399 | Completion of Substructure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
400 | Completion of Unit 800 - Desulfurization Frame |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
401 | Unit 800 - Distillation Frame |  | 858 | 85 | 2023-12-06 | 2024-02-28 |  |  |  |  | 9.771% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.2331% |  | 1.981% |  | 7.459% |  | 16.55% |  | 30.54% |  | 44.99% |  | 59.56% |  | 71.79% |  | 82.28% |  | 90.33% |  | 95.34% |  | 98.6% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
402 | Piling (Cutting only) |  | 9 | 9 | 2023-12-06 | 2023-12-14 |  |  |  |  | 1.049% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 22.22% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
403 | Cutting off Pile to GL |  | 9 | 9 | 2023-12-06 | 2023-12-14 | 100 | 100 | % | 100 | 100% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 22.2222 | 22.22% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
404 | Completion of Piling |  | 0 | 1 | 2023-12-14 | 2023-12-14 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
405 | Substructure |  | 849 | 80 | 2023-12-11 | 2024-02-28 |  |  |  |  | 98.95% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.9423% |  | 6.478% |  | 15.67% |  | 29.8% |  | 44.41% |  | 59.13% |  | 71.5% |  | 82.1% |  | 90.22% |  | 95.29% |  | 98.59% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
406 | Structure |  | 478 | 55 | 2023-12-11 | 2024-02-03 |  |  |  |  | 56.3% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 1.674% |  | 11.51% |  | 27.82% |  | 50.63% |  | 70.08% |  | 86.4% |  | 95.19% |  | 99.37% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
407 | Pile Cap |  | 188 | 40 | 2023-12-11 | 2024-01-19 |  |  |  |  | 39.33% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 3.723% |  | 19.15% |  | 42.55% |  | 71.28% |  | 89.36% |  | 99.47% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
408 | Excavation |  | 20 | 20 | 2023-12-11 | 2023-12-30 | 100 | 100 | % | 100 | 10.64% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 20 | 20% | 55 | 55% | 90 | 90% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
409 | Leveling and Compaction |  | 21 | 21 | 2023-12-13 | 2024-01-02 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 9.5238 | 9.524% | 42.8571 | 42.86% | 76.1905 | 76.19% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
410 | Lean Concrete Pouring |  | 21 | 21 | 2023-12-14 | 2024-01-03 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4.7619 | 4.762% | 38.0952 | 38.1% | 71.4286 | 71.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
411 | Pile Cutting and Treatment |  | 21 | 21 | 2023-12-16 | 2024-01-05 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 28.5714 | 28.57% | 61.9048 | 61.9% | 95.2381 | 95.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
412 | Reinforcement Bar Fixing |  | 21 | 21 | 2023-12-20 | 2024-01-09 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 9.5238 | 9.524% | 42.8571 | 42.86% | 76.1905 | 76.19% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
413 | Formwork Fixing |  | 21 | 21 | 2023-12-23 | 2024-01-12 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 28.5714 | 28.57% | 61.9048 | 61.9% | 95.2381 | 95.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
414 | Concrete Pouring |  | 21 | 21 | 2023-12-26 | 2024-01-15 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 47.619 | 47.62% | 80.9524 | 80.95% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
415 | Formwork Dismantling |  | 21 | 21 | 2023-12-29 | 2024-01-18 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
416 | Backfill with compaction |  | 21 | 21 | 2023-12-30 | 2024-01-19 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 28.5714 | 28.57% | 61.9048 | 61.9% | 95.2381 | 95.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
417 | Completion of Pile Cap |  | 0 | 1 | 2024-01-19 | 2024-01-19 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
418 | Stump |  | 125 | 33 | 2024-01-02 | 2024-02-03 |  |  |  |  | 26.15% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 3.2% |  | 20.8% |  | 51.2% |  | 81.6% |  | 97.6% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
419 | Reinforcement Bar Fixing |  | 21 | 21 | 2024-01-02 | 2024-01-22 | 100 | 100 | % | 100 | 16.8% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 47.619 | 47.62% | 80.9524 | 80.95% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
420 | Formwork Fixing |  | 21 | 21 | 2024-01-04 | 2024-01-24 | 100 | 100 | % | 100 | 16.8% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4.7619 | 4.762% | 38.0952 | 38.1% | 71.4286 | 71.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
421 | Anchor Bolt Fixing |  | 21 | 21 | 2024-01-06 | 2024-01-26 | 100 | 100 | % | 100 | 16.8% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 28.5714 | 28.57% | 61.9048 | 61.9% | 95.2381 | 95.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
422 | Concrete Pouring |  | 21 | 21 | 2024-01-10 | 2024-01-30 | 100 | 100 | % | 100 | 16.8% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 9.5238 | 9.524% | 42.8571 | 42.86% | 76.1905 | 76.19% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
423 | Formwork Dismantling |  | 21 | 21 | 2024-01-13 | 2024-02-02 | 100 | 100 | % | 100 | 16.8% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 28.5714 | 28.57% | 61.9048 | 61.9% | 95.2381 | 95.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
424 | Backfill with compaction |  | 20 | 20 | 2024-01-15 | 2024-02-03 | 100 | 100 | % | 100 | 16% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 20 | 20% | 55 | 55% | 90 | 90% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
425 | Completion of Stump |  | 0 | 1 | 2024-02-03 | 2024-02-03 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
426 | Ground Beam |  | 165 | 38 | 2023-12-14 | 2024-01-20 |  |  |  |  | 34.52% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.6061% |  | 11.52% |  | 32.12% |  | 63.03% |  | 85.45% |  | 98.18% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
427 | Excavation |  | 21 | 21 | 2023-12-14 | 2024-01-03 | 100 | 100 | % | 100 | 12.73% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4.7619 | 4.762% | 38.0952 | 38.1% | 71.4286 | 71.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
428 | Leveling and Compaction |  | 21 | 21 | 2023-12-16 | 2024-01-05 | 100 | 100 | % | 100 | 12.73% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 28.5714 | 28.57% | 61.9048 | 61.9% | 95.2381 | 95.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
429 | Lean Concrete Pouring |  | 20 | 20 | 2023-12-18 | 2024-01-06 | 100 | 100 | % | 100 | 12.12% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 20 | 20% | 55 | 55% | 90 | 90% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
430 | Reinforcement Bar Fixing |  | 21 | 21 | 2023-12-21 | 2024-01-10 | 100 | 100 | % | 100 | 12.73% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4.7619 | 4.762% | 38.0952 | 38.1% | 71.4286 | 71.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
431 | Formwork Fixing |  | 20 | 20 | 2023-12-25 | 2024-01-13 | 100 | 100 | % | 100 | 12.12% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 20 | 20% | 55 | 55% | 90 | 90% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
432 | Concrete Pouring |  | 21 | 21 | 2023-12-27 | 2024-01-16 | 100 | 100 | % | 100 | 12.73% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 9.5238 | 9.524% | 42.8571 | 42.86% | 76.1905 | 76.19% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
433 | Formwork Dismantling |  | 21 | 21 | 2023-12-30 | 2024-01-19 | 100 | 100 | % | 100 | 12.73% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 28.5714 | 28.57% | 61.9048 | 61.9% | 95.2381 | 95.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
434 | Backfill with compaction |  | 20 | 20 | 2024-01-01 | 2024-01-20 | 100 | 100 | % | 100 | 12.12% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 20 | 20% | 55 | 55% | 90 | 90% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
435 | Completion of Ground Beam |  | 0 | 1 | 2024-01-20 | 2024-01-20 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
436 | Completion of Structure |  | 0 | 1 | 2024-02-03 | 2024-02-03 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
437 | Equipment Foundation |  | 371 | 61 | 2023-12-30 | 2024-02-28 |  |  |  |  | 43.7% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 2.965% |  | 11.32% |  | 23.99% |  | 40.97% |  | 59.84% |  | 77.63% |  | 89.22% |  | 96.77% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
438 | Equipment Foundation |  | 371 | 61 | 2023-12-30 | 2024-02-28 |  |  |  |  | 100% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 2.965% |  | 11.32% |  | 23.99% |  | 40.97% |  | 59.84% |  | 77.63% |  | 89.22% |  | 96.77% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
439 | Excavation |  | 38 | 38 | 2023-12-30 | 2024-02-05 | 100 | 100 | % | 100 | 10.24% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 15.7895 | 15.79% | 34.2105 | 34.21% | 52.6316 | 52.63% | 71.0526 | 71.05% | 89.4737 | 89.47% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
440 | Leveling and Compaction |  | 37 | 37 | 2024-01-02 | 2024-02-07 | 100 | 100 | % | 100 | 9.973% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 8.1081 | 8.108% | 27.027 | 27.03% | 45.9459 | 45.95% | 64.8649 | 64.86% | 83.7838 | 83.78% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
441 | Lean Concrete Pouring |  | 37 | 37 | 2024-01-03 | 2024-02-08 | 100 | 100 | % | 100 | 9.973% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5.4054 | 5.405% | 24.3243 | 24.32% | 43.2432 | 43.24% | 62.1622 | 62.16% | 81.0811 | 81.08% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
442 | Pile Cutting and Treatment |  | 37 | 37 | 2024-01-05 | 2024-02-10 | 100 | 100 | % | 100 | 9.973% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 18.9189 | 18.92% | 37.8378 | 37.84% | 56.7568 | 56.76% | 75.6757 | 75.68% | 94.5946 | 94.59% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
443 | Reinforcement Bar Fixing |  | 37 | 37 | 2024-01-09 | 2024-02-14 | 100 | 100 | % | 100 | 9.973% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 8.1081 | 8.108% | 27.027 | 27.03% | 45.9459 | 45.95% | 64.8649 | 64.86% | 83.7838 | 83.78% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
444 | Formwork Fixing |  | 37 | 37 | 2024-01-12 | 2024-02-17 | 100 | 100 | % | 100 | 9.973% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 18.9189 | 18.92% | 37.8378 | 37.84% | 56.7568 | 56.76% | 75.6757 | 75.68% | 94.5946 | 94.59% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
445 | Anchor Bolt / Inserted Plate Fixing |  | 37 | 37 | 2024-01-15 | 2024-02-20 | 100 | 100 | % | 100 | 9.973% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 10.8108 | 10.81% | 29.7297 | 29.73% | 48.6486 | 48.65% | 67.5676 | 67.57% | 86.4865 | 86.49% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
446 | Concrete Pouring |  | 37 | 37 | 2024-01-18 | 2024-02-23 | 100 | 100 | % | 100 | 9.973% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 2.7027 | 2.703% | 21.6216 | 21.62% | 40.5405 | 40.54% | 59.4595 | 59.46% | 78.3784 | 78.38% | 97.2973 | 97.3% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
447 | Formwork Dismantling |  | 37 | 37 | 2024-01-22 | 2024-02-27 | 100 | 100 | % | 100 | 9.973% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 10.8108 | 10.81% | 29.7297 | 29.73% | 48.6486 | 48.65% | 67.5676 | 67.57% | 86.4865 | 86.49% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
448 | Backfill with compaction |  | 37 | 37 | 2024-01-23 | 2024-02-28 | 100 | 100 | % | 100 | 9.973% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 8.1081 | 8.108% | 27.027 | 27.03% | 45.9459 | 45.95% | 64.8649 | 64.86% | 83.7838 | 83.78% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
449 | Completion of Equipment Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
450 | Completion of Compressor / Equipment and Pump Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
451 | Completion of Substructure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
452 | Completion of Unit 800 - Distillation Frame |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
453 | Unit 800 - Pipe Gallery 2 |  | 755 | 80 | 2023-12-11 | 2024-02-28 |  |  |  |  | 8.598% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.5298% |  | 1.457% |  | 6.887% |  | 17.22% |  | 31.66% |  | 46.49% |  | 61.85% |  | 75.63% |  | 87.15% |  | 94.17% |  | 98.41% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
454 | Piling (Cutting only) |  | 9 | 9 | 2023-12-11 | 2023-12-19 |  |  |  |  | 1.192% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 44.44% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
455 | Cutting off Pile to GL |  | 9 | 9 | 2023-12-11 | 2023-12-19 | 100 | 100 | % | 100 | 100% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 44.4444 | 44.44% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
456 | Completion of Piling |  | 0 | 1 | 2023-12-19 | 2023-12-19 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
457 | Pipe Gallery |  | 746 | 71 | 2023-12-20 | 2024-02-28 |  |  |  |  | 98.81% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.2681% |  | 5.764% |  | 16.22% |  | 30.83% |  | 45.84% |  | 61.39% |  | 75.34% |  | 87% |  | 94.1% |  | 98.39% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
458 | Structure |  | 482 | 56 | 2023-12-20 | 2024-02-13 |  |  |  |  | 64.61% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.4149% |  | 7.469% |  | 21.58% |  | 42.74% |  | 63.69% |  | 81.12% |  | 92.74% |  | 98.13% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
459 | Pile Cap |  | 188 | 41 | 2023-12-20 | 2024-01-29 |  |  |  |  | 39% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 1.064% |  | 13.3% |  | 34.04% |  | 62.77% |  | 84.04% |  | 96.81% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
460 | Excavation |  | 21 | 21 | 2023-12-20 | 2024-01-09 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 9.5238 | 9.524% | 42.8571 | 42.86% | 76.1905 | 76.19% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
461 | Leveling and Compaction |  | 21 | 21 | 2023-12-22 | 2024-01-11 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
462 | Lean Concrete Pouring |  | 21 | 21 | 2023-12-23 | 2024-01-12 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 28.5714 | 28.57% | 61.9048 | 61.9% | 95.2381 | 95.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
463 | Pile Cutting and Treatment |  | 21 | 21 | 2023-12-26 | 2024-01-15 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 47.619 | 47.62% | 80.9524 | 80.95% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
464 | Reinforcement Bar Fixing |  | 21 | 21 | 2023-12-29 | 2024-01-18 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
465 | Formwork Fixing |  | 21 | 21 | 2024-01-02 | 2024-01-22 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 47.619 | 47.62% | 80.9524 | 80.95% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
466 | Concrete Pouring |  | 21 | 21 | 2024-01-04 | 2024-01-24 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4.7619 | 4.762% | 38.0952 | 38.1% | 71.4286 | 71.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
467 | Formwork Dismantling |  | 20 | 20 | 2024-01-08 | 2024-01-27 | 100 | 100 | % | 100 | 10.64% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 20 | 20% | 55 | 55% | 90 | 90% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
468 | Backfill with compaction |  | 21 | 21 | 2024-01-09 | 2024-01-29 | 100 | 100 | % | 100 | 11.17% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 47.619 | 47.62% | 80.9524 | 80.95% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
469 | Completion of Pile Cap |  | 0 | 1 | 2024-01-29 | 2024-01-29 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
470 | Stump |  | 126 | 34 | 2024-01-11 | 2024-02-13 |  |  |  |  | 26.14% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.7937% |  | 13.49% |  | 39.68% |  | 72.22% |  | 92.86% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
471 | Reinforcement Bar Fixing |  | 21 | 21 | 2024-01-11 | 2024-01-31 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4.7619 | 4.762% | 38.0952 | 38.1% | 71.4286 | 71.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
472 | Formwork Fixing |  | 21 | 21 | 2024-01-13 | 2024-02-02 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 28.5714 | 28.57% | 61.9048 | 61.9% | 95.2381 | 95.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
473 | Anchor Bolt Fixing |  | 21 | 21 | 2024-01-16 | 2024-02-05 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 47.619 | 47.62% | 80.9524 | 80.95% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
474 | Concrete Pouring |  | 21 | 21 | 2024-01-19 | 2024-02-08 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
475 | Formwork Dismantling |  | 21 | 21 | 2024-01-23 | 2024-02-12 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 47.619 | 47.62% | 80.9524 | 80.95% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
476 | Backfill with compaction |  | 21 | 21 | 2024-01-24 | 2024-02-13 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 9.5238 | 9.524% | 42.8571 | 42.86% | 76.1905 | 76.19% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
477 | Completion of Stump |  | 0 | 1 | 2024-02-13 | 2024-02-13 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
478 | Ground Beam |  | 168 | 39 | 2023-12-23 | 2024-01-30 |  |  |  |  | 34.85% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 6.548% |  | 23.81% |  | 51.79% |  | 78.57% |  | 94.64% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
479 | Excavation |  | 21 | 21 | 2023-12-23 | 2024-01-12 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 28.5714 | 28.57% | 61.9048 | 61.9% | 95.2381 | 95.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
480 | Leveling and Compaction |  | 21 | 21 | 2023-12-26 | 2024-01-15 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 47.619 | 47.62% | 80.9524 | 80.95% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
481 | Lean Concrete Pouring |  | 21 | 21 | 2023-12-27 | 2024-01-16 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 9.5238 | 9.524% | 42.8571 | 42.86% | 76.1905 | 76.19% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
482 | Reinforcement Bar Fixing |  | 21 | 21 | 2023-12-30 | 2024-01-19 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 28.5714 | 28.57% | 61.9048 | 61.9% | 95.2381 | 95.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
483 | Formwork Fixing |  | 21 | 21 | 2024-01-03 | 2024-01-23 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 9.5238 | 9.524% | 42.8571 | 42.86% | 76.1905 | 76.19% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
484 | Concrete Pouring |  | 21 | 21 | 2024-01-05 | 2024-01-25 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
485 | Formwork Dismantling |  | 21 | 21 | 2024-01-09 | 2024-01-29 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 47.619 | 47.62% | 80.9524 | 80.95% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
486 | Backfill with compaction |  | 21 | 21 | 2024-01-10 | 2024-01-30 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 9.5238 | 9.524% | 42.8571 | 42.86% | 76.1905 | 76.19% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
487 | Completion of Ground Beam |  | 0 | 1 | 2024-01-30 | 2024-01-30 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
488 | Completion of Structure |  | 0 | 1 | 2024-02-13 | 2024-02-13 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
489 | Underground Pits |  | 56 | 63 | 2023-12-22 | 2024-02-22 |  |  |  |  | 7.507% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 12.5% |  | 30.36% |  | 42.86% |  | 55.36% |  | 66.07% |  | 78.57% |  | 91.07% |  | 92.86% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
490 | Temporary Sheet Pile |  | 6 | 6 | 2023-12-22 | 2023-12-27 | 100 | 100 | % | 100 | 10.71% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
491 | Excavation |  | 15 | 15 | 2023-12-28 | 2024-01-11 | 100 | 100 | % | 100 | 26.79% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 6.6667 | 6.667% | 53.3333 | 53.33% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
492 | Leveling and Compaction |  | 3 | 3 | 2024-01-02 | 2024-01-04 | 100 | 100 | % | 100 | 5.357% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
493 | Lean Concrete Pouring |  | 1 | 1 | 2024-01-12 | 2024-01-12 | 100 | 100 | % | 100 | 1.786% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
494 | Base |  | 8 | 8 | 2024-01-13 | 2024-01-20 |  |  |  |  | 14.29% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 75% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
495 | Reinforcement Bar Fixing |  | 5 | 5 | 2024-01-13 | 2024-01-17 | 100 | 100 | % | 100 | 62.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
496 | Formwork Fixing |  | 2 | 2 | 2024-01-18 | 2024-01-19 | 100 | 100 | % | 100 | 25% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 50 | 50% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
497 | Concrete Pouring |  | 1 | 1 | 2024-01-20 | 2024-01-20 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
498 | Wall |  | 19 | 19 | 2024-01-22 | 2024-02-09 |  |  |  |  | 33.93% | 100% | 100% |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 21.05% |  | 57.89% |  | 94.74% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
499 | Reinforcement Bar Fixing |  | 9 | 9 | 2024-01-22 | 2024-01-30 | 100 | 100 | % | 100 | 47.37% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 44.4444 | 44.44% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
500 | Formwork Fixing |  | 9 | 9 | 2024-01-31 | 2024-02-08 | 100 | 100 | % | 100 | 47.37% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 22.2222 | 22.22% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
501 | Concrete Pouring |  | 1 | 1 | 2024-02-09 | 2024-02-09 | 100 | 100 | % | 100 | 5.263% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
502 | Formwork Dismantling |  | 1 | 1 | 2024-02-19 | 2024-02-19 | 100 | 100 | % | 100 | 1.786% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
503 | Backfill with compaction |  | 3 | 3 | 2024-02-20 | 2024-02-22 | 100 | 100 | % | 100 | 5.357% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
504 | Completion of Underground Pits |  | 0 | 1 | 2024-02-22 | 2024-02-22 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
505 | Equipment Foundation |  | 208 | 44 | 2024-01-16 | 2024-02-28 |  |  |  |  | 27.88% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 1.923% |  | 14.42% |  | 34.13% |  | 60.1% |  | 80.77% |  | 94.23% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
506 | Equipment Foundation |  | 208 | 44 | 2024-01-16 | 2024-02-28 |  |  |  |  | 100% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 1.923% |  | 14.42% |  | 34.13% |  | 60.1% |  | 80.77% |  | 94.23% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
507 | Excavation |  | 21 | 21 | 2024-01-16 | 2024-02-05 | 100 | 100 | % | 100 | 10.1% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 47.619 | 47.62% | 80.9524 | 80.95% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
508 | Leveling and Compaction |  | 21 | 21 | 2024-01-18 | 2024-02-07 | 100 | 100 | % | 100 | 10.1% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4.7619 | 4.762% | 38.0952 | 38.1% | 71.4286 | 71.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
509 | Lean Concrete Pouring |  | 21 | 21 | 2024-01-19 | 2024-02-08 | 100 | 100 | % | 100 | 10.1% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
510 | Pile Cutting and Treatment |  | 20 | 20 | 2024-01-22 | 2024-02-10 | 100 | 100 | % | 100 | 9.615% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 20 | 20% | 55 | 55% | 90 | 90% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
511 | Reinforcement Bar Fixing |  | 21 | 21 | 2024-01-25 | 2024-02-14 | 100 | 100 | % | 100 | 10.1% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4.7619 | 4.762% | 38.0952 | 38.1% | 71.4286 | 71.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
512 | Formwork Fixing |  | 20 | 20 | 2024-01-29 | 2024-02-17 | 100 | 100 | % | 100 | 9.615% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 20 | 20% | 55 | 55% | 90 | 90% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
513 | Anchor Bolt / Inserted Plate Fixing |  | 21 | 21 | 2024-01-31 | 2024-02-20 | 100 | 100 | % | 100 | 10.1% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 9.5238 | 9.524% | 42.8571 | 42.86% | 76.1905 | 76.19% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
514 | Concrete Pouring |  | 21 | 21 | 2024-02-03 | 2024-02-23 | 100 | 100 | % | 100 | 10.1% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 28.5714 | 28.57% | 61.9048 | 61.9% | 95.2381 | 95.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
515 | Formwork Dismantling |  | 21 | 21 | 2024-02-07 | 2024-02-27 | 100 | 100 | % | 100 | 10.1% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 9.5238 | 9.524% | 42.8571 | 42.86% | 76.1905 | 76.19% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
516 | Backfill with compaction |  | 21 | 21 | 2024-02-08 | 2024-02-28 | 100 | 100 | % | 100 | 10.1% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4.7619 | 4.762% | 38.0952 | 38.1% | 71.4286 | 71.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
517 | Completion of Equipment Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
518 | Completion of Compressor / Equipment and Pump Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
519 | Completion of Substructure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
520 | Completion of Unit 800 - Pipe Gallery 2 |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
521 | Unit 800 - Pipe Gallery 3 & 4 |  | 930 | 76 | 2023-12-15 | 2024-02-28 |  |  |  |  | 10.59% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.9677% |  | 4.839% |  | 12.15% |  | 23.76% |  | 40.86% |  | 57.96% |  | 74.19% |  | 87.31% |  | 94.73% |  | 98.71% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
522 | Piling (Cutting only) |  | 9 | 9 | 2023-12-15 | 2023-12-23 |  |  |  |  | 0.9677% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 77.78% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
523 | Cutting off Pile to GL |  | 9 | 9 | 2023-12-15 | 2023-12-23 | 100 | 100 | % | 100 | 100% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 77.7778 | 77.78% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
524 | Completion of Piling |  | 0 | 1 | 2023-12-23 | 2023-12-23 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
525 | Pipe Gallery |  | 921 | 71 | 2023-12-20 | 2024-02-28 |  |  |  |  | 99.03% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.2172% |  | 3.909% |  | 11.29% |  | 23.02% |  | 40.28% |  | 57.55% |  | 73.94% |  | 87.19% |  | 94.68% |  | 98.7% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
526 | Structure |  | 643 | 63 | 2023-12-20 | 2024-02-20 |  |  |  |  | 69.82% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.311% |  | 5.599% |  | 16.17% |  | 32.35% |  | 53.03% |  | 71.38% |  | 85.85% |  | 94.56% |  | 98.6% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
527 | Pile Cap |  | 251 | 48 | 2023-12-20 | 2024-02-05 |  |  |  |  | 39.04% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.7968% |  | 9.96% |  | 25.5% |  | 47.81% |  | 72.11% |  | 88.05% |  | 97.61% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
528 | Excavation |  | 28 | 28 | 2023-12-20 | 2024-01-16 | 100 | 100 | % | 100 | 11.16% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.1429 | 7.143% | 32.1429 | 32.14% | 57.1429 | 57.14% | 82.1429 | 82.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
529 | Leveling and Compaction |  | 28 | 28 | 2023-12-22 | 2024-01-18 | 100 | 100 | % | 100 | 11.16% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 25 | 25% | 50 | 50% | 75 | 75% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
530 | Lean Concrete Pouring |  | 28 | 28 | 2023-12-23 | 2024-01-19 | 100 | 100 | % | 100 | 11.16% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 21.4286 | 21.43% | 46.4286 | 46.43% | 71.4286 | 71.43% | 96.4286 | 96.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
531 | Pile Cutting and Treatment |  | 28 | 28 | 2023-12-26 | 2024-01-22 | 100 | 100 | % | 100 | 11.16% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 10.7143 | 10.71% | 35.7143 | 35.71% | 60.7143 | 60.71% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
532 | Reinforcement Bar Fixing |  | 28 | 28 | 2023-12-29 | 2024-01-25 | 100 | 100 | % | 100 | 11.16% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 25 | 25% | 50 | 50% | 75 | 75% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
533 | Formwork Fixing |  | 28 | 28 | 2024-01-02 | 2024-01-29 | 100 | 100 | % | 100 | 11.16% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 10.7143 | 10.71% | 35.7143 | 35.71% | 60.7143 | 60.71% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
534 | Concrete Pouring |  | 28 | 28 | 2024-01-04 | 2024-01-31 | 100 | 100 | % | 100 | 11.16% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 3.5714 | 3.571% | 28.5714 | 28.57% | 53.5714 | 53.57% | 78.5714 | 78.57% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
535 | Formwork Dismantling |  | 27 | 27 | 2024-01-08 | 2024-02-03 | 100 | 100 | % | 100 | 10.76% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.8148 | 14.81% | 40.7407 | 40.74% | 66.6667 | 66.67% | 92.5926 | 92.59% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
536 | Backfill with compaction |  | 28 | 28 | 2024-01-09 | 2024-02-05 | 100 | 100 | % | 100 | 11.16% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 10.7143 | 10.71% | 35.7143 | 35.71% | 60.7143 | 60.71% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
537 | Completion of Pile Cap |  | 0 | 1 | 2024-02-05 | 2024-02-05 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
538 | Stump |  | 168 | 41 | 2024-01-11 | 2024-02-20 |  |  |  |  | 26.13% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.5952% |  | 10.12% |  | 29.76% |  | 54.76% |  | 79.17% |  | 94.64% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
539 | Reinforcement Bar Fixing |  | 28 | 28 | 2024-01-11 | 2024-02-07 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 3.5714 | 3.571% | 28.5714 | 28.57% | 53.5714 | 53.57% | 78.5714 | 78.57% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
540 | Formwork Fixing |  | 28 | 28 | 2024-01-13 | 2024-02-09 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 21.4286 | 21.43% | 46.4286 | 46.43% | 71.4286 | 71.43% | 96.4286 | 96.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
541 | Anchor Bolt Fixing |  | 28 | 28 | 2024-01-16 | 2024-02-12 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 10.7143 | 10.71% | 35.7143 | 35.71% | 60.7143 | 60.71% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
542 | Concrete Pouring |  | 28 | 28 | 2024-01-19 | 2024-02-15 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 25 | 25% | 50 | 50% | 75 | 75% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
543 | Formwork Dismantling |  | 28 | 28 | 2024-01-23 | 2024-02-19 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 10.7143 | 10.71% | 35.7143 | 35.71% | 60.7143 | 60.71% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
544 | Backfill with compaction |  | 28 | 28 | 2024-01-24 | 2024-02-20 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.1429 | 7.143% | 32.1429 | 32.14% | 57.1429 | 57.14% | 82.1429 | 82.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
545 | Completion of Stump |  | 0 | 1 | 2024-02-20 | 2024-02-20 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
546 | Ground Beam |  | 224 | 46 | 2023-12-23 | 2024-02-06 |  |  |  |  | 34.84% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 4.911% |  | 17.86% |  | 38.84% |  | 63.84% |  | 83.93% |  | 95.98% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
547 | Excavation |  | 28 | 28 | 2023-12-23 | 2024-01-19 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 21.4286 | 21.43% | 46.4286 | 46.43% | 71.4286 | 71.43% | 96.4286 | 96.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
548 | Leveling and Compaction |  | 28 | 28 | 2023-12-26 | 2024-01-22 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 10.7143 | 10.71% | 35.7143 | 35.71% | 60.7143 | 60.71% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
549 | Lean Concrete Pouring |  | 28 | 28 | 2023-12-27 | 2024-01-23 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.1429 | 7.143% | 32.1429 | 32.14% | 57.1429 | 57.14% | 82.1429 | 82.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
550 | Reinforcement Bar Fixing |  | 28 | 28 | 2023-12-30 | 2024-01-26 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 21.4286 | 21.43% | 46.4286 | 46.43% | 71.4286 | 71.43% | 96.4286 | 96.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
551 | Formwork Fixing |  | 28 | 28 | 2024-01-03 | 2024-01-30 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.1429 | 7.143% | 32.1429 | 32.14% | 57.1429 | 57.14% | 82.1429 | 82.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
552 | Concrete Pouring |  | 28 | 28 | 2024-01-05 | 2024-02-01 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 25 | 25% | 50 | 50% | 75 | 75% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
553 | Formwork Dismantling |  | 28 | 28 | 2024-01-09 | 2024-02-05 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 10.7143 | 10.71% | 35.7143 | 35.71% | 60.7143 | 60.71% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
554 | Backfill with compaction |  | 28 | 28 | 2024-01-10 | 2024-02-06 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.1429 | 7.143% | 32.1429 | 32.14% | 57.1429 | 57.14% | 82.1429 | 82.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
555 | Completion of Ground Beam |  | 0 | 1 | 2024-02-06 | 2024-02-06 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
556 | Completion of Structure |  | 0 | 1 | 2024-02-20 | 2024-02-20 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
557 | Equipment Foundation |  | 278 | 51 | 2024-01-09 | 2024-02-28 |  |  |  |  | 30.18% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 1.439% |  | 10.79% |  | 25.54% |  | 46.4% |  | 70.14% |  | 85.61% |  | 95.68% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
558 | Equipment Foundation |  | 278 | 51 | 2024-01-09 | 2024-02-28 |  |  |  |  | 100% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 1.439% |  | 10.79% |  | 25.54% |  | 46.4% |  | 70.14% |  | 85.61% |  | 95.68% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
559 | Excavation |  | 28 | 28 | 2024-01-09 | 2024-02-05 | 100 | 100 | % | 100 | 10.07% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 10.7143 | 10.71% | 35.7143 | 35.71% | 60.7143 | 60.71% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
560 | Leveling and Compaction |  | 28 | 28 | 2024-01-11 | 2024-02-07 | 100 | 100 | % | 100 | 10.07% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 3.5714 | 3.571% | 28.5714 | 28.57% | 53.5714 | 53.57% | 78.5714 | 78.57% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
561 | Lean Concrete Pouring |  | 28 | 28 | 2024-01-12 | 2024-02-08 | 100 | 100 | % | 100 | 10.07% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 25 | 25% | 50 | 50% | 75 | 75% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
562 | Pile Cutting and Treatment |  | 27 | 27 | 2024-01-15 | 2024-02-10 | 100 | 100 | % | 100 | 9.712% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.8148 | 14.81% | 40.7407 | 40.74% | 66.6667 | 66.67% | 92.5926 | 92.59% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
563 | Reinforcement Bar Fixing |  | 28 | 28 | 2024-01-18 | 2024-02-14 | 100 | 100 | % | 100 | 10.07% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 3.5714 | 3.571% | 28.5714 | 28.57% | 53.5714 | 53.57% | 78.5714 | 78.57% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
564 | Formwork Fixing |  | 27 | 27 | 2024-01-22 | 2024-02-17 | 100 | 100 | % | 100 | 9.712% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.8148 | 14.81% | 40.7407 | 40.74% | 66.6667 | 66.67% | 92.5926 | 92.59% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
565 | Anchor Bolt / Inserted Plate Fixing |  | 28 | 28 | 2024-01-24 | 2024-02-20 | 100 | 100 | % | 100 | 10.07% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.1429 | 7.143% | 32.1429 | 32.14% | 57.1429 | 57.14% | 82.1429 | 82.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
566 | Concrete Pouring |  | 28 | 28 | 2024-01-27 | 2024-02-23 | 100 | 100 | % | 100 | 10.07% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 21.4286 | 21.43% | 46.4286 | 46.43% | 71.4286 | 71.43% | 96.4286 | 96.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
567 | Formwork Dismantling |  | 28 | 28 | 2024-01-31 | 2024-02-27 | 100 | 100 | % | 100 | 10.07% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.1429 | 7.143% | 32.1429 | 32.14% | 57.1429 | 57.14% | 82.1429 | 82.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
568 | Backfill with compaction |  | 28 | 28 | 2024-02-01 | 2024-02-28 | 100 | 100 | % | 100 | 10.07% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 3.5714 | 3.571% | 28.5714 | 28.57% | 53.5714 | 53.57% | 78.5714 | 78.57% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
569 | Completion of Equipment Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
570 | Completion of Compressor / Equipment and Pump Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
571 | Completion of Substructure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
572 | Completion of Unit 800 - Pipe Gallery 2 |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
573 | Unit 800 - Reaction Frame (101-103) |  | 594 | 68 | 2023-12-15 | 2024-02-20 |  |  |  |  | 6.765% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 1.178% |  | 5.556% |  | 16.33% |  | 31.14% |  | 48.99% |  | 67% |  | 82.66% |  | 93.1% |  | 98.48% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
574 | Piling (Cutting only) |  | 21 | 21 | 2023-12-15 | 2024-01-04 |  |  |  |  | 3.535% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 33.33% |  | 66.67% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
575 | Cutting off Pile to GL |  | 21 | 21 | 2023-12-15 | 2024-01-04 | 100 | 100 | % | 100 | 100% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
576 | Completion of Piling |  | 0 | 1 | 2024-01-04 | 2024-01-04 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
577 | Substructure |  | 573 | 61 | 2023-12-22 | 2024-02-20 |  |  |  |  | 96.46% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 3.316% |  | 13.26% |  | 28.62% |  | 47.12% |  | 65.79% |  | 82.02% |  | 92.84% |  | 98.43% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
578 | Structure |  | 398 | 53 | 2023-12-22 | 2024-02-12 |  |  |  |  | 69.46% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 4.774% |  | 19.1% |  | 40.95% |  | 62.81% |  | 80.65% |  | 92.96% |  | 98.49% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
579 | Pile Cap |  | 155 | 37 | 2023-12-22 | 2024-01-27 |  |  |  |  | 38.94% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 9.677% |  | 30.97% |  | 61.29% |  | 84.52% |  | 98.06% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
580 | Excavation |  | 18 | 18 | 2023-12-22 | 2024-01-08 | 100 | 100 | % | 100 | 11.61% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 38.8889 | 38.89% | 77.7778 | 77.78% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
581 | Leveling and Compaction |  | 17 | 17 | 2023-12-25 | 2024-01-10 | 100 | 100 | % | 100 | 10.97% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 23.5294 | 23.53% | 64.7059 | 64.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
582 | Lean Concrete Pouring |  | 17 | 17 | 2023-12-26 | 2024-01-11 | 100 | 100 | % | 100 | 10.97% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 17.6471 | 17.65% | 58.8235 | 58.82% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
583 | Pile Cutting and Treatment |  | 17 | 17 | 2023-12-28 | 2024-01-13 | 100 | 100 | % | 100 | 10.97% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5.8824 | 5.882% | 47.0588 | 47.06% | 88.2353 | 88.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
584 | Reinforcement Bar Fixing |  | 17 | 17 | 2024-01-01 | 2024-01-17 | 100 | 100 | % | 100 | 10.97% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 23.5294 | 23.53% | 64.7059 | 64.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
585 | Formwork Fixing |  | 17 | 17 | 2024-01-04 | 2024-01-20 | 100 | 100 | % | 100 | 10.97% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5.8824 | 5.882% | 47.0588 | 47.06% | 88.2353 | 88.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
586 | Concrete Pouring |  | 18 | 18 | 2024-01-06 | 2024-01-23 | 100 | 100 | % | 100 | 11.61% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 72.2222 | 72.22% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
587 | Formwork Dismantling |  | 17 | 17 | 2024-01-10 | 2024-01-26 | 100 | 100 | % | 100 | 10.97% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 11.7647 | 11.76% | 52.9412 | 52.94% | 94.1176 | 94.12% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
588 | Backfill with compaction |  | 17 | 17 | 2024-01-11 | 2024-01-27 | 100 | 100 | % | 100 | 10.97% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5.8824 | 5.882% | 47.0588 | 47.06% | 88.2353 | 88.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
589 | Completion of Pile Cap |  | 0 | 1 | 2024-01-27 | 2024-01-27 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
590 | Stump |  | 104 | 31 | 2024-01-13 | 2024-02-12 |  |  |  |  | 26.13% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 9.615% |  | 34.62% |  | 73.08% |  | 94.23% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
591 | Reinforcement Bar Fixing |  | 18 | 18 | 2024-01-13 | 2024-01-30 | 100 | 100 | % | 100 | 17.31% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 72.2222 | 72.22% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
592 | Formwork Fixing |  | 17 | 17 | 2024-01-16 | 2024-02-01 | 100 | 100 | % | 100 | 16.35% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 17.6471 | 17.65% | 58.8235 | 58.82% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
593 | Anchor Bolt Fixing |  | 17 | 17 | 2024-01-18 | 2024-02-03 | 100 | 100 | % | 100 | 16.35% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5.8824 | 5.882% | 47.0588 | 47.06% | 88.2353 | 88.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
594 | Concrete Pouring |  | 17 | 17 | 2024-01-22 | 2024-02-07 | 100 | 100 | % | 100 | 16.35% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 23.5294 | 23.53% | 64.7059 | 64.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
595 | Formwork Dismantling |  | 17 | 17 | 2024-01-25 | 2024-02-10 | 100 | 100 | % | 100 | 16.35% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5.8824 | 5.882% | 47.0588 | 47.06% | 88.2353 | 88.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
596 | Backfill with compaction |  | 18 | 18 | 2024-01-26 | 2024-02-12 | 100 | 100 | % | 100 | 17.31% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 38.8889 | 38.89% | 77.7778 | 77.78% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
597 | Completion of Stump |  | 0 | 1 | 2024-02-12 | 2024-02-12 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
598 | Ground Beam |  | 139 | 35 | 2023-12-26 | 2024-01-29 |  |  |  |  | 34.92% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 2.878% |  | 20.14% |  | 48.92% |  | 78.42% |  | 95.68% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
599 | Excavation |  | 17 | 17 | 2023-12-26 | 2024-01-11 | 100 | 100 | % | 100 | 12.23% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 17.6471 | 17.65% | 58.8235 | 58.82% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
600 | Leveling and Compaction |  | 17 | 17 | 2023-12-28 | 2024-01-13 | 100 | 100 | % | 100 | 12.23% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5.8824 | 5.882% | 47.0588 | 47.06% | 88.2353 | 88.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
601 | Lean Concrete Pouring |  | 18 | 18 | 2023-12-29 | 2024-01-15 | 100 | 100 | % | 100 | 12.95% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 38.8889 | 38.89% | 77.7778 | 77.78% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
602 | Reinforcement Bar Fixing |  | 17 | 17 | 2024-01-02 | 2024-01-18 | 100 | 100 | % | 100 | 12.23% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 17.6471 | 17.65% | 58.8235 | 58.82% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
603 | Formwork Fixing |  | 18 | 18 | 2024-01-05 | 2024-01-22 | 100 | 100 | % | 100 | 12.95% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 38.8889 | 38.89% | 77.7778 | 77.78% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
604 | Concrete Pouring |  | 17 | 17 | 2024-01-08 | 2024-01-24 | 100 | 100 | % | 100 | 12.23% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 23.5294 | 23.53% | 64.7059 | 64.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
605 | Formwork Dismantling |  | 17 | 17 | 2024-01-11 | 2024-01-27 | 100 | 100 | % | 100 | 12.23% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5.8824 | 5.882% | 47.0588 | 47.06% | 88.2353 | 88.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
606 | Backfill with compaction |  | 18 | 18 | 2024-01-12 | 2024-01-29 | 100 | 100 | % | 100 | 12.95% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 38.8889 | 38.89% | 77.7778 | 77.78% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
607 | Completion of Ground Beam |  | 0 | 1 | 2024-01-29 | 2024-01-29 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
608 | Completion of Structure |  | 0 | 1 | 2024-02-12 | 2024-02-12 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
609 | Equipment Foundation |  | 175 | 41 | 2024-01-11 | 2024-02-20 |  |  |  |  | 30.54% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.5714% |  | 11.43% |  | 32% |  | 57.14% |  | 80% |  | 94.86% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
610 | Equipment Foundation |  | 175 | 41 | 2024-01-11 | 2024-02-20 |  |  |  |  | 100% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.5714% |  | 11.43% |  | 32% |  | 57.14% |  | 80% |  | 94.86% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
611 | Excavation |  | 17 | 17 | 2024-01-11 | 2024-01-27 | 100 | 100 | % | 100 | 9.714% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5.8824 | 5.882% | 47.0588 | 47.06% | 88.2353 | 88.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
612 | Leveling and Compaction |  | 18 | 18 | 2024-01-13 | 2024-01-30 | 100 | 100 | % | 100 | 10.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 72.2222 | 72.22% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
613 | Lean Concrete Pouring |  | 17 | 17 | 2024-01-15 | 2024-01-31 | 100 | 100 | % | 100 | 9.714% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 23.5294 | 23.53% | 64.7059 | 64.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
614 | Pile Cutting and Treatment |  | 17 | 17 | 2024-01-17 | 2024-02-02 | 100 | 100 | % | 100 | 9.714% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 11.7647 | 11.76% | 52.9412 | 52.94% | 94.1176 | 94.12% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
615 | Reinforcement Bar Fixing |  | 18 | 18 | 2024-01-20 | 2024-02-06 | 100 | 100 | % | 100 | 10.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 72.2222 | 72.22% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
616 | Formwork Fixing |  | 17 | 17 | 2024-01-24 | 2024-02-09 | 100 | 100 | % | 100 | 9.714% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 11.7647 | 11.76% | 52.9412 | 52.94% | 94.1176 | 94.12% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
617 | Anchor Bolt / Inserted Plate Fixing |  | 18 | 18 | 2024-01-26 | 2024-02-12 | 100 | 100 | % | 100 | 10.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 38.8889 | 38.89% | 77.7778 | 77.78% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
618 | Concrete Pouring |  | 17 | 17 | 2024-01-30 | 2024-02-15 | 100 | 100 | % | 100 | 9.714% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 17.6471 | 17.65% | 58.8235 | 58.82% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
619 | Formwork Dismantling |  | 18 | 18 | 2024-02-02 | 2024-02-19 | 100 | 100 | % | 100 | 10.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 38.8889 | 38.89% | 77.7778 | 77.78% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
620 | Backfill with compaction |  | 18 | 18 | 2024-02-03 | 2024-02-20 | 100 | 100 | % | 100 | 10.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 72.2222 | 72.22% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
621 | Completion of Equipment Foundation |  | 0 | 1 | 2024-02-20 | 2024-02-20 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
622 | Completion of Equipment and Pump Foundation |  | 0 | 1 | 2024-02-20 | 2024-02-20 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
623 | Completion of Substructure |  | 0 | 1 | 2024-02-20 | 2024-02-20 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
624 | Completion of Unit 800 - Reaction Frame (101-103) |  | 0 | 1 | 2024-02-20 | 2024-02-20 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
625 | Unit 800 - Reaction Frame (103-116) |  | 1134 | 76 | 2023-12-15 | 2024-02-28 |  |  |  |  | 12.91% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.7937% |  | 4.409% |  | 11.02% |  | 21.16% |  | 35.36% |  | 52.29% |  | 69.14% |  | 83.6% |  | 92.95% |  | 97.88% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
626 | Piling (Cutting only) |  | 28 | 28 | 2023-12-15 | 2024-01-11 |  |  |  |  | 2.469% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 25% |  | 50% |  | 75% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
627 | Cutting off Pile to GL |  | 28 | 28 | 2023-12-15 | 2024-01-11 | 100 | 100 | % | 100 | 100% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 25 | 25% | 50 | 50% | 75 | 75% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
628 | Completion of Piling |  | 0 | 1 | 2024-01-11 | 2024-01-11 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
629 | Substructure |  | 1106 | 71 | 2023-12-20 | 2024-02-28 |  |  |  |  | 97.53% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.1808% |  | 3.255% |  | 9.403% |  | 19.17% |  | 33.73% |  | 51.08% |  | 68.35% |  | 83.18% |  | 92.77% |  | 97.83% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
630 | Structure |  | 828 | 71 | 2023-12-20 | 2024-02-28 |  |  |  |  | 74.86% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.2415% |  | 4.348% |  | 12.56% |  | 25.12% |  | 41.43% |  | 59.66% |  | 75.72% |  | 87.56% |  | 95.17% |  | 98.55% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
631 | Pile Cap |  | 324 | 56 | 2023-12-20 | 2024-02-13 |  |  |  |  | 39.13% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.6173% |  | 7.716% |  | 19.75% |  | 37.04% |  | 56.48% |  | 75.62% |  | 88.89% |  | 97.22% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
632 | Excavation |  | 36 | 36 | 2023-12-20 | 2024-01-24 | 100 | 100 | % | 100 | 11.11% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5.5556 | 5.556% | 25 | 25% | 44.4444 | 44.44% | 63.8889 | 63.89% | 83.3333 | 83.33% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
633 | Leveling and Compaction |  | 36 | 36 | 2023-12-22 | 2024-01-26 | 100 | 100 | % | 100 | 11.11% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 19.4444 | 19.44% | 38.8889 | 38.89% | 58.3333 | 58.33% | 77.7778 | 77.78% | 97.2222 | 97.22% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
634 | Lean Concrete Pouring |  | 36 | 36 | 2023-12-23 | 2024-01-27 | 100 | 100 | % | 100 | 11.11% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 16.6667 | 16.67% | 36.1111 | 36.11% | 55.5556 | 55.56% | 75 | 75% | 94.4444 | 94.44% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
635 | Pile Cutting and Treatment |  | 36 | 36 | 2023-12-26 | 2024-01-30 | 100 | 100 | % | 100 | 11.11% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 8.3333 | 8.333% | 27.7778 | 27.78% | 47.2222 | 47.22% | 66.6667 | 66.67% | 86.1111 | 86.11% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
636 | Reinforcement Bar Fixing |  | 36 | 36 | 2023-12-29 | 2024-02-02 | 100 | 100 | % | 100 | 11.11% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 19.4444 | 19.44% | 38.8889 | 38.89% | 58.3333 | 58.33% | 77.7778 | 77.78% | 97.2222 | 97.22% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
637 | Formwork Fixing |  | 36 | 36 | 2024-01-02 | 2024-02-06 | 100 | 100 | % | 100 | 11.11% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 8.3333 | 8.333% | 27.7778 | 27.78% | 47.2222 | 47.22% | 66.6667 | 66.67% | 86.1111 | 86.11% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
638 | Concrete Pouring |  | 36 | 36 | 2024-01-04 | 2024-02-08 | 100 | 100 | % | 100 | 11.11% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 2.7778 | 2.778% | 22.2222 | 22.22% | 41.6667 | 41.67% | 61.1111 | 61.11% | 80.5556 | 80.56% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
639 | Formwork Dismantling |  | 36 | 36 | 2024-01-08 | 2024-02-12 | 100 | 100 | % | 100 | 11.11% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 11.1111 | 11.11% | 30.5556 | 30.56% | 50 | 50% | 69.4444 | 69.44% | 88.8889 | 88.89% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
640 | Backfill with compaction |  | 36 | 36 | 2024-01-09 | 2024-02-13 | 100 | 100 | % | 100 | 11.11% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 8.3333 | 8.333% | 27.7778 | 27.78% | 47.2222 | 47.22% | 66.6667 | 66.67% | 86.1111 | 86.11% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
641 | Completion of Pile Cap |  | 0 | 1 | 2024-02-13 | 2024-02-13 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
642 | Stump |  | 216 | 49 | 2024-01-11 | 2024-02-28 |  |  |  |  | 26.09% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.463% |  | 7.87% |  | 23.15% |  | 42.59% |  | 62.04% |  | 81.48% |  | 94.44% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
643 | Reinforcement Bar Fixing |  | 36 | 36 | 2024-01-11 | 2024-02-15 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 2.7778 | 2.778% | 22.2222 | 22.22% | 41.6667 | 41.67% | 61.1111 | 61.11% | 80.5556 | 80.56% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
644 | Formwork Fixing |  | 36 | 36 | 2024-01-13 | 2024-02-17 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 16.6667 | 16.67% | 36.1111 | 36.11% | 55.5556 | 55.56% | 75 | 75% | 94.4444 | 94.44% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
645 | Anchor Bolt Fixing |  | 36 | 36 | 2024-01-16 | 2024-02-20 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 8.3333 | 8.333% | 27.7778 | 27.78% | 47.2222 | 47.22% | 66.6667 | 66.67% | 86.1111 | 86.11% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
646 | Concrete Pouring |  | 36 | 36 | 2024-01-19 | 2024-02-23 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 19.4444 | 19.44% | 38.8889 | 38.89% | 58.3333 | 58.33% | 77.7778 | 77.78% | 97.2222 | 97.22% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
647 | Formwork Dismantling |  | 36 | 36 | 2024-01-23 | 2024-02-27 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 8.3333 | 8.333% | 27.7778 | 27.78% | 47.2222 | 47.22% | 66.6667 | 66.67% | 86.1111 | 86.11% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
648 | Backfill with compaction |  | 36 | 36 | 2024-01-24 | 2024-02-28 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5.5556 | 5.556% | 25 | 25% | 44.4444 | 44.44% | 63.8889 | 63.89% | 83.3333 | 83.33% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
649 | Completion of Stump |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
650 | Ground Beam |  | 288 | 54 | 2023-12-23 | 2024-02-14 |  |  |  |  | 34.78% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 3.819% |  | 13.89% |  | 30.21% |  | 49.65% |  | 69.1% |  | 85.76% |  | 95.83% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
651 | Excavation |  | 36 | 36 | 2023-12-23 | 2024-01-27 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 16.6667 | 16.67% | 36.1111 | 36.11% | 55.5556 | 55.56% | 75 | 75% | 94.4444 | 94.44% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
652 | Leveling and Compaction |  | 36 | 36 | 2023-12-26 | 2024-01-30 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 8.3333 | 8.333% | 27.7778 | 27.78% | 47.2222 | 47.22% | 66.6667 | 66.67% | 86.1111 | 86.11% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
653 | Lean Concrete Pouring |  | 36 | 36 | 2023-12-27 | 2024-01-31 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5.5556 | 5.556% | 25 | 25% | 44.4444 | 44.44% | 63.8889 | 63.89% | 83.3333 | 83.33% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
654 | Reinforcement Bar Fixing |  | 36 | 36 | 2023-12-30 | 2024-02-03 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 16.6667 | 16.67% | 36.1111 | 36.11% | 55.5556 | 55.56% | 75 | 75% | 94.4444 | 94.44% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
655 | Formwork Fixing |  | 36 | 36 | 2024-01-03 | 2024-02-07 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5.5556 | 5.556% | 25 | 25% | 44.4444 | 44.44% | 63.8889 | 63.89% | 83.3333 | 83.33% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
656 | Concrete Pouring |  | 36 | 36 | 2024-01-05 | 2024-02-09 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 19.4444 | 19.44% | 38.8889 | 38.89% | 58.3333 | 58.33% | 77.7778 | 77.78% | 97.2222 | 97.22% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
657 | Formwork Dismantling |  | 36 | 36 | 2024-01-09 | 2024-02-13 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 8.3333 | 8.333% | 27.7778 | 27.78% | 47.2222 | 47.22% | 66.6667 | 66.67% | 86.1111 | 86.11% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
658 | Backfill with compaction |  | 36 | 36 | 2024-01-10 | 2024-02-14 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5.5556 | 5.556% | 25 | 25% | 44.4444 | 44.44% | 63.8889 | 63.89% | 83.3333 | 83.33% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
659 | Completion of Ground Beam |  | 0 | 1 | 2024-02-14 | 2024-02-14 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
660 | Completion of Structure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
661 | Equipment Foundation |  | 278 | 51 | 2024-01-09 | 2024-02-28 |  |  |  |  | 25.14% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 1.439% |  | 10.79% |  | 25.54% |  | 46.4% |  | 70.14% |  | 85.61% |  | 95.68% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
662 | Equipment Foundation |  | 278 | 51 | 2024-01-09 | 2024-02-28 |  |  |  |  | 100% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 1.439% |  | 10.79% |  | 25.54% |  | 46.4% |  | 70.14% |  | 85.61% |  | 95.68% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
663 | Excavation |  | 28 | 28 | 2024-01-09 | 2024-02-05 | 100 | 100 | % | 100 | 10.07% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 10.7143 | 10.71% | 35.7143 | 35.71% | 60.7143 | 60.71% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
664 | Leveling and Compaction |  | 28 | 28 | 2024-01-11 | 2024-02-07 | 100 | 100 | % | 100 | 10.07% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 3.5714 | 3.571% | 28.5714 | 28.57% | 53.5714 | 53.57% | 78.5714 | 78.57% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
665 | Lean Concrete Pouring |  | 28 | 28 | 2024-01-12 | 2024-02-08 | 100 | 100 | % | 100 | 10.07% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 25 | 25% | 50 | 50% | 75 | 75% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
666 | Pile Cutting and Treatment |  | 27 | 27 | 2024-01-15 | 2024-02-10 | 100 | 100 | % | 100 | 9.712% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.8148 | 14.81% | 40.7407 | 40.74% | 66.6667 | 66.67% | 92.5926 | 92.59% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
667 | Reinforcement Bar Fixing |  | 28 | 28 | 2024-01-18 | 2024-02-14 | 100 | 100 | % | 100 | 10.07% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 3.5714 | 3.571% | 28.5714 | 28.57% | 53.5714 | 53.57% | 78.5714 | 78.57% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
668 | Formwork Fixing |  | 27 | 27 | 2024-01-22 | 2024-02-17 | 100 | 100 | % | 100 | 9.712% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.8148 | 14.81% | 40.7407 | 40.74% | 66.6667 | 66.67% | 92.5926 | 92.59% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
669 | Anchor Bolt / Inserted Plate Fixing |  | 28 | 28 | 2024-01-24 | 2024-02-20 | 100 | 100 | % | 100 | 10.07% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.1429 | 7.143% | 32.1429 | 32.14% | 57.1429 | 57.14% | 82.1429 | 82.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
670 | Concrete Pouring |  | 28 | 28 | 2024-01-27 | 2024-02-23 | 100 | 100 | % | 100 | 10.07% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 21.4286 | 21.43% | 46.4286 | 46.43% | 71.4286 | 71.43% | 96.4286 | 96.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
671 | Formwork Dismantling |  | 28 | 28 | 2024-01-31 | 2024-02-27 | 100 | 100 | % | 100 | 10.07% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.1429 | 7.143% | 32.1429 | 32.14% | 57.1429 | 57.14% | 82.1429 | 82.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
672 | Backfill with compaction |  | 28 | 28 | 2024-02-01 | 2024-02-28 | 100 | 100 | % | 100 | 10.07% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 3.5714 | 3.571% | 28.5714 | 28.57% | 53.5714 | 53.57% | 78.5714 | 78.57% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
673 | Completion of Equipment Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
674 | Completion of Equipment and Pump Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
675 | Completion of Substructure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
676 | Completion of Unit 800 - Reaction Frame (103-116) |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
677 | Unit 900 - HPU |  | 1156 | 87 | 2023-12-04 | 2024-02-28 |  |  |  |  | 13.16% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.346% |  | 0.9516% |  | 1.644% |  | 5.536% |  | 14.01% |  | 26.99% |  | 44.38% |  | 63.06% |  | 78.63% |  | 89.79% |  | 96.54% |  | 98.96% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
678 | Piling (Cutting only) |  | 17 | 17 | 2023-12-04 | 2023-12-20 |  |  |  |  | 1.471% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 23.53% |  | 64.71% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
679 | Cutting off Pile to GL |  | 17 | 17 | 2023-12-04 | 2023-12-20 | 100 | 100 | % | 100 | 100% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 23.5294 | 23.53% | 64.7059 | 64.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
680 | Completion of Piling |  | 0 | 1 | 2023-12-20 | 2023-12-20 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
681 | Substructure |  | 1139 | 70 | 2023-12-21 | 2024-02-28 |  |  |  |  | 98.53% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.1756% |  | 4.126% |  | 12.73% |  | 25.9% |  | 43.55% |  | 62.51% |  | 78.31% |  | 89.64% |  | 96.49% |  | 98.95% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
682 | Structure |  | 801 | 70 | 2023-12-21 | 2024-02-28 |  |  |  |  | 70.32% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.1248% |  | 3.371% |  | 11.11% |  | 23.35% |  | 39.83% |  | 58.3% |  | 74.91% |  | 87.14% |  | 95.01% |  | 98.5% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
683 | Pile Cap |  | 314 | 55 | 2023-12-21 | 2024-02-13 |  |  |  |  | 39.2% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.3185% |  | 6.369% |  | 17.83% |  | 35.03% |  | 55.1% |  | 74.84% |  | 88.54% |  | 97.13% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
684 | Excavation |  | 35 | 35 | 2023-12-21 | 2024-01-24 | 100 | 100 | % | 100 | 11.15% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 2.8571 | 2.857% | 22.8571 | 22.86% | 42.8571 | 42.86% | 62.8571 | 62.86% | 82.8571 | 82.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
685 | Leveling and Compaction |  | 35 | 35 | 2023-12-23 | 2024-01-26 | 100 | 100 | % | 100 | 11.15% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 17.1429 | 17.14% | 37.1429 | 37.14% | 57.1429 | 57.14% | 77.1429 | 77.14% | 97.1429 | 97.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
686 | Lean Concrete Pouring |  | 34 | 34 | 2023-12-25 | 2024-01-27 | 100 | 100 | % | 100 | 10.83% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 11.7647 | 11.76% | 32.3529 | 32.35% | 52.9412 | 52.94% | 73.5294 | 73.53% | 94.1176 | 94.12% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
687 | Pile Cutting and Treatment |  | 35 | 35 | 2023-12-27 | 2024-01-30 | 100 | 100 | % | 100 | 11.15% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5.7143 | 5.714% | 25.7143 | 25.71% | 45.7143 | 45.71% | 65.7143 | 65.71% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
688 | Reinforcement Bar Fixing |  | 35 | 35 | 2023-12-30 | 2024-02-02 | 100 | 100 | % | 100 | 11.15% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 17.1429 | 17.14% | 37.1429 | 37.14% | 57.1429 | 57.14% | 77.1429 | 77.14% | 97.1429 | 97.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
689 | Formwork Fixing |  | 35 | 35 | 2024-01-03 | 2024-02-06 | 100 | 100 | % | 100 | 11.15% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5.7143 | 5.714% | 25.7143 | 25.71% | 45.7143 | 45.71% | 65.7143 | 65.71% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
690 | Concrete Pouring |  | 35 | 35 | 2024-01-05 | 2024-02-08 | 100 | 100 | % | 100 | 11.15% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 20 | 20% | 40 | 40% | 60 | 60% | 80 | 80% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
691 | Formwork Dismantling |  | 35 | 35 | 2024-01-09 | 2024-02-12 | 100 | 100 | % | 100 | 11.15% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 8.5714 | 8.571% | 28.5714 | 28.57% | 48.5714 | 48.57% | 68.5714 | 68.57% | 88.5714 | 88.57% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
692 | Backfill with compaction |  | 35 | 35 | 2024-01-10 | 2024-02-13 | 100 | 100 | % | 100 | 11.15% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5.7143 | 5.714% | 25.7143 | 25.71% | 45.7143 | 45.71% | 65.7143 | 65.71% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
693 | Completion of Pile Cap |  | 0 | 1 | 2024-02-13 | 2024-02-13 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
694 | Stump |  | 209 | 48 | 2024-01-12 | 2024-02-28 |  |  |  |  | 26.09% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 6.22% |  | 20.57% |  | 40.67% |  | 60.77% |  | 80.86% |  | 94.26% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
695 | Reinforcement Bar Fixing |  | 35 | 35 | 2024-01-12 | 2024-02-15 | 100 | 100 | % | 100 | 16.75% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 20 | 20% | 40 | 40% | 60 | 60% | 80 | 80% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
696 | Formwork Fixing |  | 34 | 34 | 2024-01-15 | 2024-02-17 | 100 | 100 | % | 100 | 16.27% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 11.7647 | 11.76% | 32.3529 | 32.35% | 52.9412 | 52.94% | 73.5294 | 73.53% | 94.1176 | 94.12% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
697 | Anchor Bolt Fixing |  | 35 | 35 | 2024-01-17 | 2024-02-20 | 100 | 100 | % | 100 | 16.75% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5.7143 | 5.714% | 25.7143 | 25.71% | 45.7143 | 45.71% | 65.7143 | 65.71% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
698 | Concrete Pouring |  | 35 | 35 | 2024-01-20 | 2024-02-23 | 100 | 100 | % | 100 | 16.75% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 17.1429 | 17.14% | 37.1429 | 37.14% | 57.1429 | 57.14% | 77.1429 | 77.14% | 97.1429 | 97.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
699 | Formwork Dismantling |  | 35 | 35 | 2024-01-24 | 2024-02-27 | 100 | 100 | % | 100 | 16.75% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5.7143 | 5.714% | 25.7143 | 25.71% | 45.7143 | 45.71% | 65.7143 | 65.71% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
700 | Backfill with compaction |  | 35 | 35 | 2024-01-25 | 2024-02-28 | 100 | 100 | % | 100 | 16.75% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 2.8571 | 2.857% | 22.8571 | 22.86% | 42.8571 | 42.86% | 62.8571 | 62.86% | 82.8571 | 82.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
701 | Completion of Stump |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
702 | Ground Beam |  | 278 | 52 | 2023-12-25 | 2024-02-14 |  |  |  |  | 34.71% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 2.518% |  | 11.87% |  | 27.7% |  | 47.84% |  | 67.99% |  | 85.25% |  | 95.68% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
703 | Excavation |  | 34 | 34 | 2023-12-25 | 2024-01-27 | 100 | 100 | % | 100 | 12.23% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 11.7647 | 11.76% | 32.3529 | 32.35% | 52.9412 | 52.94% | 73.5294 | 73.53% | 94.1176 | 94.12% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
704 | Leveling and Compaction |  | 35 | 35 | 2023-12-27 | 2024-01-30 | 100 | 100 | % | 100 | 12.59% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5.7143 | 5.714% | 25.7143 | 25.71% | 45.7143 | 45.71% | 65.7143 | 65.71% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
705 | Lean Concrete Pouring |  | 35 | 35 | 2023-12-28 | 2024-01-31 | 100 | 100 | % | 100 | 12.59% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 2.8571 | 2.857% | 22.8571 | 22.86% | 42.8571 | 42.86% | 62.8571 | 62.86% | 82.8571 | 82.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
706 | Reinforcement Bar Fixing |  | 34 | 34 | 2024-01-01 | 2024-02-03 | 100 | 100 | % | 100 | 12.23% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 11.7647 | 11.76% | 32.3529 | 32.35% | 52.9412 | 52.94% | 73.5294 | 73.53% | 94.1176 | 94.12% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
707 | Formwork Fixing |  | 35 | 35 | 2024-01-04 | 2024-02-07 | 100 | 100 | % | 100 | 12.59% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 2.8571 | 2.857% | 22.8571 | 22.86% | 42.8571 | 42.86% | 62.8571 | 62.86% | 82.8571 | 82.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
708 | Concrete Pouring |  | 35 | 35 | 2024-01-06 | 2024-02-09 | 100 | 100 | % | 100 | 12.59% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 17.1429 | 17.14% | 37.1429 | 37.14% | 57.1429 | 57.14% | 77.1429 | 77.14% | 97.1429 | 97.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
709 | Formwork Dismantling |  | 35 | 35 | 2024-01-10 | 2024-02-13 | 100 | 100 | % | 100 | 12.59% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5.7143 | 5.714% | 25.7143 | 25.71% | 45.7143 | 45.71% | 65.7143 | 65.71% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
710 | Backfill with compaction |  | 35 | 35 | 2024-01-11 | 2024-02-14 | 100 | 100 | % | 100 | 12.59% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 2.8571 | 2.857% | 22.8571 | 22.86% | 42.8571 | 42.86% | 62.8571 | 62.86% | 82.8571 | 82.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
711 | Completion of Ground Beam |  | 0 | 1 | 2024-02-14 | 2024-02-14 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
712 | Completion of Structure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
713 | Equipment Foundation |  | 338 | 57 | 2023-12-21 | 2024-02-15 |  |  |  |  | 29.68% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.2959% |  | 5.917% |  | 16.57% |  | 31.95% |  | 52.37% |  | 72.49% |  | 86.39% |  | 95.56% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
714 | Equipment Foundation |  | 338 | 57 | 2023-12-21 | 2024-02-15 |  |  |  |  | 100% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.2959% |  | 5.917% |  | 16.57% |  | 31.95% |  | 52.37% |  | 72.49% |  | 86.39% |  | 95.56% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
715 | Excavation |  | 34 | 34 | 2023-12-21 | 2024-01-23 | 100 | 100 | % | 100 | 10.06% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 2.9412 | 2.941% | 23.5294 | 23.53% | 44.1176 | 44.12% | 64.7059 | 64.71% | 85.2941 | 85.29% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
716 | Leveling and Compaction |  | 34 | 34 | 2023-12-23 | 2024-01-25 | 100 | 100 | % | 100 | 10.06% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 17.6471 | 17.65% | 38.2353 | 38.24% | 58.8235 | 58.82% | 79.4118 | 79.41% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
717 | Lean Concrete Pouring |  | 33 | 33 | 2023-12-25 | 2024-01-26 | 100 | 100 | % | 100 | 9.763% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 12.1212 | 12.12% | 33.3333 | 33.33% | 54.5455 | 54.55% | 75.7576 | 75.76% | 96.9697 | 96.97% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
718 | Pile Cutting and Treatment |  | 34 | 34 | 2023-12-27 | 2024-01-29 | 100 | 100 | % | 100 | 10.06% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5.8824 | 5.882% | 26.4706 | 26.47% | 47.0588 | 47.06% | 67.6471 | 67.65% | 88.2353 | 88.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
719 | Reinforcement Bar Fixing |  | 34 | 34 | 2023-12-30 | 2024-02-01 | 100 | 100 | % | 100 | 10.06% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 17.6471 | 17.65% | 38.2353 | 38.24% | 58.8235 | 58.82% | 79.4118 | 79.41% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
720 | Formwork Fixing |  | 34 | 34 | 2024-01-03 | 2024-02-05 | 100 | 100 | % | 100 | 10.06% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 5.8824 | 5.882% | 26.4706 | 26.47% | 47.0588 | 47.06% | 67.6471 | 67.65% | 88.2353 | 88.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
721 | Anchor Bolt / Inserted Plate Fixing |  | 34 | 34 | 2024-01-05 | 2024-02-07 | 100 | 100 | % | 100 | 10.06% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 20.5882 | 20.59% | 41.1765 | 41.18% | 61.7647 | 61.76% | 82.3529 | 82.35% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
722 | Concrete Pouring |  | 33 | 33 | 2024-01-09 | 2024-02-10 | 100 | 100 | % | 100 | 9.763% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 9.0909 | 9.091% | 30.303 | 30.3% | 51.5152 | 51.52% | 72.7273 | 72.73% | 93.9394 | 93.94% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
723 | Formwork Dismantling |  | 34 | 34 | 2024-01-12 | 2024-02-14 | 100 | 100 | % | 100 | 10.06% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 20.5882 | 20.59% | 41.1765 | 41.18% | 61.7647 | 61.76% | 82.3529 | 82.35% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
724 | Backfill with compaction |  | 34 | 34 | 2024-01-13 | 2024-02-15 | 100 | 100 | % | 100 | 10.06% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 17.6471 | 17.65% | 38.2353 | 38.24% | 58.8235 | 58.82% | 79.4118 | 79.41% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
725 | Completion of Equipment Foundation |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
726 | Completion of Equipment and Pump Foundation |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
727 | Completion of Substructure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
728 | Completion of Unit 900 - HPU |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
729 | COMPLETION OF UNIT 700, 800 and 900 (SUBSTRUCTURE) |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
730 | UNIT FACILITIES (SUBSTRUCTURE) |  | 2471 | 78 | 2023-12-13 | 2024-02-28 |  |  |  |  | 21.96% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.3238% |  | 1.619% |  | 5.544% |  | 12.71% |  | 24.93% |  | 40.67% |  | 59.85% |  | 75.88% |  | 88.14% |  | 95.35% |  | 98.66% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
731 | Unit 250 - Pipe Rack within Facility |  | 943 | 78 | 2023-12-13 | 2024-02-28 |  |  |  |  | 38.16% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.2121% |  | 1.166% |  | 5.938% |  | 14% |  | 26.83% |  | 42.21% |  | 59.28% |  | 75.5% |  | 87.17% |  | 95.44% |  | 98.73% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
732 | Piling (Cutting only) |  | 7 | 7 | 2023-12-13 | 2023-12-19 |  |  |  |  | 0.7423% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 28.57% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
733 | Cutting off Pile to GL |  | 7 | 7 | 2023-12-13 | 2023-12-19 | 100 | 100 | % | 100 | 100% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 28.5714 | 28.57% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
734 | Completion of Piling |  | 0 | 1 | 2023-12-19 | 2023-12-19 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
735 | Substructure |  | 936 | 71 | 2023-12-20 | 2024-02-28 |  |  |  |  | 99.26% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.4274% |  | 5.235% |  | 13.35% |  | 26.28% |  | 41.77% |  | 58.97% |  | 75.32% |  | 87.07% |  | 95.41% |  | 98.72% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
736 | Structure |  | 936 | 71 | 2023-12-20 | 2024-02-28 |  |  |  |  | 100% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.4274% |  | 5.235% |  | 13.35% |  | 26.28% |  | 41.77% |  | 58.97% |  | 75.32% |  | 87.07% |  | 95.41% |  | 98.72% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
737 | Pile Cap |  | 365 | 60 | 2023-12-20 | 2024-02-17 |  |  |  |  | 39% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.5479% |  | 6.849% |  | 17.53% |  | 32.88% |  | 50.14% |  | 67.4% |  | 83.56% |  | 93.42% |  | 99.18% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
738 | Excavation |  | 41 | 41 | 2023-12-20 | 2024-01-29 | 100 | 100 | % | 100 | 11.23% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4.878 | 4.878% | 21.9512 | 21.95% | 39.0244 | 39.02% | 56.0976 | 56.1% | 73.1707 | 73.17% | 90.2439 | 90.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
739 | Leveling and Compaction |  | 41 | 41 | 2023-12-22 | 2024-01-31 | 100 | 100 | % | 100 | 11.23% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 17.0732 | 17.07% | 34.1463 | 34.15% | 51.2195 | 51.22% | 68.2927 | 68.29% | 85.3659 | 85.37% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
740 | Lean Concrete Pouring |  | 41 | 41 | 2023-12-23 | 2024-02-01 | 100 | 100 | % | 100 | 11.23% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.6341 | 14.63% | 31.7073 | 31.71% | 48.7805 | 48.78% | 65.8537 | 65.85% | 82.9268 | 82.93% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
741 | Pile Cutting and Treatment |  | 40 | 40 | 2023-12-26 | 2024-02-03 | 100 | 100 | % | 100 | 10.96% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.5 | 7.5% | 25 | 25% | 42.5 | 42.5% | 60 | 60% | 77.5 | 77.5% | 95 | 95% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
742 | Reinforcement Bar Fixing |  | 41 | 41 | 2023-12-29 | 2024-02-07 | 100 | 100 | % | 100 | 11.23% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 17.0732 | 17.07% | 34.1463 | 34.15% | 51.2195 | 51.22% | 68.2927 | 68.29% | 85.3659 | 85.37% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
743 | Formwork Fixing |  | 40 | 40 | 2024-01-02 | 2024-02-10 | 100 | 100 | % | 100 | 10.96% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.5 | 7.5% | 25 | 25% | 42.5 | 42.5% | 60 | 60% | 77.5 | 77.5% | 95 | 95% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
744 | Concrete Pouring |  | 41 | 41 | 2024-01-04 | 2024-02-13 | 100 | 100 | % | 100 | 11.23% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 2.439 | 2.439% | 19.5122 | 19.51% | 36.5854 | 36.59% | 53.6585 | 53.66% | 70.7317 | 70.73% | 87.8049 | 87.8% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
745 | Formwork Dismantling |  | 40 | 40 | 2024-01-08 | 2024-02-16 | 100 | 100 | % | 100 | 10.96% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 10 | 10% | 27.5 | 27.5% | 45 | 45% | 62.5 | 62.5% | 80 | 80% | 97.5 | 97.5% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
746 | Backfill with compaction |  | 40 | 40 | 2024-01-09 | 2024-02-17 | 100 | 100 | % | 100 | 10.96% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.5 | 7.5% | 25 | 25% | 42.5 | 42.5% | 60 | 60% | 77.5 | 77.5% | 95 | 95% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
747 | Completion of Pile Cap |  | 0 | 1 | 2024-02-17 | 2024-02-17 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
748 | Stump |  | 244 | 54 | 2024-01-06 | 2024-02-28 |  |  |  |  | 26.07% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 4.098% |  | 14.75% |  | 31.97% |  | 49.18% |  | 66.39% |  | 83.61% |  | 95.08% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
749 | Reinforcement Bar Fixing |  | 41 | 41 | 2024-01-06 | 2024-02-15 | 100 | 100 | % | 100 | 16.8% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.6341 | 14.63% | 31.7073 | 31.71% | 48.7805 | 48.78% | 65.8537 | 65.85% | 82.9268 | 82.93% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
750 | Formwork Fixing |  | 40 | 40 | 2024-01-09 | 2024-02-17 | 100 | 100 | % | 100 | 16.39% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.5 | 7.5% | 25 | 25% | 42.5 | 42.5% | 60 | 60% | 77.5 | 77.5% | 95 | 95% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
751 | Anchor Bolt Fixing |  | 41 | 41 | 2024-01-11 | 2024-02-20 | 100 | 100 | % | 100 | 16.8% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 2.439 | 2.439% | 19.5122 | 19.51% | 36.5854 | 36.59% | 53.6585 | 53.66% | 70.7317 | 70.73% | 87.8049 | 87.8% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
752 | Concrete Pouring |  | 40 | 40 | 2024-01-15 | 2024-02-23 | 100 | 100 | % | 100 | 16.39% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 10 | 10% | 27.5 | 27.5% | 45 | 45% | 62.5 | 62.5% | 80 | 80% | 97.5 | 97.5% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
753 | Formwork Dismantling |  | 41 | 41 | 2024-01-18 | 2024-02-27 | 100 | 100 | % | 100 | 16.8% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 2.439 | 2.439% | 19.5122 | 19.51% | 36.5854 | 36.59% | 53.6585 | 53.66% | 70.7317 | 70.73% | 87.8049 | 87.8% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
754 | Backfill with compaction |  | 41 | 41 | 2024-01-19 | 2024-02-28 | 100 | 100 | % | 100 | 16.8% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 17.0732 | 17.07% | 34.1463 | 34.15% | 51.2195 | 51.22% | 68.2927 | 68.29% | 85.3659 | 85.37% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
755 | Completion of Stump |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
756 | Ground Beam |  | 327 | 58 | 2023-12-20 | 2024-02-15 |  |  |  |  | 34.94% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.6116% |  | 7.339% |  | 18.65% |  | 35.47% |  | 52.6% |  | 69.72% |  | 85.63% |  | 95.41% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
757 | Excavation |  | 41 | 41 | 2023-12-20 | 2024-01-29 | 100 | 100 | % | 100 | 12.54% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4.878 | 4.878% | 21.9512 | 21.95% | 39.0244 | 39.02% | 56.0976 | 56.1% | 73.1707 | 73.17% | 90.2439 | 90.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
758 | Leveling and Compaction |  | 41 | 41 | 2023-12-22 | 2024-01-31 | 100 | 100 | % | 100 | 12.54% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 17.0732 | 17.07% | 34.1463 | 34.15% | 51.2195 | 51.22% | 68.2927 | 68.29% | 85.3659 | 85.37% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
759 | Lean Concrete Pouring |  | 41 | 41 | 2023-12-23 | 2024-02-01 | 100 | 100 | % | 100 | 12.54% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.6341 | 14.63% | 31.7073 | 31.71% | 48.7805 | 48.78% | 65.8537 | 65.85% | 82.9268 | 82.93% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
760 | Reinforcement Bar Fixing |  | 41 | 41 | 2023-12-27 | 2024-02-05 | 100 | 100 | % | 100 | 12.54% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4.878 | 4.878% | 21.9512 | 21.95% | 39.0244 | 39.02% | 56.0976 | 56.1% | 73.1707 | 73.17% | 90.2439 | 90.24% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
761 | Formwork Fixing |  | 41 | 41 | 2023-12-30 | 2024-02-08 | 100 | 100 | % | 100 | 12.54% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.6341 | 14.63% | 31.7073 | 31.71% | 48.7805 | 48.78% | 65.8537 | 65.85% | 82.9268 | 82.93% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
762 | Concrete Pouring |  | 40 | 40 | 2024-01-02 | 2024-02-10 | 100 | 100 | % | 100 | 12.23% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.5 | 7.5% | 25 | 25% | 42.5 | 42.5% | 60 | 60% | 77.5 | 77.5% | 95 | 95% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
763 | Formwork Dismantling |  | 41 | 41 | 2024-01-05 | 2024-02-14 | 100 | 100 | % | 100 | 12.54% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 17.0732 | 17.07% | 34.1463 | 34.15% | 51.2195 | 51.22% | 68.2927 | 68.29% | 85.3659 | 85.37% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
764 | Backfill with compaction |  | 41 | 41 | 2024-01-06 | 2024-02-15 | 100 | 100 | % | 100 | 12.54% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.6341 | 14.63% | 31.7073 | 31.71% | 48.7805 | 48.78% | 65.8537 | 65.85% | 82.9268 | 82.93% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
765 | Completion of Ground Beam |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
766 | Completion of Structure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
767 | Completion of Substructure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
768 | Completion of Unit 250 - Pipe Rack Within Facility |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
769 | Unit 310 - City Water Tank |  | 277 | 78 | 2023-12-13 | 2024-02-28 |  |  |  |  | 11.21% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.722% |  | 3.249% |  | 10.83% |  | 16.61% |  | 28.52% |  | 44.4% |  | 65.7% |  | 79.78% |  | 90.61% |  | 96.03% |  | 97.83% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
770 | Piling (Cutting only) |  | 7 | 7 | 2023-12-13 | 2023-12-19 |  |  |  |  | 2.527% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 28.57% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
771 | Cutting off Pile to GL |  | 7 | 7 | 2023-12-13 | 2023-12-19 | 100 | 100 | % | 100 | 100% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 28.5714 | 28.57% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
772 | Completion of Piling |  | 0 | 1 | 2023-12-19 | 2023-12-19 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
773 | Substructure |  | 270 | 71 | 2023-12-20 | 2024-02-28 |  |  |  |  | 97.47% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.7407% |  | 8.519% |  | 14.44% |  | 26.67% |  | 42.96% |  | 64.81% |  | 79.26% |  | 90.37% |  | 95.93% |  | 97.78% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
774 | Structure |  | 157 | 55 | 2023-12-20 | 2024-02-12 |  |  |  |  | 58.15% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 1.274% |  | 14.65% |  | 24.84% |  | 42.04% |  | 56.05% |  | 74.52% |  | 85.35% |  | 96.18% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
775 | Pile Cap |  | 62 | 27 | 2023-12-20 | 2024-01-15 |  |  |  |  | 39.49% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 3.226% |  | 37.1% |  | 62.9% |  | 90.32% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
776 | Excavation |  | 7 | 7 | 2023-12-20 | 2023-12-26 | 100 | 100 | % | 100 | 11.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 28.5714 | 28.57% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
777 | Leveling and Compaction |  | 7 | 7 | 2023-12-22 | 2023-12-28 | 100 | 100 | % | 100 | 11.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
778 | Lean Concrete Pouring |  | 7 | 7 | 2023-12-23 | 2023-12-29 | 100 | 100 | % | 100 | 11.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
779 | Pile Cutting and Treatment |  | 7 | 7 | 2023-12-26 | 2024-01-01 | 100 | 100 | % | 100 | 11.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
780 | Reinforcement Bar Fixing |  | 7 | 7 | 2023-12-29 | 2024-01-04 | 100 | 100 | % | 100 | 11.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
781 | Formwork Fixing |  | 7 | 7 | 2024-01-02 | 2024-01-08 | 100 | 100 | % | 100 | 11.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
782 | Concrete Pouring |  | 7 | 7 | 2024-01-04 | 2024-01-10 | 100 | 100 | % | 100 | 11.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
783 | Formwork Dismantling |  | 6 | 6 | 2024-01-08 | 2024-01-13 | 100 | 100 | % | 100 | 9.677% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
784 | Backfill with compaction |  | 7 | 7 | 2024-01-09 | 2024-01-15 | 100 | 100 | % | 100 | 11.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
785 | Completion of Pile Cap |  | 0 | 1 | 2024-01-15 | 2024-01-15 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
786 | Stump |  | 41 | 20 | 2024-01-06 | 2024-01-25 |  |  |  |  | 26.11% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 24.39% |  | 63.41% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
787 | Reinforcement Bar Fixing |  | 7 | 7 | 2024-01-06 | 2024-01-12 | 100 | 100 | % | 100 | 17.07% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
788 | Formwork Fixing |  | 7 | 7 | 2024-01-09 | 2024-01-15 | 100 | 100 | % | 100 | 17.07% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
789 | Anchor Bolt Fixing |  | 7 | 7 | 2024-01-11 | 2024-01-17 | 100 | 100 | % | 100 | 17.07% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
790 | Concrete Pouring |  | 6 | 6 | 2024-01-15 | 2024-01-20 | 100 | 100 | % | 100 | 14.63% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
791 | Formwork Dismantling |  | 7 | 7 | 2024-01-18 | 2024-01-24 | 100 | 100 | % | 100 | 17.07% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
792 | Backfill with compaction |  | 7 | 7 | 2024-01-19 | 2024-01-25 | 100 | 100 | % | 100 | 17.07% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
793 | Completion of Stump |  | 0 | 1 | 2024-01-25 | 2024-01-25 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
794 | Ground Beam |  | 54 | 25 | 2024-01-19 | 2024-02-12 |  |  |  |  | 34.39% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 25.93% |  | 57.41% |  | 88.89% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
795 | Excavation |  | 7 | 7 | 2024-01-19 | 2024-01-25 | 100 | 100 | % | 100 | 12.96% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
796 | Leveling and Compaction |  | 6 | 6 | 2024-01-22 | 2024-01-27 | 100 | 100 | % | 100 | 11.11% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
797 | Lean Concrete Pouring |  | 7 | 7 | 2024-01-23 | 2024-01-29 | 100 | 100 | % | 100 | 12.96% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
798 | Reinforcement Bar Fixing |  | 7 | 7 | 2024-01-26 | 2024-02-01 | 100 | 100 | % | 100 | 12.96% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
799 | Formwork Fixing |  | 7 | 7 | 2024-01-30 | 2024-02-05 | 100 | 100 | % | 100 | 12.96% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
800 | Concrete Pouring |  | 7 | 7 | 2024-02-01 | 2024-02-07 | 100 | 100 | % | 100 | 12.96% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
801 | Formwork Dismantling |  | 6 | 6 | 2024-02-05 | 2024-02-10 | 100 | 100 | % | 100 | 11.11% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
802 | Backfill with compaction |  | 7 | 7 | 2024-02-06 | 2024-02-12 | 100 | 100 | % | 100 | 12.96% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
803 | Completion of Ground Beam |  | 0 | 1 | 2024-02-12 | 2024-02-12 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
804 | Completion of Structure |  | 0 | 1 | 2024-02-12 | 2024-02-12 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
805 | Tank / Equipment and Pump Foundation |  | 113 | 51 | 2024-01-09 | 2024-02-28 |  |  |  |  | 41.85% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 5.31% |  | 24.78% |  | 51.33% |  | 70.8% |  | 82.3% |  | 90.27% |  | 94.69% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
806 | City Water Tank T3101 |  | 73 | 51 | 2024-01-09 | 2024-02-28 |  |  |  |  | 64.6% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 8.219% |  | 38.36% |  | 57.53% |  | 68.49% |  | 80.82% |  | 84.93% |  | 91.78% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
807 | Excavation |  | 10 | 10 | 2024-01-09 | 2024-01-18 | 100 | 100 | % | 100 | 13.7% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 30 | 30% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
808 | Leveling and Compaction |  | 10 | 10 | 2024-01-09 | 2024-01-18 | 100 | 100 | % | 100 | 13.7% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 30 | 30% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
809 | Lean Concrete Pouring |  | 11 | 11 | 2024-01-12 | 2024-01-22 | 100 | 100 | % | 100 | 15.07% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 63.6364 | 63.64% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
810 | Pile Cutting and Treatment |  | 7 | 7 | 2024-01-18 | 2024-01-24 | 100 | 100 | % | 100 | 9.589% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
811 | Reinforcement Bar Fixing |  | 13 | 13 | 2024-01-22 | 2024-02-03 | 100 | 100 | % | 100 | 17.81% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 30.7692 | 30.77% | 84.6154 | 84.62% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
812 | Formwork Fixing |  | 7 | 7 | 2024-02-01 | 2024-02-07 | 100 | 100 | % | 100 | 9.589% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
813 | Anchor Bolt / Inserted Plate Fixing |  | 3 | 3 | 2024-02-08 | 2024-02-10 | 100 | 100 | % | 100 | 4.11% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
814 | Concrete Pouring |  | 1 | 1 | 2024-02-12 | 2024-02-12 | 100 | 100 | % | 100 | 1.37% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
815 | Formwork Dismantling |  | 4 | 4 | 2024-02-16 | 2024-02-19 | 100 | 100 | % | 100 | 5.479% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
816 | Backfill with compaction |  | 7 | 7 | 2024-02-22 | 2024-02-28 | 100 | 100 | % | 100 | 9.589% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
817 | Completion of City Water Tank |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
818 | Surge Transfer Water Tank T3107 |  | 20 | 25 | 2024-01-19 | 2024-02-12 |  |  |  |  | 17.7% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 40% |  | 75% |  | 85% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
819 | Excavation |  | 2 | 2 | 2024-01-19 | 2024-01-20 | 100 | 100 | % | 100 | 10% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
820 | Leveling and Compaction |  | 2 | 2 | 2024-01-19 | 2024-01-20 | 100 | 100 | % | 100 | 10% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
821 | Lean Concrete Pouring |  | 1 | 1 | 2024-01-22 | 2024-01-22 | 100 | 100 | % | 100 | 5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
822 | Pile Cutting and Treatment |  | 2 | 2 | 2024-01-23 | 2024-01-24 | 100 | 100 | % | 100 | 10% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
823 | Reinforcement Bar Fixing |  | 5 | 5 | 2024-01-25 | 2024-01-29 | 100 | 100 | % | 100 | 25% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 20 | 20% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
824 | Formwork Fixing |  | 1 | 1 | 2024-01-30 | 2024-01-30 | 100 | 100 | % | 100 | 5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
825 | Anchor Bolt / Inserted Plate Fixing |  | 2 | 2 | 2024-01-31 | 2024-02-01 | 100 | 100 | % | 100 | 10% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
826 | Concrete Pouring |  | 1 | 1 | 2024-02-02 | 2024-02-02 | 100 | 100 | % | 100 | 5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
827 | Formwork Dismantling |  | 1 | 1 | 2024-02-07 | 2024-02-07 | 100 | 100 | % | 100 | 5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
828 | Backfill with compaction |  | 3 | 3 | 2024-02-10 | 2024-02-12 | 100 | 100 | % | 100 | 15% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
829 | Completion of Surge Transfer Water Tank |  | 0 | 1 | 2024-02-12 | 2024-02-12 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
830 | City Water Tank Pump Plinth |  | 20 | 25 | 2024-01-19 | 2024-02-12 |  |  |  |  | 17.7% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 40% |  | 75% |  | 85% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
831 | Excavation |  | 2 | 2 | 2024-01-19 | 2024-01-20 | 100 | 100 | % | 100 | 10% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
832 | Leveling and Compaction |  | 2 | 2 | 2024-01-19 | 2024-01-20 | 100 | 100 | % | 100 | 10% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
833 | Lean Concrete Pouring |  | 1 | 1 | 2024-01-22 | 2024-01-22 | 100 | 100 | % | 100 | 5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
834 | Pile Cutting and Treatment |  | 2 | 2 | 2024-01-23 | 2024-01-24 | 100 | 100 | % | 100 | 10% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
835 | Reinforcement Bar Fixing |  | 5 | 5 | 2024-01-25 | 2024-01-29 | 100 | 100 | % | 100 | 25% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 20 | 20% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
836 | Formwork Fixing |  | 1 | 1 | 2024-01-30 | 2024-01-30 | 100 | 100 | % | 100 | 5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
837 | Anchor Bolt / Inserted Plate Fixing |  | 2 | 2 | 2024-01-31 | 2024-02-01 | 100 | 100 | % | 100 | 10% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
838 | Concrete Pouring |  | 1 | 1 | 2024-02-02 | 2024-02-02 | 100 | 100 | % | 100 | 5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
839 | Formwork Dismantling |  | 1 | 1 | 2024-02-07 | 2024-02-07 | 100 | 100 | % | 100 | 5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
840 | Backfill with compaction |  | 3 | 3 | 2024-02-10 | 2024-02-12 | 100 | 100 | % | 100 | 15% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
841 | Completion of Surge Transfer Water Tank |  | 0 | 1 | 2024-02-12 | 2024-02-12 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
842 | Completion of Tank / Equipment and Pump Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
843 | Completion of Substructure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
844 | Completion of Unit 310 - City Water Tank |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
845 | Unit 310 - Water Treatment |  | 201 | 71 | 2023-12-20 | 2024-02-28 |  |  |  |  | 8.134% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.995% |  | 4.478% |  | 15.92% |  | 33.33% |  | 52.74% |  | 72.14% |  | 81.09% |  | 88.06% |  | 93.03% |  | 98.01% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
846 | Piling (Cutting only) |  | 7 | 7 | 2023-12-20 | 2023-12-26 |  |  |  |  | 3.483% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 28.57% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
847 | Cutting off Pile to GL |  | 7 | 7 | 2023-12-20 | 2023-12-26 | 100 | 100 | % | 100 | 100% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 28.5714 | 28.57% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
848 | Completion of Piling |  | 0 | 1 | 2023-12-26 | 2023-12-26 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
849 | Substructure |  | 194 | 64 | 2023-12-27 | 2024-02-28 |  |  |  |  | 96.52% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 1.031% |  | 12.89% |  | 30.93% |  | 51.03% |  | 71.13% |  | 80.41% |  | 87.63% |  | 92.78% |  | 97.94% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
850 | Structure |  | 124 | 55 | 2023-12-27 | 2024-02-19 |  |  |  |  | 63.92% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 1.613% |  | 20.16% |  | 48.39% |  | 77.42% |  | 95.97% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
851 | Pile Raft |  | 117 | 27 | 2023-12-27 | 2024-01-22 |  |  |  |  | 94.35% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 1.709% |  | 21.37% |  | 51.28% |  | 76.92% |  | 95.73% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
852 | Excavation |  | 13 | 13 | 2023-12-27 | 2024-01-08 | 100 | 100 | % | 100 | 11.11% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 15.3846 | 15.38% | 69.2308 | 69.23% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
853 | Leveling and Compaction |  | 13 | 13 | 2023-12-29 | 2024-01-10 | 100 | 100 | % | 100 | 11.11% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 53.8462 | 53.85% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
854 | Lean Concrete Pouring |  | 13 | 13 | 2023-12-30 | 2024-01-11 | 100 | 100 | % | 100 | 11.11% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 46.1538 | 46.15% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
855 | Pile Cutting and Treatment |  | 13 | 13 | 2024-01-02 | 2024-01-14 | 100 | 100 | % | 100 | 11.11% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 23.0769 | 23.08% | 76.9231 | 76.92% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
856 | Reinforcement Bar Fixing |  | 13 | 13 | 2024-01-05 | 2024-01-17 | 100 | 100 | % | 100 | 11.11% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 53.8462 | 53.85% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
857 | Formwork Fixing |  | 13 | 13 | 2024-01-09 | 2024-01-21 | 100 | 100 | % | 100 | 11.11% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 23.0769 | 23.08% | 76.9231 | 76.92% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
858 | Concrete Pouring |  | 13 | 13 | 2024-01-11 | 2024-01-23 | 100 | 100 | % | 100 | 11.11% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.6923 | 7.692% | 61.5385 | 61.54% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
859 | Formwork Dismantling |  | 12 | 12 | 2024-01-15 | 2024-01-26 | 100 | 100 | % | 100 | 10.26% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 91.6667 | 91.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
860 | Backfill with compaction |  | 14 | 14 | 2024-01-16 | 2024-01-29 | 100 | 100 | % | 100 | 11.97% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 21.4286 | 21.43% | 71.4286 | 71.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
861 | Completion of Pile Cap |  | 0 | 1 | 2024-01-28 | 2024-01-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
862 | Column | Reinforcemet Bar only (Starter Bar) | 7 | 20 | 2024-01-13 | 2024-02-01 |  |  |  |  | 5.645% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 85.71% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
863 | Reinforcement Bar Fixing |  | 7 | 7 | 2024-01-13 | 2024-01-19 | 100 | 100 | % | 100 | 100% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
864 | Completion of Stump |  | 0 | 1 | 2024-02-01 | 2024-02-01 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
865 | Completion of Structure |  | 0 | 1 | 2024-02-19 | 2024-02-19 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
866 | Tank / Equipment and Pump Foundation |  | 70 | 44 | 2024-01-16 | 2024-02-28 |  |  |  |  | 36.08% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 4.286% |  | 27.14% |  | 45.71% |  | 65.71% |  | 80% |  | 94.29% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
867 | Tank T3104 |  | 44 | 44 | 2024-01-16 | 2024-02-28 |  |  |  |  | 62.86% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 6.818% |  | 29.55% |  | 45.45% |  | 61.36% |  | 77.27% |  | 90.91% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
868 | Excavation |  | 7 | 7 | 2024-01-16 | 2024-01-22 | 100 | 100 | % | 100 | 15.91% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
869 | Leveling and Compaction |  | 4 | 4 | 2024-01-20 | 2024-01-23 | 100 | 100 | % | 100 | 9.091% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
870 | Lean Concrete Pouring |  | 2 | 2 | 2024-01-24 | 2024-01-25 | 100 | 100 | % | 100 | 4.545% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
871 | Base |  | 13 | 13 | 2024-01-26 | 2024-02-07 |  |  |  |  | 29.55% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 53.85% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
872 | Reinforcement Bar Fixing |  | 8 | 8 | 2024-01-26 | 2024-02-02 | 100 | 100 | % | 100 | 61.54% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 87.5 | 87.5% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
873 | Formwork Fixing |  | 4 | 4 | 2024-02-03 | 2024-02-06 | 100 | 100 | % | 100 | 30.77% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
874 | Concrete Pouring |  | 1 | 1 | 2024-02-07 | 2024-02-07 | 100 | 100 | % | 100 | 7.692% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
875 | Tank Ring |  | 14 | 14 | 2024-02-08 | 2024-02-21 |  |  |  |  | 31.82% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 7.143% |  | 57.14% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
876 | Reinforcement Bar Fixing |  | 8 | 8 | 2024-02-08 | 2024-02-15 | 100 | 100 | % | 100 | 57.14% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 12.5 | 12.5% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
877 | Formwork Fixing |  | 5 | 5 | 2024-02-16 | 2024-02-20 | 100 | 100 | % | 100 | 35.71% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
878 | Concrete Pouring |  | 1 | 1 | 2024-02-21 | 2024-02-21 | 100 | 100 | % | 100 | 7.143% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
879 | Formwork Dismantling |  | 1 | 1 | 2024-02-24 | 2024-02-24 | 100 | 100 | % | 100 | 2.273% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
880 | Backfill with compaction |  | 3 | 3 | 2024-02-26 | 2024-02-28 | 100 | 100 | % | 100 | 6.818% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
881 | Completion of Tank T3104 |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
882 | Tank T3102 and T3103 |  | 26 | 31 | 2024-01-23 | 2024-02-22 |  |  |  |  | 37.14% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 23.08% |  | 46.15% |  | 73.08% |  | 84.62% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
883 | Excavation |  | 3 | 3 | 2024-01-23 | 2024-01-25 | 100 | 100 | % | 100 | 11.54% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
884 | Leveling and Compaction |  | 3 | 3 | 2024-01-23 | 2024-01-25 | 100 | 100 | % | 100 | 11.54% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
885 | Lean Concrete Pouring |  | 2 | 2 | 2024-01-26 | 2024-01-27 | 100 | 100 | % | 100 | 7.692% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
886 | Pile Cutting and Treatment |  | 2 | 2 | 2024-01-29 | 2024-01-30 | 100 | 100 | % | 100 | 7.692% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
887 | Reinforcement Bar Fixing |  | 7 | 7 | 2024-01-31 | 2024-02-06 | 100 | 100 | % | 100 | 26.92% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 28.5714 | 28.57% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
888 | Formwork Fixing |  | 2 | 2 | 2024-02-07 | 2024-02-08 | 100 | 100 | % | 100 | 7.692% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
889 | Anchor Bolt / Inserted Plate Fixing |  | 2 | 2 | 2024-02-09 | 2024-02-10 | 100 | 100 | % | 100 | 7.692% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
890 | Concrete Pouring |  | 1 | 1 | 2024-02-12 | 2024-02-12 | 100 | 100 | % | 100 | 3.846% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
891 | Formwork Dismantling |  | 1 | 1 | 2024-02-16 | 2024-02-16 | 100 | 100 | % | 100 | 3.846% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
892 | Backfill with compaction |  | 3 | 3 | 2024-02-20 | 2024-02-22 | 100 | 100 | % | 100 | 11.54% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
893 | Completion of Tank T3102 and T3103 |  | 0 | 1 | 2024-02-22 | 2024-02-22 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
894 | Completion of Tank / Equipment and Pump Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
895 | Completion of Substructure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
896 | Completion of Unit 310 - Water Treatment |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
897 | Unit 330 - Cooling Tower |  | 139 | 49 | 2024-01-03 | 2024-02-20 |  |  |  |  | 5.625% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 1.439% |  | 14.39% |  | 40.29% |  | 66.19% |  | 89.21% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
898 | Piling (Cutting only) |  | 14 | 14 | 2024-01-03 | 2024-01-16 |  |  |  |  | 10.07% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 14.29% |  | 64.29% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
899 | Cutting off Pile to GL |  | 14 | 14 | 2024-01-03 | 2024-01-16 | 100 | 100 | % | 100 | 100% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 64.2857 | 64.29% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
900 | Completion of Piling |  | 0 | 1 | 2024-01-16 | 2024-01-16 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
901 | Substructure |  | 125 | 46 | 2024-01-06 | 2024-02-20 |  |  |  |  | 89.93% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 8.8% |  | 33.6% |  | 62.4% |  | 88% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
902 | Pile Raft |  | 125 | 34 | 2024-01-06 | 2024-02-08 |  |  |  |  | 100% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 8.8% |  | 33.6% |  | 62.4% |  | 88% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
903 | Excavation |  | 14 | 14 | 2024-01-06 | 2024-01-19 | 100 | 100 | % | 100 | 11.2% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 92.8571 | 92.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
904 | Leveling and Compaction |  | 14 | 14 | 2024-01-09 | 2024-01-22 | 100 | 100 | % | 100 | 11.2% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 21.4286 | 21.43% | 71.4286 | 71.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
905 | Lean Concrete Pouring |  | 14 | 14 | 2024-01-10 | 2024-01-23 | 100 | 100 | % | 100 | 11.2% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 64.2857 | 64.29% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
906 | Pile Cutting and Treatment |  | 14 | 14 | 2024-01-12 | 2024-01-25 | 100 | 100 | % | 100 | 11.2% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 50 | 50% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
907 | Reinforcement Bar Fixing |  | 14 | 14 | 2024-01-16 | 2024-01-29 | 100 | 100 | % | 100 | 11.2% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 21.4286 | 21.43% | 71.4286 | 71.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
908 | Formwork Fixing |  | 14 | 14 | 2024-01-19 | 2024-02-01 | 100 | 100 | % | 100 | 11.2% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 50 | 50% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
909 | Concrete Pouring |  | 13 | 13 | 2024-01-22 | 2024-02-03 | 100 | 100 | % | 100 | 10.4% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 30.7692 | 30.77% | 84.6154 | 84.62% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
910 | Formwork Dismantling |  | 14 | 14 | 2024-01-25 | 2024-02-07 | 100 | 100 | % | 100 | 11.2% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.1429 | 7.143% | 57.1429 | 57.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
911 | Backfill with compaction |  | 14 | 14 | 2024-01-26 | 2024-02-08 | 100 | 100 | % | 100 | 11.2% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 50 | 50% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
912 | Completion of Pile Raft |  | 0 | 1 | 2024-02-08 | 2024-02-08 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
913 | Completion of Substructure |  | 0 | 1 | 2024-02-20 | 2024-02-20 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
914 | Completion of Unit 330 - Cooling Tower |  | 0 | 1 | 2024-02-20 | 2024-02-20 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
915 | Unit 340 - Instrument Air & Plant Air System |  | 189 | 72 | 2023-12-13 | 2024-02-22 |  |  |  |  | 7.649% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 1.058% |  | 4.762% |  | 9.524% |  | 20.63% |  | 32.8% |  | 44.44% |  | 62.43% |  | 77.78% |  | 89.42% |  | 95.77% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
916 | Piling (Cutting only) |  | 14 | 14 | 2023-12-13 | 2023-12-26 |  |  |  |  | 7.407% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 14.29% |  | 64.29% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
917 | Cutting off Pile to GL |  | 14 | 14 | 2023-12-13 | 2023-12-26 | 100 | 100 | % | 100 | 100% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 64.2857 | 64.29% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
918 | Completion of Piling |  | 0 | 1 | 2023-12-26 | 2023-12-26 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
919 | Substructure |  | 175 | 58 | 2023-12-27 | 2024-02-22 |  |  |  |  | 92.59% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 2.286% |  | 14.29% |  | 27.43% |  | 40% |  | 59.43% |  | 76% |  | 88.57% |  | 95.43% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
920 | Equipment Foundation |  | 175 | 58 | 2023-12-27 | 2024-02-22 |  |  |  |  | 100% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 2.286% |  | 14.29% |  | 27.43% |  | 40% |  | 59.43% |  | 76% |  | 88.57% |  | 95.43% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
921 | V3401 and V3402 |  | 35 | 38 | 2023-12-27 | 2024-02-02 |  |  |  |  | 20% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 11.43% |  | 34.29% |  | 54.29% |  | 74.29% |  | 88.57% |  | 97.14% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
922 | Excavation |  | 4 | 4 | 2023-12-27 | 2023-12-30 | 100 | 100 | % | 100 | 11.43% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 50 | 50% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
923 | Leveling and Compaction |  | 4 | 4 | 2023-12-27 | 2023-12-30 | 100 | 100 | % | 100 | 11.43% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 50 | 50% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
924 | Lean Concrete Pouring |  | 2 | 2 | 2024-01-01 | 2024-01-02 | 100 | 100 | % | 100 | 5.714% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
925 | Pile Cutting and Treatment |  | 3 | 3 | 2024-01-03 | 2024-01-05 | 100 | 100 | % | 100 | 8.571% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
926 | Reinforcement Bar Fixing |  | 10 | 10 | 2024-01-06 | 2024-01-15 | 100 | 100 | % | 100 | 28.57% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 60 | 60% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
927 | Formwork Fixing |  | 2 | 2 | 2024-01-16 | 2024-01-17 | 100 | 100 | % | 100 | 5.714% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
928 | Anchor Bolt / Inserted Plate Fixing |  | 2 | 2 | 2024-01-18 | 2024-01-19 | 100 | 100 | % | 100 | 5.714% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 50 | 50% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
929 | Concrete Pouring |  | 4 | 4 | 2024-01-20 | 2024-01-23 | 100 | 100 | % | 100 | 11.43% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
930 | Formwork Dismantling |  | 1 | 1 | 2024-01-27 | 2024-01-27 | 100 | 100 | % | 100 | 2.857% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
931 | Backfill with compaction |  | 3 | 3 | 2024-01-31 | 2024-02-02 | 100 | 100 | % | 100 | 8.571% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
932 | Completion of V3401 and V3402 |  | 0 | 1 | 2024-02-02 | 2024-02-02 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
933 | K3401 A/B/C |  | 37 | 45 | 2024-01-01 | 2024-02-14 |  |  |  |  | 21.14% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 18.92% |  | 37.84% |  | 54.05% |  | 70.27% |  | 89.19% |  | 89.19% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
934 | Foundation |  | 23 | 22 | 2024-01-01 | 2024-01-22 |  |  |  |  | 62.16% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 30.43% |  | 60.87% |  | 86.96% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
935 | Excavation |  | 3 | 3 | 2024-01-01 | 2024-01-03 | 100 | 100 | % | 100 | 13.04% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
936 | Leveling and Compaction |  | 3 | 3 | 2024-01-01 | 2024-01-03 | 100 | 100 | % | 100 | 13.04% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
937 | Lean Concrete Pouring |  | 2 | 2 | 2024-01-04 | 2024-01-05 | 100 | 100 | % | 100 | 8.696% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 50 | 50% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
938 | Reinforcement Bar Fixing |  | 8 | 8 | 2024-01-06 | 2024-01-13 | 100 | 100 | % | 100 | 34.78% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 75 | 75% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
939 | Anchor Bolt / Inserted Plate Fixing |  | 3 | 3 | 2024-01-15 | 2024-01-17 | 100 | 100 | % | 100 | 13.04% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
940 | Formwork Fixing |  | 3 | 3 | 2024-01-18 | 2024-01-20 | 100 | 100 | % | 100 | 13.04% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
941 | Concrete Pouring |  | 1 | 1 | 2024-01-22 | 2024-01-22 | 100 | 100 | % | 100 | 4.348% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
942 | Plinth |  | 10 | 10 | 2024-01-23 | 2024-02-01 |  |  |  |  | 27.03% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 30% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
943 | Reinforcement Bar Fixing |  | 4 | 4 | 2024-01-23 | 2024-01-26 | 100 | 100 | % | 100 | 40% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 75 | 75% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
944 | Formwork Fixing |  | 5 | 5 | 2024-01-27 | 2024-01-31 | 100 | 100 | % | 100 | 50% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
945 | Concrete Pouring |  | 1 | 1 | 2024-02-01 | 2024-02-01 | 100 | 100 | % | 100 | 10% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
946 | Formwork Dismantling |  | 1 | 1 | 2024-02-10 | 2024-02-10 | 100 | 100 | % | 100 | 2.703% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
947 | Backfill with compaction |  | 3 | 3 | 2024-02-12 | 2024-02-14 | 100 | 100 | % | 100 | 8.108% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
948 | Completion of K3401 A/B/C |  | 0 | 1 | 2024-02-14 | 2024-02-14 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
949 | F3405 A/B/C |  | 73 | 37 | 2024-01-01 | 2024-02-06 |  |  |  |  | 41.71% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 8.219% |  | 20.55% |  | 32.88% |  | 64.38% |  | 87.67% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
950 | Pile Cap and Ground Beam |  | 31 | 23 | 2024-01-01 | 2024-01-23 |  |  |  |  | 42.47% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 19.35% |  | 48.39% |  | 74.19% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
951 | Excavation |  | 3 | 3 | 2024-01-01 | 2024-01-03 | 100 | 100 | % | 100 | 9.677% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
952 | Leveling and Compaction |  | 3 | 3 | 2024-01-03 | 2024-01-05 | 100 | 100 | % | 100 | 9.677% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
953 | Lean Concrete Pouring |  | 3 | 3 | 2024-01-04 | 2024-01-06 | 100 | 100 | % | 100 | 9.677% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
954 | Pile Cutting and Treatment |  | 4 | 4 | 2024-01-06 | 2024-01-09 | 100 | 100 | % | 100 | 12.9% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
955 | Reinforcement Bar Fixing |  | 3 | 3 | 2024-01-10 | 2024-01-12 | 100 | 100 | % | 100 | 9.677% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
956 | Formwork Fixing |  | 4 | 4 | 2024-01-13 | 2024-01-16 | 100 | 100 | % | 100 | 12.9% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
957 | Concrete Pouring |  | 3 | 3 | 2024-01-16 | 2024-01-18 | 100 | 100 | % | 100 | 9.677% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
958 | Formwork Dismantling |  | 4 | 4 | 2024-01-19 | 2024-01-22 | 100 | 100 | % | 100 | 12.9% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
959 | Backfill with compaction |  | 4 | 4 | 2024-01-20 | 2024-01-23 | 100 | 100 | % | 100 | 12.9% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
960 | Completion of Pile Cap |  | 0 | 1 | 2024-01-23 | 2024-01-23 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
961 | Stump |  | 42 | 20 | 2024-01-18 | 2024-02-06 |  |  |  |  | 57.53% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 2.381% |  | 38.1% |  | 78.57% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
962 | Reinforcement Bar Fixing |  | 7 | 7 | 2024-01-18 | 2024-01-24 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
963 | Formwork Fixing |  | 7 | 7 | 2024-01-20 | 2024-01-26 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
964 | Anchor Bolt Fixing |  | 7 | 7 | 2024-01-23 | 2024-01-29 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
965 | Concrete Pouring |  | 7 | 7 | 2024-01-26 | 2024-02-01 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
966 | Formwork Dismantling |  | 7 | 7 | 2024-01-30 | 2024-02-05 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
967 | Backfill with compaction |  | 7 | 7 | 2024-01-31 | 2024-02-06 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 28.5714 | 28.57% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
968 | Completion of Stump |  | 0 | 1 | 2024-02-06 | 2024-02-06 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
969 | Completion of F3405 A/B/C |  | 0 | 1 | 2024-02-06 | 2024-02-06 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
970 | D3401 AB and D3402 AB |  | 30 | 23 | 2024-01-31 | 2024-02-22 |  |  |  |  | 17.14% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 6.667% |  | 46.67% |  | 73.33% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
971 | Pile Cap and Ground Beam |  | 30 | 23 | 2024-01-31 | 2024-02-22 |  |  |  |  | 100% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 6.667% |  | 46.67% |  | 73.33% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
972 | Excavation |  | 3 | 3 | 2024-01-31 | 2024-02-02 | 100 | 100 | % | 100 | 10% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
973 | Leveling and Compaction |  | 4 | 4 | 2024-02-02 | 2024-02-05 | 100 | 100 | % | 100 | 13.33% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
974 | Lean Concrete Pouring |  | 4 | 4 | 2024-02-03 | 2024-02-06 | 100 | 100 | % | 100 | 13.33% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
975 | Pile Cutting and Treatment |  | 3 | 3 | 2024-02-06 | 2024-02-08 | 100 | 100 | % | 100 | 10% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
976 | Reinforcement Bar Fixing |  | 4 | 4 | 2024-02-09 | 2024-02-12 | 100 | 100 | % | 100 | 13.33% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
977 | Formwork Fixing |  | 3 | 3 | 2024-02-13 | 2024-02-15 | 100 | 100 | % | 100 | 10% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
978 | Concrete Pouring |  | 3 | 3 | 2024-02-15 | 2024-02-17 | 100 | 100 | % | 100 | 10% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
979 | Formwork Dismantling |  | 3 | 3 | 2024-02-19 | 2024-02-21 | 100 | 100 | % | 100 | 10% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
980 | Backfill with compaction |  | 3 | 3 | 2024-02-20 | 2024-02-22 | 100 | 100 | % | 100 | 10% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
981 | Completion of Pile Cap |  | 0 | 1 | 2024-02-22 | 2024-02-22 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
982 | Completion of D3401 AB and D3402 AB |  | 0 | 1 | 2024-02-22 | 2024-02-22 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
983 | Completion of Compressor / Equipment and Pump Foundation |  | 0 | 1 | 2024-02-22 | 2024-02-22 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
984 | Completion of Substructure |  | 0 | 1 | 2024-02-22 | 2024-02-22 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
985 | Completion of Unit 340 - Instrument Air & Plant Air System |  | 0 | 1 | 2024-02-22 | 2024-02-22 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
986 | Unit 350 - Nitrogen System |  | 431 | 78 | 2023-12-13 | 2024-02-28 |  |  |  |  | 17.44% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.464% |  | 2.088% |  | 5.104% |  | 12.53% |  | 24.13% |  | 36.43% |  | 57.31% |  | 75.17% |  | 90.02% |  | 95.82% |  | 98.14% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
987 | Piling (Cutting only) |  | 14 | 14 | 2023-12-13 | 2023-12-26 |  |  |  |  | 3.248% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 14.29% |  | 64.29% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
988 | Cutting off Pile to GL |  | 14 | 14 | 2023-12-13 | 2023-12-26 | 100 | 100 | % | 100 | 100% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 64.2857 | 64.29% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
989 | Completion of Piling |  | 0 | 1 | 2023-12-26 | 2023-12-26 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
990 | Substructure |  | 417 | 64 | 2023-12-27 | 2024-02-28 |  |  |  |  | 96.75% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 1.918% |  | 9.592% |  | 21.58% |  | 34.29% |  | 55.88% |  | 74.34% |  | 89.69% |  | 95.68% |  | 98.08% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
991 | Equipment Foundation |  | 417 | 64 | 2023-12-27 | 2024-02-28 |  |  |  |  | 100% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 1.918% |  | 9.592% |  | 21.58% |  | 34.29% |  | 55.88% |  | 74.34% |  | 89.69% |  | 95.68% |  | 98.08% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
992 | V3506 / V3507 and V3508 |  | 40 | 42 | 2023-12-27 | 2024-02-06 |  |  |  |  | 9.592% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 10% |  | 37.5% |  | 52.5% |  | 70% |  | 85% |  | 90% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
993 | Excavation |  | 6 | 6 | 2023-12-27 | 2024-01-01 | 100 | 100 | % | 100 | 15% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
994 | Leveling and Compaction |  | 6 | 6 | 2023-12-27 | 2024-01-01 | 100 | 100 | % | 100 | 15% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
995 | Lean Concrete Pouring |  | 2 | 2 | 2024-01-02 | 2024-01-03 | 100 | 100 | % | 100 | 5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
996 | Pile Cutting and Treatment |  | 3 | 3 | 2024-01-04 | 2024-01-06 | 100 | 100 | % | 100 | 7.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
997 | Reinforcement Bar Fixing |  | 11 | 11 | 2024-01-08 | 2024-01-18 | 100 | 100 | % | 100 | 27.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 36.3636 | 36.36% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
998 | Formwork Fixing |  | 2 | 2 | 2024-01-19 | 2024-01-20 | 100 | 100 | % | 100 | 5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
999 | Anchor Bolt / Inserted Plate Fixing |  | 2 | 2 | 2024-01-22 | 2024-01-23 | 100 | 100 | % | 100 | 5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1000 | Concrete Pouring |  | 3 | 3 | 2024-01-24 | 2024-01-26 | 100 | 100 | % | 100 | 7.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1001 | Formwork Dismantling |  | 1 | 1 | 2024-01-31 | 2024-01-31 | 100 | 100 | % | 100 | 2.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1002 | Backfill with compaction |  | 4 | 4 | 2024-02-03 | 2024-02-06 | 100 | 100 | % | 100 | 10% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1003 | Completion of V3506 / V3507 and V3508 |  | 0 | 1 | 2024-02-06 | 2024-02-06 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1004 | V3507 and V3508 |  | 44 | 45 | 2024-01-02 | 2024-02-15 |  |  |  |  | 10.55% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 13.64% |  | 38.64% |  | 52.27% |  | 68.18% |  | 81.82% |  | 90.91% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
1005 | Excavation |  | 7 | 7 | 2024-01-02 | 2024-01-08 | 100 | 100 | % | 100 | 15.91% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1006 | Leveling and Compaction |  | 7 | 7 | 2024-01-02 | 2024-01-08 | 100 | 100 | % | 100 | 15.91% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1007 | Lean Concrete Pouring |  | 2 | 2 | 2024-01-09 | 2024-01-10 | 100 | 100 | % | 100 | 4.545% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1008 | Pile Cutting and Treatment |  | 3 | 3 | 2024-01-11 | 2024-01-13 | 100 | 100 | % | 100 | 6.818% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1009 | Reinforcement Bar Fixing |  | 13 | 13 | 2024-01-15 | 2024-01-27 | 100 | 100 | % | 100 | 29.55% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 30.7692 | 30.77% | 84.6154 | 84.62% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1010 | Formwork Fixing |  | 2 | 2 | 2024-01-29 | 2024-01-30 | 100 | 100 | % | 100 | 4.545% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1011 | Anchor Bolt / Inserted Plate Fixing |  | 2 | 2 | 2024-01-31 | 2024-02-01 | 100 | 100 | % | 100 | 4.545% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1012 | Concrete Pouring |  | 4 | 4 | 2024-02-02 | 2024-02-05 | 100 | 100 | % | 100 | 9.091% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1013 | Formwork Dismantling |  | 1 | 1 | 2024-02-09 | 2024-02-09 | 100 | 100 | % | 100 | 2.273% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1014 | Backfill with compaction |  | 3 | 3 | 2024-02-13 | 2024-02-15 | 100 | 100 | % | 100 | 6.818% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1015 | Completion of V3501 A and V3501 B |  | 0 | 1 | 2024-02-15 | 2024-02-15 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1016 | V3501 A and V3501 B |  | 40 | 42 | 2024-01-09 | 2024-02-19 |  |  |  |  | 9.592% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 15% |  | 35% |  | 52.5% |  | 70% |  | 87.5% |  | 90% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
1017 | Excavation |  | 5 | 5 | 2024-01-09 | 2024-01-13 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 60 | 60% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1018 | Leveling and Compaction |  | 5 | 5 | 2024-01-09 | 2024-01-13 | 100 | 100 | % | 100 | 12.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 60 | 60% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1019 | Lean Concrete Pouring |  | 2 | 2 | 2024-01-15 | 2024-01-16 | 100 | 100 | % | 100 | 5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1020 | Pile Cutting and Treatment |  | 3 | 3 | 2024-01-17 | 2024-01-19 | 100 | 100 | % | 100 | 7.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1021 | Reinforcement Bar Fixing |  | 12 | 12 | 2024-01-20 | 2024-01-31 | 100 | 100 | % | 100 | 30% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 50 | 50% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1022 | Formwork Fixing |  | 2 | 2 | 2024-02-01 | 2024-02-02 | 100 | 100 | % | 100 | 5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 50 | 50% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1023 | Anchor Bolt / Inserted Plate Fixing |  | 3 | 3 | 2024-02-03 | 2024-02-05 | 100 | 100 | % | 100 | 7.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1024 | Concrete Pouring |  | 3 | 3 | 2024-02-06 | 2024-02-08 | 100 | 100 | % | 100 | 7.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1025 | Formwork Dismantling |  | 1 | 1 | 2024-02-13 | 2024-02-13 | 100 | 100 | % | 100 | 2.5% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1026 | Backfill with compaction |  | 4 | 4 | 2024-02-16 | 2024-02-19 | 100 | 100 | % | 100 | 10% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1027 | Completion of V3501 A and V3501 B |  | 0 | 1 | 2024-02-19 | 2024-02-19 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1028 | EX3501 A/B |  | 26 | 30 | 2024-01-15 | 2024-02-13 |  |  |  |  | 6.235% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 26.92% |  | 53.85% |  | 76.92% |  | 84.62% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
1029 | Excavation |  | 3 | 3 | 2024-01-15 | 2024-01-17 | 100 | 100 | % | 100 | 11.54% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1030 | Leveling and Compaction |  | 3 | 3 | 2024-01-15 | 2024-01-17 | 100 | 100 | % | 100 | 11.54% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1031 | Lean Concrete Pouring |  | 2 | 2 | 2024-01-18 | 2024-01-19 | 100 | 100 | % | 100 | 7.692% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 50 | 50% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1032 | Pile Cutting and Treatment |  | 3 | 3 | 2024-01-20 | 2024-01-22 | 100 | 100 | % | 100 | 11.54% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1033 | Reinforcement Bar Fixing |  | 7 | 7 | 2024-01-23 | 2024-01-29 | 100 | 100 | % | 100 | 26.92% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1034 | Formwork Fixing |  | 2 | 2 | 2024-01-30 | 2024-01-31 | 100 | 100 | % | 100 | 7.692% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1035 | Concrete Pouring |  | 1 | 1 | 2024-02-02 | 2024-02-02 | 100 | 100 | % | 100 | 3.846% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1036 | Formwork Dismantling |  | 1 | 1 | 2024-02-07 | 2024-02-07 | 100 | 100 | % | 100 | 3.846% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1037 | Backfill with compaction |  | 4 | 4 | 2024-02-10 | 2024-02-13 | 100 | 100 | % | 100 | 15.38% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1038 | Completion of EX3501 A/B |  | 0 | 1 | 2024-02-13 | 2024-02-13 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1039 | CU3501 and CU3502 |  | 33 | 38 | 2024-01-18 | 2024-02-24 |  |  |  |  | 7.914% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 6.061% |  | 39.39% |  | 57.58% |  | 78.79% |  | 87.88% |  | 93.94% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
1040 | Excavation |  | 5 | 5 | 2024-01-18 | 2024-01-22 | 100 | 100 | % | 100 | 15.15% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 20 | 20% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1041 | Leveling and Compaction |  | 5 | 5 | 2024-01-18 | 2024-01-22 | 100 | 100 | % | 100 | 15.15% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 20 | 20% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1042 | Lean Concrete Pouring |  | 2 | 2 | 2024-01-23 | 2024-01-24 | 100 | 100 | % | 100 | 6.061% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1043 | Pile Cutting and Treatment |  | 3 | 3 | 2024-01-25 | 2024-01-27 | 100 | 100 | % | 100 | 9.091% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1044 | Reinforcement Bar Fixing |  | 9 | 9 | 2024-01-29 | 2024-02-06 | 100 | 100 | % | 100 | 27.27% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 44.4444 | 44.44% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1045 | Formwork Fixing |  | 4 | 4 | 2024-02-07 | 2024-02-10 | 100 | 100 | % | 100 | 12.12% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 50 | 50% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1046 | Concrete Pouring |  | 1 | 1 | 2024-02-14 | 2024-02-14 | 100 | 100 | % | 100 | 3.03% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1047 | Formwork Dismantling |  | 1 | 1 | 2024-02-19 | 2024-02-19 | 100 | 100 | % | 100 | 3.03% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1048 | Backfill with compaction |  | 3 | 3 | 2024-02-22 | 2024-02-24 | 100 | 100 | % | 100 | 9.091% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1049 | Completion of EX3501 A/B |  | 0 | 1 | 2024-02-24 | 2024-02-24 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1050 | K3501 |  | 33 | 37 | 2024-01-23 | 2024-02-28 |  |  |  |  | 7.914% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 18.18% |  | 42.42% |  | 63.64% |  | 81.82% |  | 90.91% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
1051 | Excavation |  | 4 | 4 | 2024-01-23 | 2024-01-26 | 100 | 100 | % | 100 | 12.12% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 75 | 75% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1052 | Leveling and Compaction |  | 4 | 4 | 2024-01-23 | 2024-01-26 | 100 | 100 | % | 100 | 12.12% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 75 | 75% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1053 | Lean Concrete Pouring |  | 3 | 3 | 2024-01-27 | 2024-01-29 | 100 | 100 | % | 100 | 9.091% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1054 | Pile Cutting and Treatment |  | 3 | 3 | 2024-01-30 | 2024-02-01 | 100 | 100 | % | 100 | 9.091% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1055 | Reinforcement Bar Fixing |  | 9 | 9 | 2024-02-02 | 2024-02-10 | 100 | 100 | % | 100 | 27.27% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 77.7778 | 77.78% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1056 | Formwork Fixing |  | 4 | 4 | 2024-02-12 | 2024-02-15 | 100 | 100 | % | 100 | 12.12% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1057 | Anchor Bolt / Inserted Plate Fixing |  | 2 | 2 | 2024-02-16 | 2024-02-17 | 100 | 100 | % | 100 | 6.061% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1058 | Concrete Pouring |  | 1 | 1 | 2024-02-19 | 2024-02-19 | 100 | 100 | % | 100 | 3.03% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1059 | Formwork Dismantling |  | 1 | 1 | 2024-02-23 | 2024-02-23 | 100 | 100 | % | 100 | 3.03% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1060 | Backfill with compaction |  | 2 | 2 | 2024-02-27 | 2024-02-28 | 100 | 100 | % | 100 | 6.061% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1061 | Completion of K3501 |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1062 | MS3501A/B HT3501 CPK3501 and SIL3501 |  | 57 | 64 | 2023-12-27 | 2024-02-28 |  |  |  |  | 13.67% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 7.018% |  | 21.05% |  | 33.33% |  | 45.61% |  | 57.89% |  | 70.18% |  | 82.46% |  | 92.98% |  | 94.74% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
1063 | Foundation |  | 33 | 30 | 2023-12-27 | 2024-01-25 |  |  |  |  | 57.89% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 12.12% |  | 36.36% |  | 57.58% |  | 78.79% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
1064 | Excavation |  | 4 | 4 | 2023-12-27 | 2023-12-30 | 100 | 100 | % | 100 | 12.12% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 50 | 50% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1065 | Leveling and Compaction |  | 4 | 4 | 2023-12-27 | 2023-12-30 | 100 | 100 | % | 100 | 12.12% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 50 | 50% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1066 | Lean Concrete Pouring |  | 2 | 2 | 2024-01-01 | 2024-01-02 | 100 | 100 | % | 100 | 6.061% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1067 | Reinforcement Bar Fixing |  | 14 | 14 | 2024-01-03 | 2024-01-16 | 100 | 100 | % | 100 | 42.42% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 64.2857 | 64.29% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1068 | Anchor Bolt / Inserted Plate Fixing |  | 3 | 3 | 2024-01-17 | 2024-01-19 | 100 | 100 | % | 100 | 9.091% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1069 | Formwork Fixing |  | 5 | 5 | 2024-01-20 | 2024-01-24 | 100 | 100 | % | 100 | 15.15% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1070 | Concrete Pouring |  | 1 | 1 | 2024-01-25 | 2024-01-25 | 100 | 100 | % | 100 | 3.03% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1071 | Plinth |  | 21 | 22 | 2024-01-26 | 2024-02-16 |  |  |  |  | 36.84% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 33.33% |  | 66.67% |  | 95.24% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
1072 | Reinforcement Bar Fixing |  | 11 | 11 | 2024-01-26 | 2024-02-05 | 100 | 100 | % | 100 | 52.38% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 63.6364 | 63.64% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1073 | Formwork Fixing |  | 5 | 5 | 2024-02-06 | 2024-02-10 | 100 | 100 | % | 100 | 23.81% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 60 | 60% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1074 | Anchor Bolt / Inserted Plate Fixing |  | 3 | 3 | 2024-02-12 | 2024-02-14 | 100 | 100 | % | 100 | 14.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1075 | Concrete Pouring |  | 2 | 2 | 2024-02-15 | 2024-02-16 | 100 | 100 | % | 100 | 9.524% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 50 | 50% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1076 | Formwork Dismantling |  | 1 | 1 | 2024-02-26 | 2024-02-26 | 100 | 100 | % | 100 | 1.754% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1077 | Backfill with compaction |  | 2 | 2 | 2024-02-27 | 2024-02-28 | 100 | 100 | % | 100 | 3.509% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1078 | Completion of MS3501A/B HT3501 CPK3501 & SIL3501 |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1079 | CPK3503 |  | 73 | 37 | 2024-01-01 | 2024-02-06 |  |  |  |  | 17.51% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 8.219% |  | 20.55% |  | 32.88% |  | 64.38% |  | 87.67% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
1080 | Foundation |  | 31 | 23 | 2024-01-01 | 2024-01-23 |  |  |  |  | 42.47% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 19.35% |  | 48.39% |  | 74.19% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
1081 | Excavation |  | 3 | 3 | 2024-01-01 | 2024-01-03 | 100 | 100 | % | 100 | 9.677% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1082 | Leveling and Compaction |  | 3 | 3 | 2024-01-03 | 2024-01-05 | 100 | 100 | % | 100 | 9.677% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1083 | Lean Concrete Pouring |  | 3 | 3 | 2024-01-04 | 2024-01-06 | 100 | 100 | % | 100 | 9.677% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1084 | Pile Cutting and Treatment |  | 4 | 4 | 2024-01-06 | 2024-01-09 | 100 | 100 | % | 100 | 12.9% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1085 | Reinforcement Bar Fixing |  | 3 | 3 | 2024-01-10 | 2024-01-12 | 100 | 100 | % | 100 | 9.677% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1086 | Formwork Fixing |  | 4 | 4 | 2024-01-13 | 2024-01-16 | 100 | 100 | % | 100 | 12.9% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1087 | Concrete Pouring |  | 3 | 3 | 2024-01-16 | 2024-01-18 | 100 | 100 | % | 100 | 9.677% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1088 | Formwork Dismantling |  | 4 | 4 | 2024-01-19 | 2024-01-22 | 100 | 100 | % | 100 | 12.9% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1089 | Backfill with compaction |  | 4 | 4 | 2024-01-20 | 2024-01-23 | 100 | 100 | % | 100 | 12.9% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1090 | Completion of Pile Cap |  | 0 | 1 | 2024-01-23 | 2024-01-23 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1091 | Stump / Plinth |  | 42 | 20 | 2024-01-18 | 2024-02-06 |  |  |  |  | 57.53% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 2.381% |  | 38.1% |  | 78.57% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
1092 | Reinforcement Bar Fixing |  | 7 | 7 | 2024-01-18 | 2024-01-24 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1093 | Formwork Fixing |  | 7 | 7 | 2024-01-20 | 2024-01-26 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1094 | Anchor Bolt Fixing |  | 7 | 7 | 2024-01-23 | 2024-01-29 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1095 | Concrete Pouring |  | 7 | 7 | 2024-01-26 | 2024-02-01 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1096 | Formwork Dismantling |  | 7 | 7 | 2024-01-30 | 2024-02-05 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1097 | Backfill with compaction |  | 7 | 7 | 2024-01-31 | 2024-02-06 | 100 | 100 | % | 100 | 16.67% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 28.5714 | 28.57% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1098 | Completion of Stump |  | 0 | 1 | 2024-02-06 | 2024-02-06 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1099 | Completion of CPK3503 |  | 0 | 1 | 2024-02-06 | 2024-02-06 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1100 | E3501, E3505 and E3506 |  | 71 | 37 | 2024-01-04 | 2024-02-09 |  |  |  |  | 17.03% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 1.408% |  | 16.9% |  | 26.76% |  | 49.3% |  | 74.65% |  | 98.59% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
1101 | Foundation |  | 30 | 23 | 2024-01-04 | 2024-01-26 |  |  |  |  | 42.25% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 3.333% |  | 40% |  | 63.33% |  | 96.67% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
1102 | Excavation |  | 3 | 3 | 2024-01-04 | 2024-01-06 | 100 | 100 | % | 100 | 10% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 33.3333 | 33.33% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1103 | Leveling and Compaction |  | 4 | 4 | 2024-01-06 | 2024-01-09 | 100 | 100 | % | 100 | 13.33% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1104 | Lean Concrete Pouring |  | 3 | 3 | 2024-01-08 | 2024-01-10 | 100 | 100 | % | 100 | 10% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1105 | Pile Cutting and Treatment |  | 3 | 3 | 2024-01-10 | 2024-01-12 | 100 | 100 | % | 100 | 10% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1106 | Reinforcement Bar Fixing |  | 4 | 4 | 2024-01-13 | 2024-01-16 | 100 | 100 | % | 100 | 13.33% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1107 | Formwork Fixing |  | 3 | 3 | 2024-01-17 | 2024-01-19 | 100 | 100 | % | 100 | 10% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1108 | Concrete Pouring |  | 4 | 4 | 2024-01-19 | 2024-01-22 | 100 | 100 | % | 100 | 13.33% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1109 | Formwork Dismantling |  | 3 | 3 | 2024-01-23 | 2024-01-25 | 100 | 100 | % | 100 | 10% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1110 | Backfill with compaction |  | 3 | 3 | 2024-01-24 | 2024-01-26 | 100 | 100 | % | 100 | 10% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1111 | Completion of Pile Cap |  | 0 | 1 | 2024-01-26 | 2024-01-26 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1112 | Stump / Plinth |  | 41 | 19 | 2024-01-22 | 2024-02-09 |  |  |  |  | 57.75% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 14.63% |  | 56.1% |  | 97.56% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
1113 | Reinforcement Bar Fixing |  | 6 | 6 | 2024-01-22 | 2024-01-27 | 100 | 100 | % | 100 | 14.63% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1114 | Formwork Fixing |  | 7 | 7 | 2024-01-24 | 2024-01-30 | 100 | 100 | % | 100 | 17.07% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 28.5714 | 28.57% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1115 | Anchor Bolt Fixing |  | 7 | 7 | 2024-01-26 | 2024-02-01 | 100 | 100 | % | 100 | 17.07% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1116 | Concrete Pouring |  | 7 | 7 | 2024-01-30 | 2024-02-05 | 100 | 100 | % | 100 | 17.07% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1117 | Formwork Dismantling |  | 7 | 7 | 2024-02-02 | 2024-02-08 | 100 | 100 | % | 100 | 17.07% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1118 | Backfill with compaction |  | 7 | 7 | 2024-02-03 | 2024-02-09 | 100 | 100 | % | 100 | 17.07% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 85.7143 | 85.71% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1119 | Completion of Stump |  | 0 | 1 | 2024-02-09 | 2024-02-09 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1120 | Completion of E3501, E3505 and E3506 |  | 0 | 1 | 2024-02-09 | 2024-02-09 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1121 | Completion of Equipment and Pump Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1122 | Completion of Substructure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1123 | Completion of Unit 340 - Instrument Air & Plant Air System |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1124 | Unit 380 - Excess Steam Recovery System |  | 216 | 58 | 2023-12-27 | 2024-02-22 |  |  |  |  | 8.741% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0.9259% |  | 4.167% |  | 11.11% |  | 26.39% |  | 42.59% |  | 60.65% |  | 78.24% |  | 93.06% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
1125 | Piling (Cutting only) |  | 9 | 9 | 2023-12-27 | 2024-01-04 |  |  |  |  | 4.167% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 22.22% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
1126 | Cutting off Pile to GL |  | 9 | 9 | 2023-12-27 | 2024-01-04 | 100 | 100 | % | 100 | 100% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 22.2222 | 22.22% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1127 | Completion of Piling |  | 0 | 1 | 2024-01-04 | 2024-01-04 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1128 | Substructure |  | 207 | 49 | 2024-01-05 | 2024-02-22 |  |  |  |  | 95.83% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 7.246% |  | 23.19% |  | 40.1% |  | 58.94% |  | 77.29% |  | 92.75% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
1129 | Structure |  | 207 | 49 | 2024-01-05 | 2024-02-22 |  |  |  |  | 100% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 7.246% |  | 23.19% |  | 40.1% |  | 58.94% |  | 77.29% |  | 92.75% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
1130 | Pile Raft |  | 124 | 34 | 2024-01-05 | 2024-02-07 |  |  |  |  | 59.9% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 12.1% |  | 38.71% |  | 66.94% |  | 90.32% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
1131 | Excavation |  | 14 | 14 | 2024-01-05 | 2024-01-18 | 100 | 100 | % | 100 | 11.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 50 | 50% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1132 | Leveling and Compaction |  | 13 | 13 | 2024-01-08 | 2024-01-20 | 100 | 100 | % | 100 | 10.48% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 30.7692 | 30.77% | 84.6154 | 84.62% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1133 | Lean Concrete Pouring |  | 14 | 14 | 2024-01-09 | 2024-01-22 | 100 | 100 | % | 100 | 11.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 21.4286 | 21.43% | 71.4286 | 71.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1134 | Pile Cutting and Treatment |  | 14 | 14 | 2024-01-11 | 2024-01-24 | 100 | 100 | % | 100 | 11.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.1429 | 7.143% | 57.1429 | 57.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1135 | Reinforcement Bar Fixing |  | 13 | 13 | 2024-01-15 | 2024-01-27 | 100 | 100 | % | 100 | 10.48% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 30.7692 | 30.77% | 84.6154 | 84.62% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1136 | Formwork Fixing |  | 14 | 14 | 2024-01-18 | 2024-01-31 | 100 | 100 | % | 100 | 11.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.1429 | 7.143% | 57.1429 | 57.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1137 | Concrete Pouring |  | 14 | 14 | 2024-01-20 | 2024-02-02 | 100 | 100 | % | 100 | 11.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 92.8571 | 92.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1138 | Formwork Dismantling |  | 14 | 14 | 2024-01-24 | 2024-02-06 | 100 | 100 | % | 100 | 11.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 14.2857 | 14.29% | 64.2857 | 64.29% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1139 | Backfill with compaction |  | 14 | 14 | 2024-01-25 | 2024-02-07 | 100 | 100 | % | 100 | 11.29% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.1429 | 7.143% | 57.1429 | 57.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1140 | Completion of Pile Cap |  | 0 | 1 | 2024-02-07 | 2024-02-07 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1141 | Stump |  | 83 | 27 | 2024-01-27 | 2024-02-22 |  |  |  |  | 40.1% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 12.05% |  | 43.37% |  | 81.93% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
1142 | Reinforcement Bar Fixing |  | 14 | 14 | 2024-01-27 | 2024-02-09 | 100 | 100 | % | 100 | 16.87% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 42.8571 | 42.86% | 92.8571 | 92.86% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1143 | Formwork Fixing |  | 14 | 14 | 2024-01-30 | 2024-02-12 | 100 | 100 | % | 100 | 16.87% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 21.4286 | 21.43% | 71.4286 | 71.43% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1144 | Anchor Bolt Fixing |  | 14 | 14 | 2024-02-01 | 2024-02-14 | 100 | 100 | % | 100 | 16.87% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.1429 | 7.143% | 57.1429 | 57.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1145 | Concrete Pouring |  | 13 | 13 | 2024-02-05 | 2024-02-17 | 100 | 100 | % | 100 | 15.66% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 30.7692 | 30.77% | 84.6154 | 84.62% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1146 | Formwork Dismantling |  | 14 | 14 | 2024-02-08 | 2024-02-21 | 100 | 100 | % | 100 | 16.87% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.1429 | 7.143% | 57.1429 | 57.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1147 | Backfill with compaction |  | 14 | 14 | 2024-02-09 | 2024-02-22 | 100 | 100 | % | 100 | 16.87% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 50 | 50% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1148 | Completion of Stump |  | 0 | 1 | 2024-02-22 | 2024-02-22 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1149 | Completion of Structure |  | 0 | 1 | 2024-02-22 | 2024-02-22 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1150 | Completion of Substructure |  | 0 | 1 | 2024-02-22 | 2024-02-22 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1151 | Completion of Unit 380 - Excess Steam Recovery System |  | 0 | 1 | 2024-02-22 | 2024-02-22 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1152 | Unit 510 - Fire Water Tank |  | 75 | 55 | 2024-01-05 | 2024-02-28 |  |  |  |  | 3.035% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 9.333% |  | 32% |  | 58.67% |  | 70.67% |  | 84% |  | 92% |  | 96% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
1153 | Piling (Cutting only) |  | 7 | 7 | 2024-01-05 | 2024-01-11 |  |  |  |  | 9.333% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
1154 | Cutting off Pile to GL |  | 7 | 7 | 2024-01-05 | 2024-01-11 | 100 | 100 | % | 100 | 100% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1155 | Completion of Piling |  | 0 | 1 | 2024-01-11 | 2024-01-11 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1156 | Substructure |  | 68 | 48 | 2024-01-12 | 2024-02-28 |  |  |  |  | 90.67% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 25% |  | 54.41% |  | 67.65% |  | 82.35% |  | 91.18% |  | 95.59% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
1157 | Tank / Equipment and Pump Foundation |  | 68 | 48 | 2024-01-12 | 2024-02-28 |  |  |  |  | 100% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 25% |  | 54.41% |  | 67.65% |  | 82.35% |  | 91.18% |  | 95.59% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
1158 | Fire Water Tank |  | 68 | 48 | 2024-01-12 | 2024-02-28 |  |  |  |  | 100% | 100% | 100% | 0% |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 25% |  | 54.41% |  | 67.65% |  | 82.35% |  | 91.18% |  | 95.59% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%
1159 | Excavation |  | 11 | 11 | 2024-01-12 | 2024-01-22 | 100 | 100 | % | 100 | 16.18% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 63.6364 | 63.64% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1160 | Leveling and Compaction |  | 11 | 11 | 2024-01-12 | 2024-01-22 | 100 | 100 | % | 100 | 16.18% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 63.6364 | 63.64% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1161 | Lean Concrete Pouring |  | 10 | 10 | 2024-01-16 | 2024-01-25 | 100 | 100 | % | 100 | 14.71% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 30 | 30% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1162 | Pile Cutting and Treatment |  | 6 | 6 | 2024-01-22 | 2024-01-27 | 100 | 100 | % | 100 | 8.824% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1163 | Reinforcement Bar Fixing |  | 14 | 14 | 2024-01-25 | 2024-02-07 | 100 | 100 | % | 100 | 20.59% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7.1429 | 7.143% | 57.1429 | 57.14% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1164 | Formwork Fixing |  | 6 | 6 | 2024-02-05 | 2024-02-10 | 100 | 100 | % | 100 | 8.824% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 66.6667 | 66.67% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1165 | Anchor Bolt / Inserted Plate Fixing |  | 3 | 3 | 2024-02-12 | 2024-02-14 | 100 | 100 | % | 100 | 4.412% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1166 | Concrete Pouring |  | 1 | 1 | 2024-02-15 | 2024-02-15 | 100 | 100 | % | 100 | 1.471% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1167 | Formwork Dismantling |  | 3 | 3 | 2024-02-20 | 2024-02-22 | 100 | 100 | % | 100 | 4.412% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1168 | Backfill with compaction |  | 3 | 3 | 2024-02-26 | 2024-02-28 | 100 | 100 | % | 100 | 4.412% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1169 | Completion of Fire Water Tank |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1170 | Completion of Tank / Equipment and Pump Foundation |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1171 | Completion of Substructure |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1172 | Completion of Unit 510 - Fire Water Tank |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1173 | COMPLETION OF OTHER UNIT (SUBSTRUCTURE) |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
1174 | MECHANICAL COMPLETION |  | 0 | 1 | 2024-02-28 | 2024-02-28 | 100 | 100 | % | 100 | 0% | 100% | 100% | 0% |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100%
| x | x | x | x | x | x | x | x | x | x | x | x | x | x |  |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x |  | x
Formulas:
Plan Start = MIN([Plan Start, row below]:F1037)
Plan Finish = MAX([Plan Finish, row below]:G1037)